## 1- Ex Ante Results
Statewide Quarterly Report Template
Tab 1: Ex Ante Results
Final (updated 7-22-2026)
ComEd Ex Ante Results - Section 8-103B/8-104 (EEPS) Programs
CY2026 Q2 |  | 2026 LRP |  | LE Forecast |  |  |  |  | Budget | LE Forecast
Section 8-103B/8-104 (EEPS) Program | Net Energy Savings Achieved YTD (MWh) | 2026 Original Plan Savings Goal (MWh)* | Approved Net Energy Savings Goal (MWh)** | Implementation Plan Savings Goal (MWh) | % Savings Achieved Compared to Implementation Plan Savings Goal | Program Costs YTD | Incentive Costs YTD*** | Non-Incentive Costs YTD*** | 2025 Original Plan Budget**** | 2025 Approved Budget***** | % of Costs YTD Compared to Approved Budget
Commercial & Industrial Programs
Incentives | 53134.64 | 184591.39 | 184591.39 | 153119.31 | 34.7% | 20091735.38 | 13461462.7046 | 6630272.6754 | 73251450 | 59602675.5568 | 33.71%
Standard | 48852.64 | 164991.39 | 164991.39 | 134198.31 | 36.4% | 17088885.47 | 11449553.2649 | 5639332.2051 | 62159975 | 48493483.3931 | 35.24%
Custom | 4282 | 19600 | 19600 | 18921 | 22.63% | 3002849.91 | 2011909.4397 | 990940.4703 | 11091475 | 11109192.1637 | 27.03%
Small Business | 90248.5 | 197722.6 | 197722.6 | 181228.58 | 49.8% | 38675114.71 | 25912326.8557 | 12762787.8543 | 80219888 | 75019198.5043 | 51.55%
Midstream/Upstream | 229042 | 253145 | 253145 | 313083 | 73.16% | 42752300.38 | 28644041.2546 | 14108259.1254 | 69633166 | 79138312.6604 | 54.02%
New Construction Bus/Pub | 1105 | 6800 | 6800 | 5168 | 21.38% | 966631.6 | 647643.172 | 318988.428 | 4049395 | 3698889.8622 | 26.13%
Industrial Systems | 16575 | 54500 | 54500 | 54964 | 30.16% | 5916442.06 | 3964016.1802 | 1952425.8798 | 16633320 | 16127115.24 | 36.69%
Retro-commissioning | 20699 | 39400 | 39400 | 43705 | 47.36% | 7426660.27 | 4975862.3809 | 2450797.8891 | 13853336 | 15152421.35 | 49.01%
Strategic Energy Management | 9704.86 | 47687 | 47687 | 47476.86 | 20.44% | 4115765.83 | 2757563.1061 | 1358202.7239 | 11428426 | 11403444.77 | 36.09%
Facility Assessments | N/A | N/A | N/A | N/A | N/A | 307001.23 | 205690.8241 | 101310.4059 | 1482130 | 1133331.3752 | 27.09%
Commercial Foodservice | 288.57 | 1500 | 1500 | 1499.57 | 19.24% | 151976.58 | 101824.3086 | 50152.2714 | 564155 | 563102.88 | 26.99%
Business Energy Analyzer | 7601.45 | 22000 | 22000 | 11636.81 | 65.32% | 24971.8 | 16731.106 | 8240.694 | 815189 | 694188.704 | 3.597%
Energy Usage Data System | N/A | N/A | N/A | N/A | N/A | 265204.54 | 177687.0418 | 87517.4982 | 558344 | 558344 | 47.5%
Energy Advising | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 975000 | 575000 | 0%
Electrification | 12444 | 23200 | 23200 | 28629.3377 | 43.47% | N/A | N/A | N/A | N/A | N/A | N/A
Business Outreach | N/A | N/A | N/A | N/A | N/A | 1776971.67 | 1190571.0189 | 586400.6511 | 5557311 | 5124695.0611 | 34.67%
Business General | N/A | N/A | N/A | N/A | N/A | 837.25 | 560.9575 | 276.2925 | 45898 | 638.25 | 131.2%
C&I Programs Subtotal | 440843.02 | 830545.99 | 830545.99 | 840510.4677 | 52.45% | 122471613.3 | 82055980.911 | 40415632.389 | 279067008 | 268791358.214 | 45.56%
C&I Private Sector Programs
Incentives - Private | 44486.9 | 148993.11 | 148993.11 | 118616.3 | 37.5% | 16589651.12 | 11115066.2504 | 5474584.8696 | 57265814 | 44755277.9917 | 37.07%
Standard - Private | 40800.9 | 131993.11 | 131993.11 | 104623.3 | 39% | 13965019.02 | 9356562.7434 | 4608456.2766 | 47653965 | 36020942.3913 | 38.77%
Custom - Private | 3686 | 17000 | 17000 | 13993 | 26.34% | 2624632.1 | 1758503.507 | 866128.593 | 9611849 | 8734335.6004 | 30.05%
Small Business - Private | 85212.66 | 173996 | 173996 | 160997.9 | 52.93% | 36088485.57 | 24179285.3319 | 11909200.2381 | 69877649 | 64773881.46 | 55.71%
Midstream Upstream - Private | 206619 | 225511 | 225511 | 265638 | 77.78% | 38948688.95 | 26095621.5965 | 12853067.3535 | 62675811 | 69298958.9668 | 56.2%
Midstream/Upstream Private - Electrification | 12444 | 23200 | 23200 | 23248.0293 | 53.53% | N/A | N/A | N/A | N/A | N/A | N/A
Industrial Systems - Private | 16575 | 54250 | 54250 | 54608 | 30.35% | 5845030.71 | 3916170.5757 | 1928860.1343 | 15801653 | 15805742.55 | 36.98%
Retro-commissioning - Private | 12016 | 25610 | 25610 | 27661 | 43.44% | 4510630.78 | 3022122.6226 | 1488508.1574 | 8989825 | 10280909.46 | 43.87%
Strategic Energy Management - Private | 8704.07 | 39103 | 39103 | 39103.07 | 22.26% | 3412655.12 | 2286478.9304 | 1126176.1896 | 9141299 | 9157990.47 | 37.26%
New Construction - Private | 904 | 5100 | 5100 | 3396 | 26.62% | 745872.89 | 499734.8363 | 246138.0537 | 3164042 | 2812922.4028 | 26.52%
New Construction - Private - Electrification | 0 | 0 | 0 | 5381.3084 | 0% | N/A | N/A | N/A | N/A | N/A | N/A
Facility Assessment - Private | N/A | N/A | N/A | N/A | N/A | 245666.23 | 164596.3741 | 81069.8559 | 1185705 | 906820.3022 | 27.09%
Energy Usage Data System - Private | N/A | N/A | N/A | N/A | N/A | 87360.93 | 58531.8231 | 28829.1069 | 558344 | 185864.66 | 47%
Energy Advising - Private | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 487500 | 287500 | 0%
Commercial Foodservice - Private | 262 | 1425 | 1425 | 1425 | 18.39% | 142623.16 | 95557.5172 | 47065.6428 | 536105 | 535053.17 | 26.66%
Business Energy Analyzer - Private | 6841.31 | 19800 | 19800 | 10473.11 | 65.32% | 18594.15 | 12458.0805 | 6136.0695 | 611393 | 520508.47 | 3.572%
Private Sector Outreach | N/A | N/A | N/A | N/A | N/A | 1524841.63 | 1021643.8921 | 503197.7379 | 4755090 | 4370865.3161 | 34.89%
Private Sector General | N/A | N/A | N/A | N/A | N/A | 837.25 | 560.9575 | 276.2925 | 45898 | 638.25 | 131.2%
C&I Programs - Private Sector Total | 394064.94 | 716988.11 | 716988.11 | 710547.7177 | 55.46% | 108160938.49 | 72467828.7883 | 35693109.7017 | 235096128 | 223692933.4695 | 48.35%
C&I Public Sector Programs
Incentives - Public | 8647.74 | 35598.28 | 35598.28 | 34503.01 | 25.06% | 3502084.26 | 2346396.4542 | 1155687.8058 | 15985636 | 14847397.5651 | 23.59%
Standard - Public | 8051.74 | 32998.28 | 32998.28 | 29575.01 | 27.22% | 3123866.45 | 2092990.5215 | 1030875.9285 | 14506010 | 12472541.0018 | 25.05%
Custom - Public | 596 | 2600 | 2600 | 4928 | 12.09% | 378217.81 | 253405.9327 | 124811.8773 | 1479626 | 2374856.5633 | 15.93%
Small Business - Public | 5035.84 | 23726.6 | 23726.6 | 20230.68 | 24.89% | 2586629.14 | 1733041.5238 | 853587.6162 | 10342239 | 10245317.0443 | 25.25%
Midstream/Upstream - Public | 22423 | 27634 | 27634 | 47445 | 47.26% | 3803611.43 | 2548419.6581 | 1255191.7719 | 6957355 | 9839353.6936 | 38.66%
Industrial Systems - Public | 0 | 250 | 250 | 356 | 0% | 71411.35 | 47845.6045 | 23565.7455 | 831667 | 321372.69 | 22.22%
Retro-commissioning - Public | 8683 | 13790 | 13790 | 16044 | 54.12% | 2916029.49 | 1953739.7583 | 962289.7317 | 4863511 | 4871511.89 | 59.86%
Strategic Energy Management - Public | 1000.79 | 8584 | 8584 | 8373.79 | 11.95% | 703110.71 | 471084.1757 | 232026.5343 | 2287127 | 2245454.3 | 31.31%
New Construction - Public | 201 | 1700 | 1700 | 1772 | 11.34% | 220758.71 | 147908.3357 | 72850.3743 | 885353 | 885967.4595 | 24.92%
Facility Assessments - Public | N/A | N/A | N/A | N/A | N/A | 61335 | 41094.45 | 20240.55 | 296425 | 226511.073 | 27.08%
Energy Usage Data System - Public | N/A | N/A | N/A | N/A | N/A | 177843.61 | 119155.2187 | 58688.3913 | - | 372479.34 | 47.75%
Energy Advising - Public | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 487500 | 287500 | 0%
Commercial Foodservice - Public | 26.57 | 75 | 75 | 74.57 | 35.63% | 9353.42 | 6266.7914 | 3086.6286 | 28050 | 28049.71 | 33.35%
Business Energy Analyzer - Public | 760.14 | 2200 | 2200 | 1163.7 | 65.32% | 6377.65 | 4273.0255 | 2104.6245 | 203796 | 173680.234 | 3.672%
Public Sector Outreach | N/A | N/A | N/A | N/A | N/A | 252130.04 | 168927.1268 | 83202.9132 | 802221 | 753829.745 | 33.45%
C&I Programs - Public Sector Total | 46778.08 | 113557.88 | 113557.88 | 129962.75 | 35.99% | 14310674.81 | 9588152.1227 | 4722522.6873 | 43970880 | 45098424.7445 | 31.73%
Residential and Income Eligible Programs
Home Energy Report | 44840 | 95011 | 95011 | 92263 | 48.6% | 3012641.99 | 2018470.1333 | 994171.8567 | 6207771 | 6072927.62 | 49.61%
Single-Family Upgrades | 2626 | 4116 | 4116 | 7242 | 36.26% | 3146597.96 | 2108220.6332 | 1038377.3268 | 7656058 | 7726964.431 | 40.72%
Multi-Family Upgrades | 7755.87 | 16079.2 | 16079.2 | 16076.33 | 48.24% | 11104608.11 | 7440087.4337 | 3664520.6763 | 27138389 | 27094831.3002 | 40.98%
Home Energy Products | 90468.52 | 163667.24 | 163667.24 | 195619.87 | 46.25% | 19886595.32 | 13324018.8644 | 6562576.4556 | 34866447 | 40442931.4342 | 49.17%
New Construction - Income Eligible | 2284.33 | 3818.92 | 3818.92 | 4688.94 | 48.72% | 813922.98 | 545328.3966 | 268594.5834 | 1888169 | 1874850.6025 | 43.41%
New Contruction - Electric | 481.94 | 824.01 | 824.01 | 972.49 | 49.56% | 141421.81 | 94752.6127 | 46669.1973 | 369750 | 369749.9986 | 38.25%
Heating and Cooling - Contractor/Midstream Rebates | 9504 | 22831 | 22831 | 22932 | 41.44% | 1866081.02 | 1250274.2834 | 615806.7366 | 4123950 | 4109724.07 | 45.41%
Whole Home Electric | 2068 | 14736 | 14736 | 14742 | 14.03% | 0 | 0 | 0 | 0 | 0
Electrification | 30576.7493 | 72025.8345 | 72025.8345 | 72535.8459 | 52.68% | 19578223.98 | 13117410.0666 | 6460813.9134 | 54145234 | 53112708.704 | 36.86%
Residential and IE General | N/A | N/A | N/A | N/A | N/A | 964289.75 | 646074.1325 | 318215.6175 | 2846499 | 2494803.25 | 38.65%
Residential and Income Eligible Programs Subtotal | 190605.4093 | 393109.2045 | 393109.2045 | 427072.4759 | 44.63% | 60514382.92 | 40544636.5564 | 19969746.3636 | 139242267 | 143299491.4106 | 42.23%
Residential Market Rate Programs
Residential Behavior - Home Energy Report | 44840 | 95011 | 95011 | 92263 | 48.6% | 3012641.99 | 2018470.1333 | 994171.8567 | 6207771 | 6072927.62 | 49.61%
Single-Family Upgrades – Home Energy Assessments - Market Rate | N/A | N/A | N/A | N/A | N/A | 7860.79 | 5266.7293 | 2594.0607 | - | 7860.79 | 100%
Home Energy Products - Market Rate (Includes Marketplace 2.0 Non-Lighting, School Kits, Retail, and Retail Products Platform) | 21725.34 | 49393.14 | 49393.14 | 43586.7 | 49.84% | 4673683.15 | 3131367.7105 | 1542315.4395 | 10170751 | 9336272.0125 | 50.06%
All-Electric New Construction | 481.94 | 824.01 | 824.01 | 972.49 | 49.56% | 141421.81 | 94752.6127 | 46669.1973 | 369750 | 369749.9986 | 38.25%
Heating and Cooling - Contractor/Midstream Rebates | 9504 | 22831 | 22831 | 22932 | 41.44% | 1866081.02 | 1250274.2834 | 615806.7366 | 4123950 | 4109724.07 | 45.41%
Residential General | N/A | N/A | N/A | N/A | N/A | 10129.52 | 6786.7784 | 3342.7416 | 135719 | 126541.97 | 8.005%
Home Energy Products - Market Rate - Electrification | 286.9248 | 545 | 545 | 566.1273 | 50.68% | 0 | 0 | 0 | 0 | 0 | N/A
All-Electric New Construction - Electrification | 636.0951 | 2179.0026 | 2179.0026 | 2048.6927 | 31.05% | 334184.28 | 223903.4676 | 110280.8124 | 1009409 | 1009408.5407 | 33.11%
Contractor/Midstream Rebates Electrification | 18454.5016 | 46168.4643 | 46168.4643 | 46310.585 | 39.85% | 3882141.02 | 2601034.4834 | 1281106.5366 | 8536063 | 8486709.32 | 45.74%
Residential Market Rate Subtotal | 95928.8015 | 216951.6168 | 216951.6168 | 208679.595 | 45.97% | 13928143.58 | 9331856.1986 | 4596287.3814 | 30553413 | 29519194.3219 | 47.18%
Income Qualified Programs
Single-Family Upgrades – Income Eligible Retrofits | 827 | 1623 | 1623 | 2026 | 40.82% | 2610900.97 | 1749303.6499 | 861597.3201 | 6663590 | 6156814.4776 | 42.41%
Single-Family Upgrades – Home Energy Assessments - IE | 1799 | 2493 | 2493 | 5216 | 34.49% | 527836.2 | 353650.254 | 174185.946 | 992468 | 1562289.1634 | 33.79%
Multi-Family Upgrades - Income Eligible | 7230 | 15234 | 15234 | 15250 | 47.41% | 9962933.79 | 6675165.6393 | 3287768.1507 | 24743493 | 24694608.4689 | 40.34%
Multi-Family Upgrades - Public Housing | 525.87 | 845.2 | 845.2 | 826.33 | 63.64% | 1141674.32 | 764921.7944 | 376752.5256 | 2394896 | 2400222.8313 | 47.57%
Home Energy Products - Income Eligible (Includes IE Kits/Food Bank, and Retail Dedicated and Undedicated) | 68743.18 | 114274.1 | 114274.1 | 152033.17 | 45.22% | 15212912.17 | 10192651.1539 | 5020261.0161 | 24695696 | 31106659.4217 | 48.91%
Affordable Housing New Construction | 2284.33 | 3818.92 | 3818.92 | 4688.94 | 48.72% | 813922.98 | 545328.3966 | 268594.5834 | 1888169 | 1874850.6025 | 43.41%
Whole Home Electric (Single Family Upgrades - IE) | 1311 | 2513 | 2513 | 2532 | 51.78% | 0 | 0 | 0 | 0 | 0 | N/A
Whole Home Electric (Multi Family Upgrades - IE) | 757 | 12223 | 12223 | 12210 | 6.2% | 0 | 0 | 0 | 0 | 0 | N/A
Home Energy Products - Income Eligible Electrification | 54.0302 | 94 | 94 | 102.5544 | 52.68% | 0 | 0 | 0 | 0 | 0 | N/A
Affordable Housing New Construction Electrification | 3882.4841 | 8509.067 | 8509.067 | 8642.1699 | 44.92% | 1446945.88 | 969453.7396 | 477492.1404 | 3356746 | 3333067.7933 | 43.41%
Whole Home Electric (Multi Family Upgrades Electrification - IE) | 2173.9772 | 5973.8476 | 5973.8476 | 6032.5874 | 36.04% | 4324407.9 | 2897353.293 | 1427054.607 | 21119629 | 20185087.89 | 21.42%
Whole Home Electric (Single Family Upgrades Electrification - IE) | 5088.7362 | 8556.453 | 8556.453 | 8833.1292 | 57.61% | 9590544.9 | 6425665.083 | 3164879.817 | 20123387 | 20098435.16 | 47.72%
IE General | N/A | N/A | N/A | N/A | N/A | 954160.23 | 639287.3541 | 314872.8759 | 2710780 | 2368261.28 | 40.29%
Income Qualified Programs Subtotal | 94676.6078 | 176157.5876 | 176157.5876 | 218392.8809 | 43.35% | 46586239.34 | 31212780.3578 | 15373458.9822 | 108688854 | 113780297.0888 | 40.94%
Demonstration of Breakthrough Equipment and Devices
Emerging Technology/R&D | 0 | 7355 | 7355 | 500 | 0% | 3316530.5 | 2222075.435 | 1094455.065 | 10012109 | 8876648.78 | 37.36%
Voltage Optimization | 19568 | 67241.01 | 67241.01 | 70762 | 27.65% | 0 | 0 | 0 | 0 | 0 | N/A
Customer Journey Optimization | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0 | 102796 | 0 | N/A
Demonstration of Breakthrough Equipment and Devices Subtotal | 19568 | 74596.01 | 74596.01 | 71262 | 27.46% | 3316530.5 | 2222075.435 | 1094455.065 | 10114905 | 8876648.78 | 37.36%
Additional/Other Claimable Savings****** | 0 | 1000 | 1000 | 1000 | 0% | N/A | N/A | N/A | N/A | N/A | N/A
Other Fuel (Therm) Conversion | 141075 | 141075 | 141075 | 141075 | 100% | N/A | N/A | N/A | N/A | N/A | N/A
Lighting Carryover | 0 | 607.64 | 607.64 | 607.64 | 0% | N/A | N/A | N/A | N/A | N/A | N/A
Overall Total ComEd Section 8-103B/8-104 (EEPS) Programs | 792091.4293 | 1440933.8445 | 1440933.8445 | 1481527.5836 | 53.46% | 186302526.72 | 124822692.9024 | 61479833.8176 | 428424180 | 420967498.4047 | 44.26%
Footnotes:
*Original Plan Savings Goal refers to the original savings goal approved in the Commission's Final Order approving the EE Plan. For Section 8-104 programs, this value should match the Plan Energy Savings Goal set forth in the completed Adjustable Savings Goal Template. Subject to change.
**The Approved Net Energy Savings Goal refers to the most updated portfolio-level savings goal. In the case of Section 8-104 programs, the values in this column should match the Adjusted Energy Savings Goal contained in the Program Administrator's updated Adjustable Savings Goal Template.
***Because actual incentive costs are not available until year-end, estimates are provided in the Incentive Costs YTD column for Q1. A blended rate of 67% is applied to all programs that typically have incentive costs; this excludes behavioral programs, voltage optimization, emerging technology, market transformation, outreach, general, and portfolio-level costs.
****Original Plan Budget refers to the budget contained in the approved EE Plan, which could be the original filed EE Plan or a compliance EE Plan.
*****Approved Budget refers to the Program Administrator's current budget for this Program Year, that may have been modified in light of the flexibility policy. This may also be the Implementation Plan Budget.

## 2- Costs
Statewide Quarterly Report Template
Tab 2: Costs
Instructions: *For Program and Portfolio-Level Costs, each Program Administrator should include actual costs incurred from the beginning of the Program Year through the end of the applicable quarter, regardless of what Program Year the costs are associated with. *Program Administrators should add a footnote specifying if there are non-rider energy efficiency costs that are not reported in the Quarterly Reports.
ComEd Section 8-103B/8-104 (EEPS) Costs as of
CY2026 Q2
Section 8-103B/8-104 (EEPS) Cost Category | 2026 Actual Costs YTD
Program Costs by Sector
C&I Programs Private Sector | 108160938.49
C&I Programs Public Sector | 14310674.81
Residential (Market Rate) Programs | 13928143.58
Income Qualified Programs | 46586239.34
Total ComEd Program Costs | 182985996.22
Portfolio-Level Costs by Portfolio Cost Category (Section 8-103B/8-104 EEPS)
Demonstration of Breakthrough Equipment and Devices Costs | 3316530.5
Evaluation Costs | 4729615.3
Marketing Costs (including Education and Outreach) | 1643233.23
Portfolio Administrative Costs | 13640022.56
Total ComEd Portfolio-Level Costs | 23329401.59
Total ComEd Program and Portfolio-Level Section 8-103B/8-104 (EEPS) Costs | 206315397.81
ComEd Section 8-103B/8-104 (EEPS) Costs as of CY2026 Q2
Overall Total Costs | 2026 Actual Costs YTD | 2026 Approved Budget | % of Costs YTD Compared to Approved Budget
Total ComEd Program and Portfolio-Level Section 8-103B/8-104 (EEPS) Costs | 206315397.81 | 454187928 | 45.43%

## 3- Energy
Statewide Quarterly Report Template
Tab 3: Historical Energy Saved
Instructions: *Each Program Administrator will fill out the historical "Energy Saved" table for Quarterly Reports. The "IL Department of Commerce Energy Saved" historical table may also be added to each utility's Quarterly Report. *Program Administrators are encouraged to provide source references for greater transparency.
| ComEd Section 8-103B/8-104 (EEPS) Energy Saved (MWh) as of | [5 empty] | IL Department of Commerce and Economic Opportunity Energy Saved (MWh)
CY2026 Q2
| Program Year | Evaluation Status (Ex Ante, Verified***, or ICC Approved) | Net Energy Savings Achieved (MWh) | Original Plan Savings Goal** (MWh) | Net Energy Savings Goal* (MWh) | % of Net Energy Savings Goal Achieved | Department | EPY1 | EPY2 | EPY3 | EPY4/ GPY1 | EPY5/ GPY2 | EPY6/ GPY3 | EPY7/ GPY4 | EPY8/ GPY5 | EPY9/ GPY6*
| EPY1- 6/1/08-5/31/09 | ICC Approved | 163717 | 148842 | 148842 | 110% | Net Savings Achieved (MWh) | 18636 | 34038 | 54130 | 107640 | 98944 | 86439 | 85124.306 | 30340.597 | 171941.09
| EPY2- 6/1/09-5/31/10 | ICC Approved | 472132 | 312339 | 312339 | 151.2% | Evaluation Status (Ex Ante, Verified**, or ICC Approved) | ICC Approved | ICC Approved | ICC Approved | ICC Approved | ICC Approved | ICC Approved | Verified | Verified | Verified
| EPY3- 6/1/10-5/31/11 | ICC Approved | 626715 | 458919 | 458919 | 136.6% | Source | Docket 10-0520, ComEd PY1 Evaluation Summary Report (2009-12-23), p. 17. | Docket 10-0520, Staff Ex. 1.1, p. 12 (Navigant Memo, DCEO PY2 Energy Impact Summary (2011-09-21)). | Docket 11-0593. | Docket 13-0078. | Docket 14-0075. | Docket 15-0274. | EPY7/GPY4 DCEO Cost Effectiveness Summary Report, p. 7. | Docket 19-0684 | Docket 19-0684
| Electric Plan 1 Total |  | 1262564 | 920100 | 920100 | 137.2%
| EPY4/GPY1- 6/1/11-5/31/12 | ICC Approved | 944111 | 610804 | 610804 | 154.6% | Footnotes:
| EPY5/GPY2- 6/1/12-5/31/13 | ICC Approved | 942061 | 806353 | 806353 | 116.8% | *Electric Program Year 9 (EPY9) and Gas Program Year 6 (GPY6) covers energy efficiency programs offered from June 1, 2016 to May 31, 2017.
| EPY6/GPY3- 6/1/13-5/31/14 | ICC Approved | 977911 | 809556 | 791103 | 123.6% | **Verified savings refer to evaluator estimated savings that are intended to count toward compliance with a Program Administrator's energy savings goal. Verified savings generally utilize deemed net-to-gross ratios and IL-TRM algorithms, where applicable. See also the definition of 'savings verification' in the IL-TRM Policy Document.
| Electric Plan 2/Gas Plan 1 Total |  | 2864083 | 2226713 | 2208260 | 129.7%
| EPY7/GPY4- 6/1/14-5/31/15 | Verified | 809877.658 | 648029 | 648029 | 125%
| EPY8/GPY5- 6/1/15-5/31/16 | Verified | 671027.051 | 541983 | 541983 | 123.8%
| EPY9/GPY6- 6/1/16-12/31/17 | Verified | 1087076 | 787629 | 787629 | 138%
| Electric Plan 3/Gas Plan 2 Total |  | 2567980.709 | 1977641 | 1977641 | 129.9%
Plan 5 | 2018 | Verified | 1859773.288 | 1713349 | 1713349 | 108.5%
| 2019 | Verified | 1700029.45 | 1629672 | 1629672 | 104.3%
| 2020 | Verified | 1821166.2136 | 1637572 | 1637572 | 111.2%
| 2021 | Verified | 1849877.162 | 1658918 | 1658918 | 111.5%
| 2018-2021 Plan Total |  | 7230846.1136 | 6639511 | 6639511 | 108.9%
Plan 6 | 2022 | Verified | 1724232 | 1738072.0006 | 1738072.0006 | 99.2%
| 2023 | Verified | 1601359.4374 | 1544746.0016 | 1544746.0016 | 103.7%
| 2024 | Verified | 1908293.5561 | 1777872.298 | 1777872.298 | 107.3%
| 2025 | Verified | 1892686 | 1911163.77 | 1911163.77 | 99.03%
| 2022-2025 Plan Total |  | 7126570.9935 | 6971854.0703 | 6971854.0703 | 102.2%
Plan 7 | 2026 | Ex Ante | 792091.4293 | 1440933.8445 | 1440933.8445 | 54.97%
| 2027 | Ex Ante | Pending | 1377948 | 1377948 | 0%
| 2028 | Ex Ante | Pending | 1397642 | 1397642 | 0%
| 2029 | Ex Ante | Pending | 1262721 | 1262721 | 0%
| 2022-2025 Plan Total |  | 792091.4293 | 5479244.8445 | 5479244.8445 | 14.46%
Footnotes:
*Net Energy Savings Goal refers to the most updated portfolio-level savings goal. In the case of Section 8-104 programs, the values in this column should match the Adjusted Energy Savings Goal contained in the Program Administrator's updated Adjustable Savings Goal Template.
**Original Plan Savings Goal refers to the original savings goal approved in the Commission's Final Order approving the EE Plan. For Section 8-104 programs, this value should match the Plan Energy Savings Goal set forth in the completed Adjustable Savings Goal Template.
***Verified savings refer to evaluator estimated savings that are intended to count toward compliance with a Program Administrator's energy savings goal. Verified savings generally utilize deemed net-to-gross ratios and IL-TRM algorithms, where applicable. See also the definition of 'savings verification' in the IL-TRM Policy Document.

## 4- Other
Statewide Quarterly Report Template
Tab 4: Historical Other - Environmental and Economic Impacts
Instructions: *Each Program Administrator should complete the Environmental and Economic Impacts table for Quarterly Reports. *Each Program Administrator should include a footnote to explain how performance metrics are derived (for example: the calculation for "Direct Portfolio Jobs.")
Environmental and Economic Impacts for the ComEd Service Territory as of
CY2026 Q2 |  | Open columns to expand all plan years
Performance Metrics (Equivalents)* |  | EPY1 | CY2022 | CY2023 | CY2024 | CY2025 | CY2026
Net Energy Savings Achieved (MWh)** |  | 182353 | 1724232 | 1569223.0419 | 1941922.1787 | 1882146.1322 | 792091.4293
Carbon reduction (tons) |  | 115046.9413 | 664025.8616 | 604329.7436 | 650501.9137 | 638725.3299 | 277581.7662
Cars removed from the road |  | 24635.3193 | 144353.4482 | 131376.0312 | 144877.9318 | 148884.1866 | 64703.1416
Acres of trees planted |  | 135349.3427 | 809787.6361 | 736987.4922 | 774407.0401 | 638731.1244 | 277584.2844
Number of homes powered for 1 year***** |  | 20452.3329 | 198187.5862 | 180370.4646 | 225072.1116 | 218143.965 | 91804.7554
Direct Portfolio Jobs****** |  | 66 | 457 | 484 | 502 | 463 | 501.48
Income qualified homes served*** |  |  | 89548 | 98592 | 84309 | 69170 | 24295
Performance Metrics (Equivalents) Since inception******* | CY2008 | CY2009 | CY2022 | CY2023 | CY2024 | CY2025 | CY2026
Electric Bill Savings ($) | 1400000 | 19800000 | 7653843402.3071 | 9152219571.9667 | 11035367032.5564 | 13308503542.9017 | 14227384000.6561
Net Energy Savings Achieved (MWh)******** | 12997.1694 | 187713.3045 | 70358375.164 | 82474110.9868 | 95734272.1776 | 111612052.7104 | 117658213.132
Carbon reduction (metric tons) | 6331.6852 | 91446.1853 | 27095994.4414 | 31761933.7805 | 32068909.8362 | 37876679.2087 | 41232329.2507
Cars removed from the road | 1367.5346 | 19750.796 | 5890433.5742 | 6904768.2132 | 7142296.1773 | 8828894.5355 | 9611082.4395
Acres of trees planted | 8222.9678 | 118761.2796 | 33043895.6603 | 38734065.586 | 38177273.6146 | 37877022.8236 | 41232703.308
Number of homes powered for one year | 1502.2156 | 21695.9437 | 8087169.5591 | 9401973.4367 | 11095766.3627 | 12936028.3623 | 13636788.7265
Footnotes:
*Unless otherwise noted, performance metrics for carbon reduction, cars removed from the road, and acres of trees planted are derived from the U.S. EPA Greenhouse Gas Equivalencies Calculator: https://www.epa.gov/energy/greenhouse-gas-equivalencies-calculator
**This includes Sections 8-103, 8-103B, 8-104, and 16-111.5B savings achieved. In addition, this includes Illinois Department of Commerce and Economic Opportunity program savings achieved through May 31, 2017.
***To the extent the portfolio offers a low income program and tracks participation. Includes Single Family Retrofits (CBA+IHWAP), Multi Family Retrofits (IEMS+IHWAP), Affordable Housing, Public Housing Retrofits, IE Kits, Elementary Education Kits. Excludes Lighting Discounts and Food Bank. Low income customers were previously served by the IL Department of Commerce and Economic Opportunity until May 31, 2017. Utilities began serving both low income and public sector customers on June 1, 2017.
****Electric Program Year 9 (EPY9) and Gas Program Year 6 (GPY6) covers energy efficiency programs offered from June 1, 2016 to December 31, 2017.
*****Direct Portfolio Jobs will be updated at least once per year.
******Direct portfolio Jobs reflect actual positions held by ComEd and its contractors that are part of the Rider EEPP and does not attempt to capture indirect jobs in the energy efficiency industry that may result from the ComEd Energy Efficiency Program.
*******This includes performance metrics for $ saved by customers, net energy savings, carbon reduction, cars removed from the road, acres of trees planted and number of homes powered since inception of the program. Data presented is cumulative.
********Legacy and persisting savings from prior year's measures are partially claimed each quarter to avoid a substantial increase in estimated customer bill savings at the start of each year.

## 5- CPAS
Statewide Quarterly Report Template
Tab 5: CPAS Progress
Instructions: *The electric utilities Ameren Illinois and ComEd should complete the CPAS and AAIG Progress Ex Ante Results table in Quarterly Reports.
Color Coded Key:
Reported items
Statutory and/or approved plan inputs
Calculations
ComEd CPAS and AAIG Progress Ex Ante Results - Section 8-103B Portfolio
CY2026 Q2
Cumulative Persisting Annual Savings (CPAS) Goal Progress CY2026 Q2
a | Current Year CPAS Goal (% of Eligible 2014-2016 Average Annual Sales) | 17.9% | ICC approved plan compliance filing
b | Baseline - 2014-2016 Average Annual Sales Less Exempt Customers (MWh) | 83000528 | ICC approved plan compliance filing
c | Current Year CPAS Goal (MWh) | 14857094.512 | = a * b
d | CPAS Achieved at End of Previous Year (MWh) | 14330354.502 | verification report for previous year
Savings Expiring in Current Year
e | 2012-2017 Legacy Savings Persisting in Current Year (% of Sales) | 2.3% | statute
f | 2012-2017 Legacy Savings Persisting in Previous Year (% of Sales) | 2.5% | statute
g | 2012-2017 Legacy Savings Expiring in Current Year (% of Sales) | 0.2% | = f - e
h | 2012-2017 Legacy Savings Expiring in Current Year (MWh) | 166001.056 | = g * b
i | Savings from Measures Installed post-2017 Expiring in Current Year (MWh)* | 494105.921 | verification report for previous year
j | Total Savings Expiring in Current Year (MWh) | 660106.977 | = h + i
k | New Annual Savings Needed to Meet Current Year CPAS Goal (MWh) | 1186846.987 | = c - d + j
l | New Annual Savings this Quarter (MWh) | 421965.18 | utility report
m | New Annual Savings this YTD (MWh) | 792091 | sum of utility reports for all quarters to date
n | New Annual Savings YTD as % Needed to Meet Current Year CPAS Goal | 66.74% | = m / k
Applicable Annual Incremental Goal (AAIG) Progress
o | Previous Year's CPAS Goal (% of Sales) | 17% | ICC approved plan compliance filing
p | Previous Year's CPAS Goal (MWh) | 14110089.76 | = o * b
q | Current Year Applicable Annual Incremental Goal (MWh) | 747004.752 | = c - p
r | New Savings Required to Meet AAIG (MWh) | 1407111.729 | = q + j
s | New Savings Achieved YTD (MWh) | 792091 | same as "m"
t | Expiring savings that have to be offset before counting progress towards AAIG (MWh) | 660106.977 | = j
u | Progress towards AAIG (after offsetting expiring savings) - MWh YTD | 131984.023 | = s - t
v | Progress towards AAIG (after offsetting expiring savings) - % YTD | 17.67% | = u / q
Footnotes:
*Savings from Measures Installed post-2017 Expiring in Current Year per Guidehouse's April 2025 first draft of evaluation report.

## 6- Historical Costs
Statewide Quarterly Report Template
Tab 6: Historical Costs
Instructions: *Each Program Administrator will fill out the "Historical Energy Efficiency Costs" table for Quarterly Reports. *For Costs, each Program Administrator should include actual costs incurred from the beginning of the Program Year through the end of the applicable quarter or Program Year, regardless of what Program Year the costs are associated with. Costs include both Program and Portfolio-Level Costs as well as On-Bill Financing costs. *Program Administrators should add a footnote specifying if there are non-rider energy efficiency costs that are not reported in the Quarterly Reports.
ComEd Service Territory Historical Energy Efficiency Costs as of
CY2026 Q2
| Program Year | Actual ComEd EEPS Costs | Actual DCEO EEPS Costs | Total Actual EEPS Costs (ComEd + DCEO) | Actual Section 16-111.5B Costs | Total Actual EEPS + Section 16-111.5B Costs
| EPY1- 6/1/08-5/31/09 | 27356150.45 | 6949809.14 | 34305959.59 | 0 | 34305959.59
| EPY2- 6/1/09-5/31/10 | 52071860.0449 | 11471615 | 63543475.0449 | 0 | 63543475.0449
| EPY3- 6/1/10-5/31/11 | 75691132.85 | 28659010.5 | 104350143.35 | 0 | 104350143.35
| Electric Plan 1 Total | 155119143.3449 | 47080434.64 | 202199577.9849 | 0 | 202199577.9849
| EPY4/GPY1- 6/1/11-5/31/12 | 106315194.5 | 35049987 | 141365181.5 | 0 | 141365181.5
| EPY5/GPY2- 6/1/12-5/31/13 | 107354963.67 | 33565649.33 | 140920613 | 31329 | 140951942
| EPY6/GPY3- 6/1/13-5/31/14 | 124096016.17 | 31563417 | 155659433.17 | 29469183.29 | 185128616.46
| Electric Plan 2/Gas Plan 1 Total | 337766174.34 | 100179053.33 | 437945227.67 | 29500512.29 | 467445739.96
| EPY7/GPY4- 6/1/14-5/31/15 | 128288585 | 33728435 | 162017020 | 39150326.56 | 201167346.56
| EPY8/GPY5- 6/1/15-5/31/16 | 108343594 | 3670970 | 112014564 | 87103873 | 199118437
| EPY9/GPY6- 6/1/16-12/31/17 | 222451927.54 | 57854489 | 280306416.54 | 159497825.46 | 439804242
| Electric Plan 3/Gas Plan 2 Total | 459084106.54 | 95253894 | 554338000.54 | 285752025.02 | 840090025.56
| Program Year | Actual ComEd EEPS Costs YTD | Approved ComEd EEPS Budget | % of Costs YTD Compared to Approved Budget
Plan 5 | 2018 | 352988359 | 351334190 | 100.5%
| 2019 | 351381796 | 351334190 | 100%
| 2020 | 346480330 | 351334190 | 98.62%
| 2021 | 351037751.6546 | 351334190 | 99.92%
| 2018-2021 Plan Total | 1401888236.6546 | 1405336760 | 99.75%
Plan 6 | 2022 | 399377042 | 408267882 | 97.82%
| 2023 | 415602522.6462 | 439746496.2964 | 94.51%
| 2024 | 435219509 | 437772939 | 99.42%
| 2025 | 447335381 | 447014912.0219 | 100.1%
| 2022-2025 Plan Total | 1697534454.6462 | 1732802229.3184 | 97.96%
Plan 7 | 2026 | 206315397.81 | 454187928 | 45.43%
| 2027 | 0 | 540333593 | N/A
| 2028 | 0 | 540191892 | N/A
| 2029 | 0 | 540030654 | N/A
| 2026-2029 Plan Total | 206315397.81 | 2074744067 | 9.944%

## MF IQ Metrics
Income Qualified Multi-Family Metrics
Building Types Treated
Size | Housing Type | Number of Buildings |  | Number of Apartments
|  | Central Heating System | Individual heating System | Central Heating System | Individual heating System
Buildings <20 Units | Public Housing
Subsidized Housing
Unsubsidized Housing
Buildings 20-49 Units | Public Housing
Subsidized Housing
Unsubsidized Housing
Buildings w/50+ Units | Public Housing
Subsidized Housing
Unsubsidized Housing
Measures Installed (Evaluator Provided)
|  | Buildings | Apartments
Total participants |  | 29 | 2170
Total participants w/electric heat |  | 8 | 257
Number participants where measure is installed:
Multifamily Upgrades - Public Housing | Direct Install in-unit | 0 | 0
| Heat pumps | 1 | 49
| heat pump water heaters | 0 | 0
| Gas heating system replacements | 1 | 32
| Other HVAC equipment measures | 20 | 1071
| Attic Insulation | 15 | 714
| Other Insulation | 7 | 116
| Air sealing | 15 | 714
| Common area lighting w/controls | 0 | 0
| Common area lighting w/o controls | 0 | 0
| Other | 15 | 877
for electric utilities only…
Reasons Building Envelope Measures Not Installed | [5 empty] | Reasons Building Heat Pump Measures Not Installed
Component |  |  | Buildings | Apartments |  | Component |  |  | Buildings | Apartments
| Total Buldings / Units Served | [5 empty] | Total Electrically Heated Buildings / Units Served
| Total Buildings / Units Assessed | [5 empty] | Total Electrically Heated Buildings/Units Assessed
Multifamily Upgrades - Public Housing | Note: The following data is associated with buildings served with a Multi-Family Energy Savings assessment. |  |  |  |  | Multifamily Upgrades - Public Housing | Note: The following data is associated with buildings served with a Multi-Family Energy Savings assessment.
| Installed Insulation/Air Sealing Measures | [5 empty] | Installed Heat Pumps
| Did Not Install Insulation/Air Sealing Measures | [5 empty] | Did Not Install Heat Pumps
| A. Not qualified for measures | [5 empty] | A. Not qualified for measures
|  | 1. Measure already there/already upgraded | [5 empty] | 1. Measure already there/already upgraded
|  | 2. Not cost-effective | [5 empty] | 2. Not cost-effective
|  | 3. Cannot access attic or other space | [5 empty] | 3. No good location or space
4. Not applicable (e.g., no attic)
5. Health and safety cost too high or extensive
| B. Qualified and offered measure, but didn't install | [5 empty] | B. Qualified and offered measure, but didn't install
|  | 1. Building owner not willing to make co-pay | [5 empty] | 1. Building owner not willing to make co-pay
|  | 2. Building owner sees no benefit | [5 empty] | 2. Building owner sees no benefit
|  | 3. Building owner will not accept disruption | [5 empty] | 3. Building owner will not accept disruption
|  | 4. Deferring to a future year | [5 empty] | 4. Deferring to a future year
|  | 5. Building owner dislikes aesthetics | [5 empty] | 5. Building owner dislikes aesthetics
|  | 6. Building owner non-responsive | [5 empty] | 6. Building owner non-responsive
|  | 7. Building owner not willing/able to address Health & Safety work or deferrable conditions | [5 empty] | 7. Building owner not willing/able to address Health &d Safety work or deferrable conditions
8. Desired heat pump does not meet program specification requirements
Measures Installed (Evaluator Provided)
|  | Buildings | Apartments
Total participants |  | 993 | 37633
Total participants w/electric heat |  | 255 | 9148
Number participants where measure is installed:
Multifamily Upgrades - Income Eligible | Direct Install in-unit | 328 | 10281
| Heat pumps | 99 | 1580
| heat pump water heaters | 0 | 0
| Gas heating system replacements | 21 | 488
| Other HVAC equipment measures | 271 | 8029
| Attic Insulation | 357 | 9712
| Other Insulation | 23 | 774
| Air sealing | 184 | 2294
| Common area lighting w/controls | 0 | 0
| Common area lighting w/o controls | 207 | 17991
| Other | 621 | 18427
for electric utilities only…
Reasons Building Envelope Measures Not Installed | [5 empty] | Reasons Building Heat Pump Measures Not Installed
Component |  |  | Buildings | Apartments |  | Component |  |  | Buildings | Apartments
| Total Buldings / Units Served | [5 empty] | Total Electrically Heated Buildings / Units Served
| Total Buildings / Units Assessed | [5 empty] | Total Electrically Heated Buildings/Units Assessed
Multifamily Upgrades - Income Eligible | Note: The following data is associated with buildings served with a Multi-Family Energy Savings assessment. |  |  |  |  | Multifamily Upgrades - Income Eligible | Note: The following data is associated with buildings served with a Multi-Family Energy Savings assessment.
| Installed Insulation/Air Sealing Measures | [5 empty] | Installed Heat Pumps
| Did Not Install Insulation/Air Sealing Measures | [5 empty] | Did Not Install Heat Pumps
| A. Not qualified for measures | [5 empty] | A. Not qualified for measures
|  | 1. Measure already there/already upgraded | [5 empty] | 1. Measure already there/already upgraded
|  | 2. Not cost-effective | [5 empty] | 2. Not cost-effective
|  | 3. Cannot access attic or other space | [5 empty] | 3. No good location or space
4. Not applicable (e.g., no attic)
5. Health and safety cost too high or extensive
| B. Qualified and offered measure, but didn't install | [5 empty] | B. Qualified and offered measure, but didn't install
|  | 1. Building owner not willing to make co-pay | [5 empty] | 1. Building owner not willing to make co-pay
|  | 2. Building owner sees no benefit | [5 empty] | 2. Building owner sees no benefit
|  | 3. Building owner will not accept disruption | [5 empty] | 3. Building owner will not accept disruption
|  | 4. Deferring to a future year | [5 empty] | 4. Deferring to a future year
|  | 5. Building owner dislikes aesthetics | [5 empty] | 5. Building owner dislikes aesthetics
|  | 6. Building owner non-responsive | [5 empty] | 6. Building owner non-responsive
|  | 7. Building owner not willing/able to address Health & Safety work or deferrable conditions | [5 empty] | 7. Building owner not willing/able to address Health &d Safety work or deferrable conditions
8. Desired heat pump does not meet program specification requirements

## SF E&A Metrics
Evaluator Provided |  |  | Evaluator Provided
Equity and Affordability Reporting Metrics
Component | Metric |  | Component | Metric
Whole Home Electrification | Total number of IQ single family whole building program participants | 213 | Home Energy Assessment | Total number of IQ single family program participants | 6782
| Total number of IQ single family whole building program participants adopting air sealing | 131 |  | Total number of IQ single family whole building program participants adopting air sealing | 1695
| Total number of IQ single family whole building program participants adopting insulation | 201 |  | Total number of IQ single family whole building program participants adopting insulation | 347
| Total number of IQ single family whole building program participants with electric resistant heating adopting heat pumps | 213 |  | Total number of IQ single family whole building program participants with electric resistant heating adopting heat pumps | 0
| Total number of IQ single family whole building program participants with fossil fuel heating adopting heat pumps | 0 |  | Total number of IQ single family whole building program participants with fossil fuel heating adopting heat pumps | 0
| Total number of IQ single family whole building program participants adopting heat pump water heaters | 206 |  | Total number of IQ single family whole building program participants adopting heat pump water heaters | 0
| Total number of IQ single family whole building program participants with fossil fuel heating or hot water systems replaced with another fossil fuel system | 0 |  | Total number of IQ single family whole building program participants with fossil fuel heating or hot water systems replaced with another fossil fuel system | 0