## Policy Manual Tracker
Proposed Policy Tracker
SAG Policy Manual Subcommittee
Updated 5/16/2023 by SAG Facilitator
Tracker Overview *Policies highlighted in green have a corresponding Policy Template that includes additional information. *If policy language was not submitted in the Policy Proposal, Subcommittee participant(s) will be assigned to draft language throughout the Subcommittee process. *This tracker reflects the threshold feedback discussion from the Sept. 21 meeting, where participants agreed to remove several policy proposals from the discussion list. The policy proposals that were removed are no longer on this tracking list, but can be found on the Subcommittee website - see link below. *Policies highlighted in yellow in column G have reached general agreement, and do not require further discussion at this time. Note: Policies related to income qualified will be reviewed by interested IQ EE Committee participants for input at the May Equity Subcommittee meeting. Policy Manual Subcommittee Website: Planning documents and Policy Proposals are available for download on the SAG website: https://www.ilsag.info/meetings/subcommittees/policy-manual-version-3-0-subcommittee/
Administrative Edits | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Introductory language / participation in Policy Manual Version 3.0 | "Acknowledgements" section | SAG Facilitator | Both Electric and Gas | N/A | This language should be updated to reflect who participates in the Version 3.0 process. | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Introductory language | "Acknowledgements" section | Edit raised by NRDC in Small Group meeting | Both Electric and Gas | N/A | Introduction to the Policy Manual should mention there may be policies where consensus was developed by utilities and non-financially interested parties, that did not involve other administrators | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Fix Table of Contents error | Table of Contents | SAG Facilitator | Both Electric and Gas | N/A | Section 6.7 does not show up in the Table of Contents | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Clarify Current Adjustable Goals Policy | Section 6.2, Adjustable Savings Goals Beginning in 2022 | ICC Staff | Gas | N/A | Edits are needed in the current adjustable goals policy, to clarify in which docket gas adjustable goal spreadsheets are filed. They should be filed in the EE Plan docket that the spreadsheet relates to. The current policy mentions filing, but not the forum. | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Independence Policy Clarification | Existing independence provisions | ICC Staff | Both Electric and Gas | Independence Policy Clarification (ICC Staff) | A minor edit is needed to the current independence policy provisions. There are three independence provisions in Policy Manual Version 2.1 – Section 3.5, SAG Facilitator Independence; Section 7.1 (ii), IL-TRM Administrator Independence; and Section 7.5, Evaluator Independence. There is language in each independence provision regarding “acting independently.” For the SAG Facilitator and IL-TRM Administrator provisions, “is not acting independent” should be changed to “was not acting independently”, to be consistent with the evaluator independence provision. | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Weighted Average Measure Life (WAML) Clarification | Section 11.4, Electric Utility Weighted Average Measure Life | ICC Staff | Electric | Weighted Average Measure Life Clarification (ICC Staff) | The Weighted Average Measure Life (WAML) policy needs to be clarified to exclude voltage optimization. This question was raised during the 2021 evaluation report review process. Proposed policy language included in template. | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Clarify Policy Manual is specific to EE policies | TBD | Ameren Illinois | Both Electric and Gas | N/A | Language should be added to the Policy Manual clarifying it is specifically for energy efficiency policies | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Create new section cross-referencing all IQ policies | New section | IQ South Committee Facilitator | Both Electric and Gas | N/A | Create a simple cross-reference table in the Policy Manual that lists all IQ-related policies. | May 31 meeting agenda - SAG Facilitator overview of administrative edits
Electrification Policy Proposals | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Electrification Savings in Cost-Effectiveness | TBD | Opinion Dynamics | Both Electric and Gas | Electrification Savings in Cost-Effectiveness (Opinion Dynamics) | Include guidance in the Policy Manual on how to treat the impacts of electrification, to ensure all parties conduct cost-effectiveness analyses in a consistent manner and to ensure costs and benefits are defined consistently across the broader DER landscape in Illinois (e.g., EE, managed charging, building electrification, etc.). | Discussed at Oct., Nov. and Jan. meetings - small group proposed redline edits to Policy Manual, under review (comments due 2/9). Additional edits will be circulated for a second round of review (tentatively in May).
Electrification Cost-Effectiveness | TBD | Ameren Illinois | Both Electric and Gas | Electrification Cost-Effectiveness (Ameren Illinois) | There appears to be a tension between offering cost-effective energy efficiency measures to reduce load and offering cost-ineffective or close to cost-ineffective electrification measures that will increase load. Accordingly, Illinois electric utilities choosing to pursue electrification under Section 8-103B(b-27) should design and deliver energy efficiency electrification programs that have been shown to provide significant benefit to customers choosing to switch fuels, considering cost-effectiveness. Further details surrounding this policy may be subject to further analysis and discussion. | Discussed at Oct. and Dec. meetings; follow-up in future meeting if needed
Interactions Between Electrification and Other Efficiency Measures | TBD | Joint Stakeholders** | Electric | Follow-up from December Meeting: Interactive Effects Joint Stakeholder Proposal | Proposed policy language on counting electrification savings. It is important to be clear about which savings are “counted first” and the related issue of which fuel is counted as having been saved: When an electrification measure is installed in concert with, at the same time and/or as part of a project in which other efficiency measures that would affect future electricity consumption by the electrification measure, the electrification savings should be counted first and savings from the interacting efficiency measures should be treated as standard electric efficiency measures with savings estimated relative to the new electric baseline. | Discussed at Oct., Nov., Dec. and Jan. meetings; participants generally comfortable with language 3/27/23 Update: There may need to be further discussion about the “interactive effects policy” per the ongoing review of bill impacts calculators with Ameren IL, ComEd and the gas utilities. On agenda for 5/31 meeting.
Fuel Switching | TBD | Peoples Gas & North Shore Gas | Both Electric and Gas | Peoples Gas & North Shore Gas Fuel Switching Policy Proposal | See column E for link to review policy proposal (updated version added 1/26). | Discussed at Jan. meeting; follow-up in Feb. No additional discussion needed at this time, currently non-consensus.
Electrification Bill Impacts | TBD | Nicor Gas | Electric | Nicor Gas Policy Proposal: Electrification Bill Impacts | See column E for link to review policy proposal (updated version added 1/26). | Discussed at Jan. and Feb. meetings. Nicor Gas will propose higher level principles at 5/31 meeting
Electrification Energy Consumption Reduction | TBD | Nicor Gas | Electric | Nicor Gas Policy Proposal: Electrification Energy Consumption Reduction | See column E for link to review policy proposal (updated version added 1/26). | Discussed at Jan. and Feb. meetings. Nicor Gas will propose higher level principles at 5/31 meeting
Evaluation Policy Proposals | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Allowing Renewable Measures Under EE Programs | TBD | Guidehouse | Both Electric and Gas | Allowing Renewable Measures Under EE Programs (Guidehouse) | This policy proposal is intended to give the utilities and their independent evaluators guidance about which measures with renewable energy (RE) components can be included in the energy efficiency (EE) portfolios and under what conditions. This issue was previously discussed by SAG in July 2021, with a policy proposal circulated for review in November 2021. This policy proposal has been updated compared to the original discussion. See the template for the specific proposal. | May 31 meeting agenda
Evaluating Savings from Non-Qualified Equipment (from 2020 SAG resolution) | TBD | Guidehouse | Both Electric and Gas | Evaluating Savings from Non-Qualified Equipment (Final, Jan. 2020) | The policy question discussed and resolved was how should evaluation treat projects or measure installations that don’t meet the criteria of the program (e.g., equipment efficiency, equipment application, DLC listing), but do still result in energy savings? This was resolved in January 2020. | Discussed May 3; participants agreed this policy resolution should be included in Policy Manual
Heating Penalties and Negative Savings Policies | TBD | Opinion Dynamics and Guidehouse | Both Electric and Gas | Heating Penalties Policies (Opinion Dynamics and Guidehouse) | Proposed policies related to heating penalties and negative savings. Policies 1-3 proposed by Opinion Dynamics; policies 4-5 proposed by Guidehouse. This issue was previously discussed by SAG in 2020. There were delays in reaching final resolution due to the Portfolio Planning Process and post-CEJA negotiations. | Discussed May 3; participants generally comfortable with policies
Net-to-Gross (NTG) Clarification | Section 8.3, Calculating TRC | ICC Staff | Both Electric and Gas | Net-to-Gross (NTG) Clarification (ICC Staff) | The NTG policy needs to be clarified so that NTG is applied to the benefits side of TRC calculation, including the net present value avoided replacement costs (if negative, then treated as incremental cost, if positive, then treated as a benefit – but apply NTG in both scenarios). Clarification is needed because this question was raised in an evaluation report | Discussed in October meeting; edits incorporated into the Policy Manual by a small group (edits circulated for review in Jan., were due 2/9). Additional edits will be circulated for a second round of review (tentatively in May).
Income Qualified (IQ) / Income Eligible (IE) Policy Proposals | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Policy Proposals from IQ North Committee Leadership Team and IQ North Facilitator | New section | N/A | Both Electric and Gas | Policy Proposals from IQ North Committee Leadership Team and IQ North Facilitator | Suggestion discussed during 9/21/22 meeting: Development of general IQ policy principles for inclusion in Policy Manual. | Discussed April 19; SAG Facilitator recommendation to remove from Policy Manual process, this requires further development with the IQ Committees per feedback. This policy will not be included in Policy Manual Version 3.
| TBD | IQ North Committee Leadership Team and IQ North Facilitator | Both Electric and Gas |  | 7- Local CBOs/CAAs Considered “Non-financially interested parties” Policy indicating that, by definition, local CBOs/CAAs are included in definition of “non-financially interested parties” except in the narrow case that a contract with that organization is being considered by SAG or a SAG subcommittee. | Discussed in Feb; follow-up in March and April meetings. Agreement reached on edits to SAG Process Guidance document; this will remain in that process document and will not be included in the Policy Manual.
| New section | IQ North Committee Facilitator | Both Electric and Gas |  | 1. Create single section in Policy Manual for IQ Policies | Discussed in Feb; follow-up in April SAG Facilitator recommendation to remove from Policy Manual process, this requires further development with the IQ Committees per feedback. This policy will not be included in Policy Manual Version 3 (except for a simple section cross-referencing IQ policies).
| TBD |  |  |  | 2. All IQ items discussed through SAG should be grouped together | Discussed in Feb; participants generally comfortable with policy
Single Family IQ Eligibility Verification Guidelines | Section 4.3, Income Eligibility Verification Guidelines for Low Income Customers | Ameren Illinois | Both Electric and Gas | Single Family IQ Eligibility Verification Guidelines (Ameren Illinois) | Current Illinois policy in Section 4.3 provides income eligibility verification guidelines for lowincome customers in multifamily properties. The verification guidelines provide flexibility in qualification to minimize time, paperwork and hassle; recognizing that the majority of customers meeting alternative verification guidelines are income eligible. The majority of customers participating in federal, local government, and/or community organization programs or located in a low-income census tract should be expected to have incomes at or below 80% of Area Median Income. Allowing the same verification pathways for single family programs would also minimize time, paperwork and hassle for the program administrator and participants. | Discussed at October and December meeting; follow-up April 19 and May 3. Agreement reached on edits.
Net-to-Gross Policy for Disadvantaged Areas | Section 7, Evaluation Policies | Ameren Illinois | Both Electric and Gas | Net-to-Gross Policy for Disadvantaged Areas (Ameren Illinois) | To address continuing concerns around equity in program access and participation, AIC proposes the SAG consider enhancing the NTG Ratio policy for both residential and business programs serving customers in areas identified as facing significant disadvantages. This policy seeks to identify a generally accepted definition for “disadvantaged areas”, as it relates specifically to Section 8-103B and 8-104 energy efficiency. Once accepted, utilities will be able to focus additional program resources and efforts in these areas of agreed upon need. | Discussed with Subcommittee in Oct.; three Small Group meetings held; follow-up at May 10 Subcommittee meeting. Small Group meeting will be scheduled soon to discuss remaining comments.
New Income Qualified Accountability Committee Section | New section | Joint Stakeholders* | Both Electric and Gas | New Income Qualified Accountability Committee Section (Joint Stakeholders*) | Add a Low-Income Energy Efficiency Accountability Committee (IQ Accountability Committee) section into the Policy Manual, similar to Section 3 of the Policy Manual with details on the Illinois EE Stakeholder Advisory Group (SAG). This new IQ Accountability Committee section could include information about what the IQ Accountability is, any clarification needed on statutory interpretation, who can be involved (e.g. open to all), details about the leadership committee (leadership from community-based organizations), how to get involved, resources available for participation, committee purpose, etc. This language should be developed in collaboration with current IQ Accountability Committee Leadership. This language should also be posted on the SAG website or another webpage in order to explain who is eligible to participate in the IQ, how to get involved, and provide a specific point of contact to assist interested parties in getting involved. | Similar proposal to row 34 SAG Facilitator recommendation to remove from Policy Manual process, this requires further development with the IQ Committees per feedback. This policy will not be included in Policy Manual Version 3.
One-Stop Shop Program Design Definition for IQ MF Retrofit | TBD | Joint Stakeholders* | Both Electric and Gas | One-Stop Shop Program Design Definition for IQ Multifamily Retrofit (Joint Stakeholders*) | A definition of one-stop shop program design within IE/IQ Multifamily Retrofit Programs. See proposed policy template for the proposed definition. | Discussed in November; participants generally comfortable with language
Income Qualified / Income Eligible Reporting Proposals | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Equity and Affordability Statewide Reporting Metrics | Section 6, Program Administration and Reporting | (Joint Stakeholders*) | Both Electric and Gas | Equity and Affordability Principles + Metrics (Joint Stakeholder Proposal) | The adoption of statewide, consistent equity and affordability reporting principles and metrics. See column E for link to updated proposal, for discussion at Feb. meeting. | Discussed in February, March and April meetings; follow-up discussion May 10. Small Group meeting will be scheduled soon to discuss remaining comments.
IQ Multi-Family Reporting Metrics | Section 6, Program Administration and Reporting | (Joint Stakeholders*) | Both Electric and Gas | IQ Multifamily Reporting Principles (Proposed Edits following Nov. Meeting) | The adoption of statewide, consistent Income Qualified (IQ) Multifamily reporting principles and metrics. See column E for link to updated proposal, for discussion at Feb. meeting if there are additional comments. | Discussed in November and December; participants generally comfortable with language
Health and Safety Reporting | Section 6, Program Administration and Reporting | (Joint Stakeholders*) | Both Electric and Gas | IQ Health & Safety Reporting Principles (Proposed Edits following Nov. Meeting) | Consistent, statewide health and safety reporting guidelines and metrics, reported quarterly for income eligible retrofit programs. See policy proposal for proposed reporting. See column E for link to updated proposal, for discussion at Feb. meeting if there are additional comments. | Discussed in November and December; participants generally comfortable with language
Diverse Contracting Reporting | Section 6, Program Administration and Reporting | NCLC / COFI | Both Electric and Gas | Diverse Contracting Reporting Metrics (NCLC / COFI Proposal) | Proposal to establish specific reporting metrics related to energy efficiency supplier diversity to enable transparent tracking of the goal to increase opportunities for diverse vendors within the realm of energy efficiency program implementation. See policy proposal for potential new metrics. See column E for link to updated proposal, for discussion at Feb. meeting. | Discussed in February, March and April meetings; follow-up discussion May 10. Small Group meeting will be scheduled soon to discuss remaining comments.
Independence Policy Proposals | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
LIEEAC Facilitator Independence | New section | ComEd | Electric; Gas TBD | LIEEAC Facilitator Independence (ComEd) | The proposal is to develop protocols to ensure that Low Income EE Accountability Committee (LIEEAC) Facilitator independence is maintained. This is necessary, because in ComEd’s Revised Plan 6 Stipulation it agreed to work with the SAG Policy Manual subcommittee and LIEEAC to do so, as a part of the the Policy Manual Version 3.0 discussions. See policy proposal for 4 protocols excerpted from ComEd's stipulation. | Discussed in March and April; participants generally comfortable with language
IL-TRM Administrator and Independent Evaluator Contract Review | Section 7.1, IL-TRM Administrator Independence | Ameren Illinois | Both Electric and Gas | IL-TRM Administrator and Independent Evaluator Contract Review (Ameren Illinois) | Current policy requires program administrators submit finalized but not yet executed contracts with IL-TRM administrators and independent evaluators to the Commission for review. However, current policies do not contain any timeline for when the Commission should complete its review of the finalized but not yet executed contract. Timely execution of contracts with the TRM administrator or independent facilitators are necessary for program administrators to continue delivering its programs to customers. Establishing a 14-day timeline for Commission review allows program administrators the ability to plan around the review timeline and then begin implementing programs immediately upon receipt of Commission approval. | Discussed in March; participants generally comfortable with language
IL-TRM Administrator Role | TBD | ComEd | Both Electric and Gas | IL-TRM Administrator Role (ComEd) | Policy Manual v2.1 does not mention the role of “technical resource” and instead says, “As described in more detail in the IL-TRM Policy Document, the IL-TRM Administrator is an independent entity who has primary responsibility for managing the update process to the ILTRM.” | Small Group discussed in early December; discussed edits with Subcommittee at Dec. meeting; follow-up discussion in February meeting Participants generally comfortable with language, pending additional minor edits flagged in Feb. meeting
Proposals that Relate to Program Administration | [5 empty] | Facilitator Notes
Policy Proposal | Policy Manual Section | Submitted By | Electric, Gas, or Both | Link to Proposal | Summary of Policy Proposal
Cumulative Persisting Annual Savings (CPAS) Goal Setting | Section 11.2, Cumulative Persisting Annual Savings | ComEd | Electric | CPAS Goal Setting (ComEd) | Section 8-103B of Public Act 102-0062 (PUA) directs the ICC to establish additional cumulative persisting annual savings (CPAS) goals beyond 2030, and specifically required the ICC to set 2031-2035 goals no later than December 31, 2021, with a default statutory goal of 0.9% per year. This was discussed over the course of several SAG workshops and meetings with Staff and other stakeholders. Although parties appeared to generally be aligned that material downward adjustments to the default goals were potentially necessary, due to the statutory deadline of December 31, 2021, many parties also believed it was impossible at that time to develop the required evidentiary record upon which to base a decision to adjust the CPAS goals. Given this tight timeline, ComEd proposed to establish a policy to revisit the establishment of CPAS goals beyond 2030 in a later process, ahead of the 2030-2033 Plan filing, when more current and robust data and analysis is available, including the potential study, and adequate time is allowed to thoroughly discuss. | Discussed in January and March; small group discussing stakeholder feedback
Framework for Claiming Savings from Co-Funded Programs | TBD | ComEd | Both Electric and Gas | Framework for Claiming Savings from Co-Funded Programs (ComEd) | The proposal is to discuss the framework for claiming savings from co-funded building and industrial electrification programs and from ComEd’s role in helping state, municipal, and other public partners apply for and access federal and/or state funds for co-funded EE opportunities (e.g., Infrastructure Investment & Jobs Act). It was agreed to do so amongst the Parties to ComEd’s Revised Plan 6 Stipulation, via the SAG Policy Manual subcommittee, to ensure this is addressed as part of Illinois Energy Efficiency Policy Manual Version 3.0. | Discussed in October; Small Group to discuss further
Prohibited Expenses Expansion | Section 5.4, Prohibited Expenses | ICC Staff | Both Electric and Gas | Prohibited Expenses Expansion (ICC Staff) | ICC Staff recommends expanding the prohibited expenses list to add back in tickets to sports events (previously approved in v1.0), and add incentive compensation tied to financial metrics and incentive compensation unrelated to energy efficiency. During v2.0 update process, Staff had proposed broadening the tickets to sports events to incorporate a broader prohibition on entertainment expenses, but agreement couldn’t be reached on the broader entertainment prohibition so the tickets to sports events was dropped. As a result of the tickets to sports events being dropped, Staff has noticed that the previous language prohibiting tickets to sports events has been removed from some contracts; therefore, Staff is proposing tickets to sports events to be added back so the utilities will start including the sports ticket prohibition in all contracts again. Staff previously proposed the incentive compensation items, but they had to be withdrawn due to an open docket and litigation during the v2.0 update process. NCLC and Staff also propose Entertainment to be added to list of prohibited expenses. | May 31 meeting agenda
*Joint Stakeholders = The following Illinois Energy Efficiency for All (IL EEFA) Coalition Members and EE Settlement Groups: ACES 4 Youth, Blacks in Green/Green Power Alliance, City of Chicago, Community Investment Corporation (CIC), Citizens Utility Board (CUB), Natural Resources Defense Council (NRDC), People for Community Recovery (PCR), and National Consumer Law Center (NCLC) / Community Organizing on Family Issues (COFI).
**Joint Stakeholders = City of Chicago, NRDC, CUB, NCLC / COFI
***Joint Stakeholders = NRDC, ICC Staff, NCLC / COFI