## Sheet1
SAG Policy Manual Subcommittee
Policy Manual Version 3.0 Update Process
Policy Manual Status Update Table with Proposed Effective Dates (updated 7/21/2023)
OPEN POLICIES
Policy | Policy Proposed By | Policy Materials | Status Update | Action Item for Interested Policy Manual Participants | Proposed Effective Date
Electrification Policies
Electrification Bill Impacts | Nicor Gas, Peoples Gas & North Shore Gas | Bill Impacts Policy (with 7/19 comments from Ameren Illinois and ComEd) | Ameren Illinois and ComEd shared comments and edits on 7/19. | Review final edits at 7/27 meeting | 2023 - if that is not possible, no later than 2024
Electrification Energy Consumption Reduction | Nicor Gas | Nicor Gas Presentation from 6/27 Meeting: Follow-up on Electrification Comments | Nicor Gas will present what language could be agreed to at the next meeting. | Review final edits at 7/27 meeting | TBD
Evaluation Policies
Allowing Renewable Measures Under EE Programs | Guidehouse | Updated Guidehouse Policy Proposal (discussed 7/13) | Small group meeting was held on Thurs. 7/13. A smaller group discussed edited language, however agreement could not be reached at this time. This policy will not be included in the Policy Manual. If needed, agreement can be reached in the future. | None | Policy will not be included in Policy Manual
Example Measures that May Apply to the Proposed Renewable Energy/EE Policy
Program Administration Policies
Cumulative Persisting Annual Savings (CPAS) Goal Setting | ComEd | Not available yet | ComEd is reviewing stakeholder edits/may propose additional edits following 5/30 small group meeting. | No action item at this time | TBD
Prohibited Expenses | ICC Staff | Prohibited Expenses Policy (with comments from Ameren Illinois and Nicor Gas) | Policy edits discussed at 7/11 meeting - additional edits may be circulated to the group | Review final edits at 7/27 meeting | Jan. 1, 2024
FINAL DRAFT POLICIES
Policy |  | Link to Final Draft Policy | Status Update | Action Item for Interested Policy Manual Participants | Proposed Effective Date
Electrification Policies
Interactive Effects |  | Interactive Effects | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | Jan. 1, 2023; if not possible, Jan. 1, 2024
Evaluation Policies
Heating Penalty Policy |  | Heating Penalties Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | *UPDATED* Jan. 1, 2023 (per feedback from Opinion Dynamics)
Negative Savings Policy |  | Negative Savings Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | Jan. 1, 2024
Non-Qualified Equipment Policy |  | Non-Qualified Equipment Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | Jan. 1, 2024
Income Qualified Policies
Single Family IQ Eligibility Verification Guidelines Policy (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | Proposed policy edit: For non-IHWAP braided, single-family whole building retrofit projects, a self-certification process “will include information in languages other than English when there is a demonstrated need… --”The utilities will check on which languages information is provided other than English. Proposed policy edit: “Program Administrators, to the extent they utilize Community Action Agencies (CAAs) and Community-Based Organizations (CBOs) to establish eligibility for income qualified programs, shall permit those entities to use reasonable discretion to serve needy customers using low-income funds even if the customer cannot produce documentation of income and/or they do not meet any of the eligibility requirements above but shall document its decision to qualify the customer as eligible for low-income funds.” --Ameren Illinois will review edit with programs team; other utilities will also review. Review proposed effective date | October 2022 (this is the date the "interim resolution" was finalized)
Net-to-Gross Policy for Disadvantaged Areas (see linked document) |  | IQ Policies for Policy Manual | No feedback received from IQ review | Review proposed effective date | Jan. 1, 2024
LIEEAC Facilitator Independence (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19; policy is final | Review proposed effective date | Jan. 1, 2024
SAG Financial Conflict of Interest Policy (see linked document) |  | IQ Policies for Policy Manual | Policy will not be included in manual, it will stay in the SAG Process Guidance Document with edits incorporated into the 2024 update. Proposed edits will be discussed this fall. | N/A | N/A
All IQ Items Discussed Through SAG Should be Grouped Together (see linked document) |  | IQ Policies for Policy Manual | No feedback received from IQ review | Review proposed effective date | Jan. 1, 2024
IQ Multi-Family Reporting Principles (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | Review proposed effective date | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
IQ Health and Safety Reporting Principles (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | Review proposed effective date | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Equity and Affordability Reporting (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | An edit was proposed by Community Investment Corp. to the second section of the policy regarding periodic analyses performed by the utilities: “The number or proportion of energy efficiency program participants that are payment troubled (e.g., customers at risk of being disconnected; with high arrears; participating in bill assistance programs).” --Utilities will check internally with their program teams on whether/how this addition to the policy could be operationalized. Review proposed effective date | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Diverse Contracting Reporting (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | SAG Facilitator followed up with Cheryl Watson. Cheryl suggested using “historically disadvantaged communities”, instead of “environmental justice.” --Cheryl may propose an additional edit to clarify further. Review proposed effective date | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
One Stop Shop Program Design Definition for IQ Multi-Family Retrofit (see linked document) |  | IQ Policies for Policy Manual | Feedback discussed 7/19 | Karen Lusson will review and propose edits based on the 7/19 discussion. Review proposed effective date | 2022
Independence Policies
IL-TRM Administrator Role Policy |  | Track Changes Edits to Policy Manual | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | Jan. 1, 2024
Track Changes Edits to IL-TRM Policy Document
IL-TRM Administrator and Independent Evaluator Contract Review Policy |  | IL-TRM Administrator and Independent Evaluator Contract Review Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date | Jan. 1, 2024
Other Policy Updates
Administrative Edits to Policy Manual |  | Administrative Edits (6/29/23) | SAG Facilitator incorporated two additional edits flagged during 6/27 meeting. No other concerns were raised; administrative edits will be finalized. | Review proposed effective date | Jan. 1, 2024
Section 8 Policy Manual Edits |  | Additional Redline Edits to Policy Manual Section 8 (Total Resource Cost Test) | Small Group proposed redline edits to Policy Manual to reflect "costs as costs" and "benefits as benefits". First round of comments was due in Feb. Comments received from Blacks in Green and PG/NSG. Small group made additional minor edits. Final comments on edits were due July 10. Confirmed edits are final at July 11 meeting. | Review proposed effective date | Jan. 1, 2024