## Sheet1
SAG Policy Manual Subcommittee
Policy Manual Version 3.0 Update Process
Policy Manual Status Update Table with Proposed Effective Dates (updated 7/28/2023)
Policy | Link to Final Draft Policy | Action Items | Proposed Effective Date | Comments on Proposed Effective Dates (Comments due Wed. 8/9)
Electrification Policies
Electrification Bill Impacts | Electrification Bill Impacts Policy | There is one remaining sentence that has not been agreed to include in the policy: “Utilities shall also provide bill impacts by individual electrification measures.” Scott Eckel, ICC, Office of General Counsel (OGC) will review internally and follow-up by Friday, Aug. 4, if possible. Key question: Is this required by the statute? | Jan. 1, 2024
Electrification Energy Consumption Reduction | Electrification Energy Consumption Reduction Policy | Nicor Gas, PG/NSG have concerns about the language in paragraph #3. They will discuss internally and follow-up. | Jan. 1, 2024
Interactive Effects | Interactive Effects | N/A | Jan. 1, 2023; if not possible, Jan. 1, 2024
Evaluation Policies
Heating Penalty Policy | Heating Penalties Policy | N/A | Jan. 1, 2023
Negative Savings Policy | Negative Savings Policy | N/A | Jan. 1, 2024
Non-Qualified Equipment Policy | Non-Qualified Equipment Policy | N/A | Jan. 1, 2024
Income Qualified Policies
Single Family IQ Eligibility Verification Guidelines Policy | IQ Policies for Policy Manual (updated 7/27) | N/A | October 2022 (this is the date the "interim resolution" was finalized)
Net-to-Gross Policy for Disadvantaged Areas | IQ Policies for Policy Manual (updated 7/27) | N/A | Jan. 1, 2024
LIEEAC Facilitator Independence | IQ Policies for Policy Manual (updated 7/27) | N/A | Jan. 1, 2024
All IQ Items Discussed Through SAG Should be Grouped Together | IQ Policies for Policy Manual (updated 7/27) | N/A | Jan. 1, 2024
IQ Multi-Family Reporting Principles | IQ Policies for Policy Manual (updated 7/27) | Need to finalize the process-related language at the end of the policy (see redline in document) | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
IQ Health and Safety Reporting Principles | IQ Policies for Policy Manual (updated 7/27) | Need to finalize the process-related language at the end of the policy (see redline in document) | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Equity and Affordability Reporting | IQ Policies for Policy Manual (updated 7/27) | 7/27 Follow-up: Need to determine whether the bullet “The number or proportion of energy efficiency program participants that are payment troubled (e.g., customers at risk of being disconnected; with high arrears; participating in bill assistance programs)” should be included in the Policy Manual, or separately in the SAG Reporting Working Group metrics discussion. SAG Facilitator will follow-up with interested parties. Need to finalize the process-related language at the end of the policy. The language in red below has not been agreed to by utilities. | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Diverse Contracting Reporting | IQ Policies for Policy Manual (updated 7/27) | 7/27 Follow-up: Elizabeth Horne asked whether “historically” is needed in the updated phrase “historically disadvantaged communities.” SAG Facilitator to follow-up with Cheryl Watson about this phrase, and share any feedback with Elizabeth. Need to finalize the process-related language at the end of the policy. The language in red below has not been agreed to by utilities. | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
One Stop Shop Program Design Definition for IQ Multi-Family Retrofit | One-Stop-Shop Program Design Definition for Income Qualified Multifamily Retrofit Policy | 7/27 Follow-up: The utilities will review internally to make sure the new policy edits can be operationalized. Written feedback due by Wed. August 9. | *Updated 7/28* As early as possible, but no later than Jan. 1, 2024
Independence Policies
IL-TRM Administrator Role Policy | Track Changes Edits to Policy Manual | N/A | Jan. 1, 2024
Track Changes Edits to IL-TRM Policy Document
IL-TRM Administrator and Independent Evaluator Contract Review Policy | IL-TRM Administrator and Independent Evaluator Contract Review Policy | N/A | Jan. 1, 2024
Program Administration Policies
Cumulative Persisting Annual Savings (CPAS) Goal Setting | Not available yet | ComEd is reviewing stakeholder edits/may propose additional edits following 5/30 small group meeting. | TBD
Prohibited Expenses | Prohibited Expenses Policy | 7/27 Follow-up: Utilities will take this back to internal legal and accounting teams. Are there any suggestions on how this language could be revised? Karen Lusson and Elizabeth Horne will follow-up with Jean Gibson. | Jan. 1, 2024
Other Policy Updates
Administrative Edits to Policy Manual | Administrative Edits (6/29/23) | N/A | Jan. 1, 2024
Section 8 Policy Manual Edits | Additional Redline Edits to Policy Manual Section 8 (Total Resource Cost Test) | N/A | Jan. 1, 2024