## Sheet1
SAG Policy Manual Subcommittee
Policy Manual Version 3.0 Update Process
Policy Manual Status Update Table with Proposed Effective Dates (updated 7/6/2023)
OPEN POLICIES
Policy | Policy Proposed By | Policy Materials | Status Update | Action Item for Interested Policy Manual Participants | Proposed Effective Date
Electrification Policies
Electrification Bill Impacts | Nicor Gas | Nicor Gas Presentation from 6/27 Meeting: Follow-up on Electrification Comments | Policy edits discussed at 6/27 meeting. Nicor Gas, Peoples Gas & North Shore Gas to coordinate and create “clean” compromise version of bill impacts policy for Policy Manual Subcommittee to review. | Participate in 7/11 Policy Manual meeting when follow-up policy is presented | TBD
Electrification Energy Consumption Reduction | Nicor Gas | Nicor Gas Presentation from 6/27 Meeting: Follow-up on Electrification Comments | Policy edits discussed at 6/27 meeting. Nicor Gas, Peoples Gas & North Shore Gas to coordinate and create “clean” compromise version of bill impacts policy for Policy Manual Subcommittee to review. | Participate in 7/11 Policy Manual meeting when follow-up policy is presented | TBD
Bill Impacts Working Group | Peoples Gas & North Shore Gas | Peoples Gas & North Shore Gas Compromise Policy Proposal from 6/27 Meeting: Bill Impacts | Compromise proposal presented at 6/27 meeting. Nicor Gas, Peoples Gas & North Shore Gas to coordinate and create “clean” compromise version of bill impacts policy for Policy Manual Subcommittee to review. | Participate in 7/11 Policy Manual meeting when follow-up policy is presented | TBD
Evaluation Policies
Allowing Renewable Measures Under EE Programs | Guidehouse | Allowing Renewable Measures Under EE Programs | Small group meeting scheduled on Thurs. 7/13 | Participate in 7/13 small group meeting | TBD
Example Measures that May Apply to the Proposed Renewable Energy/EE Policy
Program Administration Policies
Cumulative Persisting Annual Savings (CPAS) Goal Setting | ComEd | Not available yet | ComEd is reviewing stakeholder edits/may propose additional edits following 5/30 small group meeting. | No action item at this time | N/A - policy will not be included in manual
Prohibited Expenses | ICC Staff | Prohibited Expenses Policy (with comments from Ameren Illinois and Nicor Gas) | Policy edits discussed at 6/27 meeting | ICC Staff is preparing additonal policy edits, to present at 7/11 meeting | Jan. 1, 2024
Other Policy Updates
Section 8 Policy Manual Edits | Various - edits drafted by a small group | Additional Redline Edits to Policy Manual Section 8 (Total Resource Cost Test) | Small Group proposed redline edits to Policy Manual to reflect "costs as costs" and "benefits as benefits". First round of comments was due in Feb. Comments received from Blacks in Green and PG/NSG. Small group made additional minor edits. | Final comments on additional edits due Monday, July 10 | Jan. 1, 2024
FINAL DRAFT POLICIES
Policy |  | Link to Final Draft Policy | Status Update | Action Item for Interested Policy Manual Participants | Proposed Effective Date
Electrification Policies
Interactive Effects |  | Interactive Effects | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2023; if not possible, Jan. 1, 2024
Evaluation Policies
Heating Penalty Policy |  | Heating Penalties Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2024
Negative Savings Policy |  | Negative Savings Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2024
Non-Qualified Equipment Policy |  | Non-Qualified Equipment Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2024
Income Qualified Policies
Single Family IQ Eligibility Verification Guidelines Policy (see page 3 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting | October 2022 (this is the date the "interim resolution" was finalized)
Net-to-Gross Policy for Disadvantaged Areas (see page 5 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting --Nicor Gas, PG/NSG to follow-up on rate class eligibility --Discuss other proposed redline edits in policy | Jan. 1, 2024
LIEEAC Facilitator Independence (see page 7 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting | Jan. 1, 2024
SAG Financial Conflict of Interest Policy (see page 8 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting | N/A - policy will not be included in manual, it will stay in the SAG Process Guidance Document with edits incorporated into the 2024 update
All IQ Items Discussed Through SAG Should be Grouped Together (see page 10 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting | Jan. 1, 2024
IQ Multi-Family Reporting Principles (see page 11 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting --Discuss final paragraph about incorporating into future EE Plans | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
IQ Health and Safety Reporting Principles (see page 12 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting --Discuss final paragraph about incorporating into future EE Plans | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Equity and Affordability Reporting (see page 13 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting --Discuss final paragraph about incorporating into future EE Plans | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
Diverse Contracting Reporting (see page 14 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting --Discuss final paragraph about incorporating into future EE Plans | Jan. 1, 2024 Program Administrators will apply best efforts to address as many of the objectives as possible in reporting for both program year 2022 and program year 2023.
One Stop Shop Program Design Definition for IQ Multi-Family Retrofit (see page 15 in linked document) |  | Income Qualified (IQ) Policies Developed by SAG Policy Manual Subcommittee | Feedback requested from SAG Equity Subcommittee, IQ North and IQ South EE Committees at 6/26 meeting; due 7/17 | Review proposed effective date, goal is to finalize effective dates at July 11 meeting IQ Committee feedback will be discussed at 7/19 meeting | 2022
Independence Policies
IL-TRM Administrator Role Policy |  | Track Changes Edits to Policy Manual | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2024
Track Changes Edits to IL-TRM Policy Document
IL-TRM Administrator and Independent Evaluator Contract Review Policy |  | IL-TRM Administrator and Independent Evaluator Contract Review Policy | Policy is considered "final draft"; confirm final effective date at end of Policy Manual process (July 2023) | Review proposed effective date, goal is to finalize effective dates at July 11 meeting | Jan. 1, 2024
Other Policy Updates
Administrative Edits to Policy Manual |  | Administrative Edits (6/29/23) | SAG Facilitator incorporated two additional edits flagged during 6/27 meeting. No other concerns were raised; administrative edits will be finalized. | No action item at this time | Jan. 1, 2024