## Large Group SAG
2026 Large Group SAG Follow-up Items |  |  |  | Last Update: 9/4/26
Purpose: This is a tracking document to summarize open issues and follow-up items from Large Group SAG meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
Large Group SAG Net-to-Gross (NTG) Meeting #1 | Sep. 3, 2026 | For independent evaluators to present initial Net-toGross (NTG) recommendations for the 2027 program year, including proposed changes compared to the previous year and notable research results. | 1. A question was raised about whether SAG has a policy on SAG participants using an AI notetaker. The SAG Facilitator will raise this with the SAG Steering Committee at the next meeting, scheduled in December. 2. ComEd NTG Values: Guidehouse will update the definition used for DIY Big Box and Warehouse, to be consistent with the IL-TRM.
Large Group SAG | Jul. 15, 2026 | For the SAG Facilitator to present an overview of the 2026 SAG Plan and request feedback. | SAG Facilitator to provide final 2026 SAG Plan and final SAG Process Guidance document by July 31. | The final SAG planning materials for 2026 are posted on the SAG Planning page:
2026 SAG Plan (Final 7/31/2026)
SAG Process Guidance 2026 Update (Final 7/30/2026)
Large Group SAG | Jun. 8, 2026 | To discuss interpretation of the Net-to-Gross (NTG) Ratio for Disadvantaged Areas policy (see Illinois Energy Efficiency Policy Manual Section 7.4), regarding how Trade Allies are considered in application of the policy. | 1. Does Guidehouse remove distributors or trade allies from their NTG samples when they are in disadvantaged areas? | 1. Response from Guidehouse: For ComEd, with the exception of the Commercial Instant Discounts program, Trade Allies/Distributors are removed when in DACs. Because of the small sample size available for the Instant Discounts program, removing them prevents statistically valid results, so the Trade Allies/Distributors are not removed. For IL GAS, similarly, Trade Allies are not removed when there is a small sample.
|  |  | 2. A request for feedback was circulated to SAG following the meeting, due on June 26: Should the location of a Trade Ally in a utility's service territory be considered when applying the NTG for Disadvantaged Areas policy? | Comments received on June 26 are posted on the Policy page: https://www.ilsag.info/policy/ There was also an opportunity for comments on a potential compromise, due on August 19. Comments are posted on the Policy page. Resolution of this issue is TBD; there is currently no consensus.
Large Group SAG | Mar. 31, 2026 | For stakeholders to present feedback on the Nicor Gas draft revised 2027-2029 EE Plan, presented to SAG on March 24. | March 31, 2026 Large Group SAG Meeting: Follow-up Items for Nicor Gas | Responses to follow-up items will be discussed during confidential negotiations between Nicor Gas and non-financially interested parties, if needed.
Large Group SAG | Mar. 24, 2026 | 1. For Nicor Gas to present the revised draft 2027-2029 EE Plan | Nicor Gas Follow-up Items: 1. NCLC: What is the breakdown by program for the IE weatherization budgets on slide 21? 2. NRDC: From slide 33, can you show us what the numbers look like if extended to 2040? Over the full life of the amortization. 3. NRDC requested additional discussion regarding measure life. 4. NRDC: For future discussions, it would be helpful if Nicor Gas could provide breakdowns of what the significantly increased MT budget would be spent on, as well as whether the Company intends to claim savings from MT. Similar question/request for R&D. 5. NCLC: Will the return on the EE asset be the overall ROR of 6.90% or the ROE of 9.60%? | Responses to follow-up items will be discussed during confidential negotiations between Nicor Gas and non-financially interested parties, if needed.
|  | 2. For stakeholders to present feedback on Peoples Gas and North Shore Gas’ draft revised EE Plan, presented to SAG on March 17. | PGL-NSG Follow-up Items: 1. ICC Staff and ICC Office of General Counsel: For the added Clean and Reliable Grid Act or ("CRGA") spending, what is the expected cost per additional therm saved? 8-104(e20) a. Please provide this: i. for the revised portfolio overall, and ii. by major sector if available, such as residential, income-qualified, business, and public sector. 2. ICC Staff and ICC Office of General Counsel: How much of the added CRGA spending is expected to produce savings beyond what would have been achieved under the previously approved plan? Please explain, in plain language, what savings are truly incremental because of the CRGA revision. 3. ICC Staff and ICC Office of General Counsel: How will Peoples Gas/North Shore meet the separate requirement that at least 10% of the entire portfolio (of EE measures) be procured from local governments, municipal corporations, school districts, and community college districts? 8-103(e). 4. ICC Staff and ICC Office of General Counsel: How many customers, buildings, or units do you expect to serve under the revised plan? 5. IL AG’s Office: Requested all information presented in comparison to approved 2026-29 Plan. Redline copies of 2026-29 stipulation and plan preferred. March 17 presentation already included some comparisons. Thank you, this is helpful. 6. IL AG’s Office: Explanation and calculation of anticipated savings. Confirm income eligible (IE) commitment does not affect savings goals. | Responses to follow-up items will be discussed during confidential negotiations between Peoples Gas & North Shore Gas and non-financially interested parties, if needed.
Large Group SAG | Mar. 17, 2026 | 1. For interested SAG participants to present feedback on the Ameren Illinois draft 2027-2029 EE Plan | Follow-up Items for Ameren Illinois from March 17 SAG Meeting | Responses to follow-up items will be discussed during confidential negotiations between Ameren Illinois and non-financially interested parties, if needed.
|  | 2. For Peoples Gas and North Shore Gas to present the revised draft 2027-2029 EE Plan. | PGL-NSG Follow-up Items: 1. NCLC: What percentage of the Home Energy Savings weatherization program will be allocated to "major measures"? 2. Community Investment Corp.: For the kits, is success measured by customers who then take up further retrofits? 3. NCLC: Requested an explanation of "Epic Savers". PGL/NSG to provide a description. 4. Community Investment Corp. Question Sent by Email: Can PG-NSG outline in more detail how increasing IQ spending impacts program implementation in practice. For example, will this allow for deeper retrofits/more measures available, more parity in cost sharing for joint programs which may lead to serving more customers (or perhaps a combination of both!). | Peoples Gas and North Shore Gas Responses to March 17 SAG Questions
Large Group SAG | Mar. 4, 2026 | For Ameren Illinois to present a draft revised EE Plan for 2027-2029. | 1. Karen Lusson (NCLC) requested an explanation of the 6-12% reference on slide 21: Home Efficiency represents 6-12% of the Residential (incl IQ) Budget in 2027-2029, compared to 2% for 2026 2. Kari Ross (NRDC): What channels will the moderate income program be focused on? 3. Abby Miner (Illinois Office of the Attorney General) requested definitions or short descriptions of each program. | Ameren Illinois Responses to March 4 SAG Questions
Small Group SAG | Mar. 3, 2026 | To hold a follow-up discussion on feedback received on the Inflation Reduction Act (IRA) savings attribution policy proposal presented by Illinois utilities during the January 13 Large Group SAG meeting. | ComEd will prepare a draft policy document and coordinate with the other utilities before circulating the document for review. Process to resolve final IRA attribution policy document: 1. The final draft IRA attribution policy document will be circulated for review to the distribution list from the March 3 SAG Small Group Meeting. 2. If substantive edits are received, a follow-up discussion will be scheduled with parties who shared proposed edit(s). 3. The final policy document will be posted on the Policy page of the SAG website. 4. The policy will be included in the next comprehensive update to the Policy Manual, planned for 2027. | The draft policy document was circulated for review on June 30. Comments were due on July 17. Comments received are posted on the policy page: https://www.ilsag.info/policy/ IL utilities are currently working on responding to comments.
Large Group SAG | Jan. 13, 2026 | 1. For interested SAG participants to present feedback on the draft ComEd 2027-2029 EE Plan presented to SAG on December 18 | 1. Several SAG participants requested an Income Eligible (IE) breakout. | ComEd provided an updated 2027-2029 EE Plan presentation, with updated spend/savings tables including a breakout of Income Eligible (IE) spend. See the appendix beginning on slide 29: ComEd Revised Draft EE Plan for 2027-2029 (1/14/26)
|  |  | 2. NRDC requested customer journey mapping for the joint residential Home Energy Savings offering. | See the northern Illinois utilities’ September 18, 2025 SAG Equity Subcommittee presentation (slide 2): SAG-Retrofits-Prioritization_9.18-Joint-Utility-Presentation_updated.pdf
|  |  | 3. Following the January 13 meeting, SAG participants had an opportunity to submit additional feedback to ComEd in writing. Feedback was due by Wednesday, January 21. | The following feedback was received: Comments from The Preservation Compact (1/21/26)
|  | 2. To discuss Inflation Reduction Act (IRA) attribution with Illinois utility EE programs. | 2. A request for feedback was circulated to SAG following the meeting, due on January 28. | Comments received in January are posted on the Policy page: https://www.ilsag.info/policy/ There was a SAG Small Group meeting on March 3 to discuss policy feedback - see the tracker above.

## SAG Equity Subcommittee
2026 SAG Equity Subcommittee Follow-up Items |  |  |  | Last Update: TBD
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Equity Subcommittee meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG Equity Subcommittee | Oct. 28, 2026
SAG Equity Subcommittee | Sept. 22, 2026

## SAG MT Working Group
2026 SAG Market Transformation Savings Working Group Follow-up Items |  |  |  | Last Update: TBD
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Market Transformation (MT) Savings Working Group meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG MT Savings Working Group | Oct. 6, 2026

## SAG NEI Working Group
2026 SAG Non-Energy Impacts Working Group Follow-up Items |  |  |  | Last Update: TBD
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Non-Energy Impacts (NEI) Working Group meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG NEI Working Group | Nov. 2, 2026