## Large Group SAG
2026 Large Group SAG Follow-up Items |  |  |  | Last Update: 10/7/26
Purpose: This is a tracking document to summarize open issues and follow-up items from Large Group SAG meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
Large Group SAG Q3 Meeting | Sept. 29, 2026 | 1. For Ameren Illinois to report-out on EE Portfolio progress in 2026 | 1. Slide 26 of the Appendix includes “Income-Qualified Single Family and Multifamily Installed Units by Measure.” The numbers for SF and MF are out of a total of how many units served (separated by SF and MF)? 2. Slide 13 mentions MF challenges. Has Ameren experienced a difference between master metered and individually metered MF units? 3. Slide 13 mentions gaps in contractor capacity. Once Ameren identifies gaps, does Ameren work with the state weatherization program or the CEJA job training programs to see if there are opportunities to engage trade allies through those programs? Ameren offered to follow-up with information about Ameren’s recruitment plan. 4. Slide 14 mentions a 10% accessibility referral conversion to whole-home comprehensive programs. Does Ameren have data on the 10% figure and how the company might be utilizing tools to increase that conversion? 5. Slide 15 describes Ameren’s electrification bill impact analysis tool. There was discussion in the meeting chat regarding whether the tool uses the Low Income Credit Adjustment (LICA) for gas, or ESDA for electric. Can Ameren explain why this data hasn’t been included, or what the plans might be to use this in the future?
|  | 2. For ComEd to report-out on EE Portfolio progress in 2026 | 1. For the IQ joint weatherization program, provide the breakdown of SF vs. MF, and IHWAP vs. utility only (joint), for both customer participation and budget through Q2. 2. ComEd will follow-up with additional details on the cold climate heat pump specification that is used for the full electrification offering and for the partial /hybrid electrification offering. Is it the ENERGY STAR cold climate, the NEAP cold climate, or something else? 3. Does ComEd have a standard switchover temperature that is recommended for partial/hybrid electrification? 4. Research & Development: What is the budget for the AC variation pilot? 5. 2026 Whole Home Electrification Program Highlights: Why aren't the electric resistance heat (ERH) homes provided the savings?
|  | 3. For the SAG Facilitator to share a SAG update | No follow-up items. | N/A
Large Group SAG Net-to-Gross (NTG) Meeting #3 | Sept. 17, 2026 | To follow-up on evaluator Net-to-Gross (NTG) recommendations for ComEd for the 2027 program year and discuss consensus. | The Office of the Illinois Attorney General (AG) is reviewing Guidehouse responses to their questions regarding ComEd Data Center New Construction NTG values. If there is a change to this NTG value, it will be discussed during NTG Meeting #4 (scheduled on Thursday, Sept. 24). If there is no change and consensus is reached with the AG, NTG Meeting #4 will be cancelled. | Resolved. Final NTG spreadsheets for 2027 were posted and circulated to SAG.
Large Group SAG Net-to-Gross (NTG) Meeting #2 | Sept. 10, 2026 | To follow-up on evaluator Net-to-Gross (NTG) recommendations for each utility for the 2027 program year and discuss consensus. | Follow-up items for Guidehouse on the ComEd Custom Program Memo: 1. Provide the survey instruments used for data center research and add to the memo. 2. Add a paragraph to the memo regarding changes to Data Center New Construction program design. | ComEd Custom Program CY2025 Net-to-Gross Research Results Memo (Redline 9/16/2026)
|  |  | Follow-up questions for Guidehouse and ComEd from the Office of the Illinois Attorney General: 1. Data Center New Construction: The basis for the recommended change is based on "In-depth telephone interviews and web surveys for sampled projects" a. How many interviews/surveys were conducted? b. What were the sizes of the sampled data center projects? Were they hyper-scalers, whole building data centers, subcomponent of a building, etc.? c. What questions were asked to ascertain free ridership? How was it determined that the incentive influenced the project scope? d. What are the expected data center sizes for the future applications? Should there be different approaches for different scales? 2. All but Street Lights and Data Centers New Construction a. How many interviews/surveys were conducted? b. What questions were asked? (Note: Guidehouse stated it can add the survey to the end of the memo as an appendix.) | ComEd NTG Values – Office of the Illinois Attorney General Questions with Guidehouse Responses (Final 9/18/2026)
Large Group SAG Net-to-Gross (NTG) Meeting #1 | Sep. 3, 2026 | For independent evaluators to present initial Net-toGross (NTG) recommendations for the 2027 program year, including proposed changes compared to the previous year and notable research results. | 1. A question was raised about whether SAG has a policy on SAG participants using an AI notetaker. 2. ComEd NTG Values: Guidehouse will update the definition used for DIY Big Box and Warehouse, to be consistent with the IL-TRM. | 1. The SAG Facilitator will raise this with the SAG Steering Committee at the next meeting, scheduled in December. 2. No response needed.
Large Group SAG | Jul. 15, 2026 | For the SAG Facilitator to present an overview of the 2026 SAG Plan and request feedback. | SAG Facilitator to provide final 2026 SAG Plan and final SAG Process Guidance document by July 31. | The final SAG planning materials for 2026 are posted on the SAG Planning page:
2026 SAG Plan (Final 7/31/2026)
SAG Process Guidance 2026 Update (Final 7/30/2026)
Large Group SAG | Jun. 8, 2026 | To discuss interpretation of the Net-to-Gross (NTG) Ratio for Disadvantaged Areas policy (see Illinois Energy Efficiency Policy Manual Section 7.4), regarding how Trade Allies are considered in application of the policy. | 1. Does Guidehouse remove distributors or trade allies from their NTG samples when they are in disadvantaged areas? | 1. Response from Guidehouse: For ComEd, with the exception of the Commercial Instant Discounts program, Trade Allies/Distributors are removed when in DACs. Because of the small sample size available for the Instant Discounts program, removing them prevents statistically valid results, so the Trade Allies/Distributors are not removed. For IL GAS, similarly, Trade Allies are not removed when there is a small sample.
|  |  | 2. A request for feedback was circulated to SAG following the meeting, due on June 26: Should the location of a Trade Ally in a utility's service territory be considered when applying the NTG for Disadvantaged Areas policy? | Comments received on June 26 are posted on the Policy page: https://www.ilsag.info/policy/ There was also an opportunity for comments on a potential compromise, due on August 19. Comments are posted on the Policy page. Resolution of this issue is TBD; there is currently no consensus.
Large Group SAG | Mar. 31, 2026 | For stakeholders to present feedback on the Nicor Gas draft revised 2027-2029 EE Plan, presented to SAG on March 24. | March 31, 2026 Large Group SAG Meeting: Follow-up Items for Nicor Gas | Responses to follow-up items will be discussed during confidential negotiations between Nicor Gas and non-financially interested parties, if needed.
Large Group SAG | Mar. 24, 2026 | 1. For Nicor Gas to present the revised draft 2027-2029 EE Plan | Nicor Gas Follow-up Items: 1. NCLC: What is the breakdown by program for the IE weatherization budgets on slide 21? 2. NRDC: From slide 33, can you show us what the numbers look like if extended to 2040? Over the full life of the amortization. 3. NRDC requested additional discussion regarding measure life. 4. NRDC: For future discussions, it would be helpful if Nicor Gas could provide breakdowns of what the significantly increased MT budget would be spent on, as well as whether the Company intends to claim savings from MT. Similar question/request for R&D. 5. NCLC: Will the return on the EE asset be the overall ROR of 6.90% or the ROE of 9.60%? | Responses to follow-up items will be discussed during confidential negotiations between Nicor Gas and non-financially interested parties, if needed.
|  | 2. For stakeholders to present feedback on Peoples Gas and North Shore Gas’ draft revised EE Plan, presented to SAG on March 17. | PGL-NSG Follow-up Items: 1. ICC Staff and ICC Office of General Counsel: For the added Clean and Reliable Grid Act or ("CRGA") spending, what is the expected cost per additional therm saved? 8-104(e20) a. Please provide this: i. for the revised portfolio overall, and ii. by major sector if available, such as residential, income-qualified, business, and public sector. 2. ICC Staff and ICC Office of General Counsel: How much of the added CRGA spending is expected to produce savings beyond what would have been achieved under the previously approved plan? Please explain, in plain language, what savings are truly incremental because of the CRGA revision. 3. ICC Staff and ICC Office of General Counsel: How will Peoples Gas/North Shore meet the separate requirement that at least 10% of the entire portfolio (of EE measures) be procured from local governments, municipal corporations, school districts, and community college districts? 8-103(e). 4. ICC Staff and ICC Office of General Counsel: How many customers, buildings, or units do you expect to serve under the revised plan? 5. IL AG’s Office: Requested all information presented in comparison to approved 2026-29 Plan. Redline copies of 2026-29 stipulation and plan preferred. March 17 presentation already included some comparisons. Thank you, this is helpful. 6. IL AG’s Office: Explanation and calculation of anticipated savings. Confirm income eligible (IE) commitment does not affect savings goals. | Responses to follow-up items will be discussed during confidential negotiations between Peoples Gas & North Shore Gas and non-financially interested parties, if needed.
Large Group SAG | Mar. 17, 2026 | 1. For interested SAG participants to present feedback on the Ameren Illinois draft 2027-2029 EE Plan | Follow-up Items for Ameren Illinois from March 17 SAG Meeting | Responses to follow-up items will be discussed during confidential negotiations between Ameren Illinois and non-financially interested parties, if needed.
|  | 2. For Peoples Gas and North Shore Gas to present the revised draft 2027-2029 EE Plan. | PGL-NSG Follow-up Items: 1. NCLC: What percentage of the Home Energy Savings weatherization program will be allocated to "major measures"? 2. Community Investment Corp.: For the kits, is success measured by customers who then take up further retrofits? 3. NCLC: Requested an explanation of "Epic Savers". PGL/NSG to provide a description. 4. Community Investment Corp. Question Sent by Email: Can PG-NSG outline in more detail how increasing IQ spending impacts program implementation in practice. For example, will this allow for deeper retrofits/more measures available, more parity in cost sharing for joint programs which may lead to serving more customers (or perhaps a combination of both!). | Peoples Gas and North Shore Gas Responses to March 17 SAG Questions
Large Group SAG | Mar. 4, 2026 | For Ameren Illinois to present a draft revised EE Plan for 2027-2029. | 1. Karen Lusson (NCLC) requested an explanation of the 6-12% reference on slide 21: Home Efficiency represents 6-12% of the Residential (incl IQ) Budget in 2027-2029, compared to 2% for 2026 2. Kari Ross (NRDC): What channels will the moderate income program be focused on? 3. Abby Miner (Illinois Office of the Attorney General) requested definitions or short descriptions of each program. | Ameren Illinois Responses to March 4 SAG Questions
Small Group SAG | Mar. 3, 2026 | To hold a follow-up discussion on feedback received on the Inflation Reduction Act (IRA) savings attribution policy proposal presented by Illinois utilities during the January 13 Large Group SAG meeting. | ComEd will prepare a draft policy document and coordinate with the other utilities before circulating the document for review. Process to resolve final IRA attribution policy document: 1. The final draft IRA attribution policy document will be circulated for review to the distribution list from the March 3 SAG Small Group Meeting. 2. If substantive edits are received, a follow-up discussion will be scheduled with parties who shared proposed edit(s). 3. The final policy document will be posted on the Policy page of the SAG website. 4. The policy will be included in the next comprehensive update to the Policy Manual, planned for 2027. | The draft policy document was circulated for review on June 30. Comments were due on July 17. Comments received are posted on the policy page: https://www.ilsag.info/policy/ IL utilities are currently working on responding to comments.
Large Group SAG | Jan. 13, 2026 | 1. For interested SAG participants to present feedback on the draft ComEd 2027-2029 EE Plan presented to SAG on December 18 | 1. Several SAG participants requested an Income Eligible (IE) breakout. | ComEd provided an updated 2027-2029 EE Plan presentation, with updated spend/savings tables including a breakout of Income Eligible (IE) spend. See the appendix beginning on slide 29: ComEd Revised Draft EE Plan for 2027-2029 (1/14/26)
|  |  | 2. NRDC requested customer journey mapping for the joint residential Home Energy Savings offering. | See the northern Illinois utilities’ September 18, 2025 SAG Equity Subcommittee presentation (slide 2): SAG-Retrofits-Prioritization_9.18-Joint-Utility-Presentation_updated.pdf
|  |  | 3. Following the January 13 meeting, SAG participants had an opportunity to submit additional feedback to ComEd in writing. Feedback was due by Wednesday, January 21. | The following feedback was received: Comments from The Preservation Compact (1/21/26)
|  | 2. To discuss Inflation Reduction Act (IRA) attribution with Illinois utility EE programs. | 2. A request for feedback was circulated to SAG following the meeting, due on January 28. | Comments received in January are posted on the Policy page: https://www.ilsag.info/policy/ There was a SAG Small Group meeting on March 3 to discuss policy feedback - see the tracker above.

## SAG Equity Subcommittee
2026 SAG Equity Subcommittee Follow-up Items |  |  |  | Last Update: 10/7/2026
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Equity Subcommittee meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG Equity Subcommittee | Oct. 28, 2026
SAG Equity Subcommittee | Sept. 22, 2026 | 1. For the IQ South EE Committee to report-out on 2026 activities; 2. For the IQ North EE Committee to report-out on 2026 activities; and 3. To educate participants on the Ameren Illinois Phase 2 Market Development Initiative (MDI) assessment. | No follow-up items. | N/A

## SAG MT Working Group
2026 SAG Market Transformation Savings Working Group Follow-up Items |  |  |  | Last Update: TBD
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Market Transformation (MT) Savings Working Group meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG MT Savings Working Group | Oct. 6, 2026 | 1. To request feedback on a proposed approach for future SAG MT Savings Working Group meetings | Feedack is requested on the SAG Facilitator’s Market Transformation Working Group process proposal - due Wednesday, October 21. Visit the October 6 meeting page for the comment template.
|  | 2. To discuss ComEd appliance MT initiative updates. | There is an opportunity for feedback on the ComEd ENERGY STAR Retail Products Platform (ESRPP) Natural Market Baseline (NMB) revisions - due Wednesday, October 21. Visit the October 6 meeting page for the comment template.

## SAG NEI Working Group
2026 SAG Non-Energy Impacts Working Group Follow-up Items |  |  |  | Last Update: TBD
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Non-Energy Impacts (NEI) Working Group meetings held in 2026. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Yellow Highlight indicates an open item
Meeting Name | Meeting Date | Meeting Purpose | Follow-up Items | Response to Follow-up Item
SAG NEI Working Group | Nov. 2, 2026