## 1- Large Group SAG
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from Large Group SAG meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Topic or Presentation | Follow-up Item | Response to Follow-up Item
Annual SAG Evaluation Plan Meetings | Dec. 6, 2023 (Day 2) | https://www.ilsag.info/event/wednesday-december-6-sag-evaluation-plan-meeting-day-2/ | Nicor Gas 2024 Evaluation Plan | No follow-up items; initial feedback summarized in notes | N/A
|  |  | PG/NSG 2024 Evaluation Plan | No follow-up items; initial feedback summarized in notes | N/A
| Dec. 5. 2023 (Day 1) | https://www.ilsag.info/event/tuesday-december-5-sag-evaluation-plan-meeting-day-1/ | Ameren IL 2024 Evaluation Plan | No follow-up items; initial feedback summarized in notes | N/A
|  |  | ComEd 2024 Evaluation Plan | No follow-up items; initial feedback summarized in notes | N/A
Q4 Large Group SAG Meeting | Nov. 15, 2023 (Day 2) | https://www.ilsag.info/event/wednesday-november-15-q4-sag-meeting-day-2/ | Ameren IL Voltage Optimization Presentation | No follow-up items | N/A
|  |  | ComEd Voltage Optimization Presentation | No follow-up items | N/A
|  |  | PG/NSG Quarterly Update Presentation | 1) Provide additional breakdown of income qualified participation for income qualified multifamily and single-family. 2) Follow-up on where a list of implementers and subcontractors can be found for each EE program. | Pending response
|  |  | Ameren IL Quarterly Update Presentation | 1) Provide the Q3 whole building retrofit spend, and whole building projections for Q4. 2) Share more information about how the process works for customers when there is achoice of electrifying or switching to natural gas. 3) What is assumed in terms of savings achieved via the smart thermostats once they are sent to the customer? Are installations assumed? Or is there follow-up? | Ameren Illinois Follow-up to Questions Raised during November 2023 Quarterly Update Presentation
| Nov. 14, 2023 (Day 1) | https://www.ilsag.info/event/tuesday-november-14-q4-sag-meeting-day-1/ | Northern IL Utilities Multi-Family Energy Savings Presentation | See notes for list of questions raised | Follow-up Response to Questions Raised During Northern Illinois Multi-Family Energy Savings Presentation
|  |  | ComEd Quarterly Update Presentation | No follow-up items | N/A
|  |  | Nicor Gas Quarterly Update Presentation | 1) Provide the breakdown on Nicor Gas spend on income eligible weatherization since 2011. 2) If any community organizations are interested in getting involved with Nicor Gas community engagement efforts, reach out to John Mansfield: jomansfi@southernco.com | 1) Pending response 2) N/A
Q3 Large Group SAG Meeting | Sept. 26, 2023 | https://www.ilsag.info/event/tuesday-september-26-q3-sag-meeting/ | ComEd Presentation: Income Eligible Weatherization Customer Bill Impacts | 1) ComEd will share the final bill impacts report. | 1) Income-Eligible Bill Impacts Analysis (Resource Innovations Report prepared for ComEd, Nicor Gas, Peoples Gas & North Shore Gas)
|  |  |  | 2) ComEd will review the multi-family data, per questions about common area vs. tenants. 3) Karen Lusson (National Consumer Law Center) and Katie Elmore (Community Investment Corp.) are interested in more information about low IQ multi-family participation numbers (slide 8). 4) Karen Lusson (National Consumer Law Center) requested additional information about why the data shows higher gas bills in the summer. | 2) Pending response 3) Pending response 4) Pending response
|  |  | SAG Facilitator Update | The SAG Reporting Working Group will develop reporting metrics this fall, to finalize by end of January 2024. This is a follow-up to four new policies that were added to the updated Policy Manual (Version 3.0).
Annual SAG Net-to-Gross Meetings | Sept. 27, 2023 | https://www.ilsag.info/event/wednesday-september-27-sag-meeting-ntg-4/ | NTG update process meeting #4 | Identified in meeting notes | N/A
| Sept. 20, 2023 | https://www.ilsag.info/event/wednesday-september-20-sag-meeting-ntg-3/ | NTG update process meeting #3 | Identified in meeting notes | N/A
| Sept. 13, 2023 | https://www.ilsag.info/event/wednesday-september-13-sag-meeting-ntg-2/ | NTG update process meeting #2 | Identified in meeting notes | N/A
| Sept. 6, 2023 | https://www.ilsag.info/event/wednesday-september-6-sag-meeting-ntg-1/ | NTG update process meeting #1 | Identified in meeting notes | N/A
Q2 Large Group SAG Meeting | April 25, 2023 (Day 1) | https://www.ilsag.info/event/tuesday-april-25-q2-sag-meeting-day-1/ | Ameren IL Quarterly Update Presentation | Do you have data on walkaway rates form the audits you mentioned for HP installations (MF)? | Clarification was requested by the SAG Facilitator on May 23. A response will be provided later if clarification is received.
|  |  |  | Do you have any data about how many of these communities that participated in the (Street Light) program are black and brown or economically disadvantaged? | Ameren has always focused on disadvantaged communities to make sure lighting projects are conducted as indicated by community leaders. A full list of communities is linked below. Please contact Ameren if a particular community of interest is not shown.
https://www.ilsag.info/wp-content/uploads/Ameren-IL_LED-Enhanced-Street-Light-Communities_2023.xlsx
|  |  |  | Where are these stores that people can get bulbs at discounts? | Ameren is targeting all thrift stores, dollar stores, and 100 zip codes that we have determined to be low-to-moderate income. A list of stores can be found at PY22-Q3-Ameren-Illinois-Quarterly-Report-Final.pdf (ilsag.info). Please see Appendix B starting on page 34.
|  |  | Nicor Gas Quarterly Update Presentation | No follow-up items | N/A
| April 26, 2023 (Day 2) | https://www.ilsag.info/event/wednesday-april-26-q2-sag-meeting-day-2/ | ComEd Quarterly Update Presentation | No follow-up items | N/A
|  |  | PG/NSG Quarterly Update Presentation | No follow-up items | N/A
Q1 Large Group SAG Meeting | Mar. 22, 2023 | https://www.ilsag.info/event/wednesday-march-22-q1-sag-meeting/ | Presentations from ACEEE and the University of Michigan Energy Equity Project on EE equity metrics | No follow-up items | N/A
Large Group SAG Meeting | Jan. 19, 2023 | https://www.ilsag.info/event/thursday-january-19-sag-meeting/ | SAG Facilitator overview of 2023 SAG Plan | Feedback or edits on the Final Draft 2023 SAG Plan and SAG Process Guidance document by COB Thursday, January 26 | Final 2023 SAG Plan posted, see link below
https://www.ilsag.info/wp-content/uploads/SAG-2023-Plan_1-31-2023-FINAL.pdf

## 2- Equity Subcommittee
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Equity Subcommittee meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Presentation | Follow-up Item | Response to Follow-up Item
SAG Equity Subcommittee / Joint with IQ North and IQ South EE Committees | Dec. 13, 2023 | https://www.ilsag.info/event/december-13-2023-equity-subcommittee-meeting/ | Ameren IL Diverse Procurement MDI Initiative | 1) Email to be added Encolor’s distribution list – eeprograms_rfp@encolorconsulting.com 2) A stakeholder requested more information about other utilities’ diverse procurement initiatives. SAG Facilitator will follow-up. | 1) N/A 2) Pending response
|  |  | ComEd MDI Initiative Update | No follow-up items | N/A
|  |  | LIEEAC IQ South Subcommittee Update | The SAG Market Transformation Savings Working Group has discussed stretch codes and building performance initiatives in Illinois. SAG Facilitator to follow-up with Nelson May to share their recent presentation to SAG and contact information for Slipstream. | Completed
SAG Equity Subcommittee / Joint with IQ North and IQ South EE Committees | Jul. 12, 2023 | https://www.ilsag.info/event/wednesday-july-12-equity-subcommittee-meeting/ | IL Utilities Updates on Market Development Initiatives | Which utility EE programs have closed vs. open networks for residential, C&I and income-eligible?
From the northern Illinois utilities research presentation, what is the breakdown from the research from the states reviewed? What % of contracts are going to IL-based firms?
From the Nicor Gas presentation, share the % of overall contractors that the diverse pool represents.
If any participants have questions, feedback, or insights to share that relate to the Illinois utility Market Development Initiative offerings, please reach out to the SAG Facilitator (Celia@CeliaJohnsonConsulting.com). Written feedback is due by Friday, Sept. 22. The SAG Facilitator will coordinate with the utilities on any comments received.
SAG Equity Subcommittee / Joint with IQ North and IQ South EE Committees | Jun. 26, 2023 | https://www.ilsag.info/event/monday-june-26-equity-subcommittee-meeting-joint-with-iq-north-and-iq-south-ee-committees/ | Introduction to IQ-Related Policies for Policy Manual Version 3.0 | Feedback on IQ Policies Due by Thursday, July 13 | Deadline passed - feedback received and discussed by Policy Manual Subcommittee

## 3- NLC Subcommittee
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Network Lighting Control Subcommittee meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Presentation | Follow-up Item | Response to Follow-up Item
SAG NLC Subcommittee | Mar. 7, 2023 | https://www.ilsag.info/event/tuesday-march-7-network-lighting-controls-subcommittee-meeting/ | Ameren IL Presentation: NLC Update | No follow-up items | N/A
|  |  | ComEd Presentation: NLC Update | ComEd follow-up item: On slide 14, what share of lighting overall does this represent? There is interest in the overall standard lighting savings trend over the same period, compared to NLCs.

## 4- MT Savings Working Group
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Market Transformation (MT) Savings Working Group meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Presentation | Follow-up Item | Response to Follow-up Item
SAG MT Savings Working Group | Oct. 25, 2023 | https://www.ilsag.info/event/wednesday-october-25-market-transformation-savings-working-group-meeting/ | Ameren IL Luminaire Level Lighting Controls MT Initiative Business Plan Summary | Ameren IL requested comments on the Business Plan; circulated the Working Group with comments due 11/16. No comments received. | N/A
|  |  | Slipstream and MEEA update on Stretch Energy Codes and Building Performance Standards | No follow-up items | N/A
|  |  | Nicor Gas Update on High Performance Windows | Nicor Gas requested comments on the Logic Model and MPI table; circulated the Working Group with comments due 11/8. No comments received. | N/A
SAG MT Savings Working Group | 2023-05-22 | https://www.ilsag.info/event/monday-may-22-market-transformation-savings-working-group-meeting/ | ComEd Presentation: Review of Final Attachment C Comments | Jim Fay and small group writing team to review Attachment C edits to ensure consistency with discussion and feedback. An updated redline version will be circulated to the MT Working Group for review, highlighting any additional changes. If there are any substantive comments, a follow-up meeting will be scheduled. | Updated Attachment C circulated on 8/30; comments due by 9/13
|  |  | Status Update on Current IL MT Initiatives | Jim Fay to follow-up with Phil Mosenthal on Massachusetts codes initiative. Rick Tonielli to follow-up with Chris Neme on Retail Products Platform plumbing channel. | N/A
|  |  | Ameren Illinois Presentation: Luminaire Level Lighting Controls | Rick Tonielli to follow-up with Seth Craigo-Snell on 2022 Retail Products Platform results, vs. 2021. | N/A
|  |  | Slipstream and MEEA Presentation: Energy Codes & Building Performance Standards | No follow-up items | N/A
SAG MT Savings Working Group | Apr. 13, 2023 | https://www.ilsag.info/event/thursday-april-13-market-transformation-savings-working-group-meeting/ | ComEd Presentation: Summary of Illinois TRM Attachment C Revisions and Final Draft Policy Document | Comments on IL-TRM Attachment C and Market Transformation Policies due by Monday, May 8 | Deadline passed - feedback received and discussed by MT Savings Working Group
|  |  | ComEd and Guidehouse Presentation: Retail Products Platform Update | No follow-up items | N/A

## 5- NEI Working Group
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Non-Energy Impact Working Group meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Presentation | Follow-up Item | Response to Follow-up Item
Non-Energy Impacts Working Group Meeting | Oct. 4, 2023 | https://www.ilsag.info/event/wednesday-october-4-non-energy-impacts-working-group-meeting/ | Ameren IL IQ Participant NEI Impacts | No follow-up items | N/A

## 6- Reporting Working Group
SAG Follow-up Items in 2023
Purpose: This is a tracking document to summarize open issues and follow-up items from SAG Reporting Working Group meetings in 2023. Follow-up is organized in reverse chronological order, with the most recent meetings listed first.
Meeting Name | Meeting Date | Link to Meeting Page | Presentation | Follow-up Item | Response to Follow-up Item
Starting in October 2023, the Reporting Working Group focused on a "metrics process" to reach agreement on four sets of metrics, as referenced in the recently updated Policy Manual Version 3.0. Visit the Reporting Working Group webpage for additional information: https://www.ilsag.info/reporting-working-group/
Ameren IL Multifamily Metrics Workshop | Sept. 12, 2023 | https://www.ilsag.info/event/tuesday-september-12-reporting-working-group-meeting/ | Ameren Illinois Presentation: Multi-Family Metrics Workshop | Next meeting TBD | N/A