## Large Group SAG
Illinois Energy Efficiency Stakeholder Advisory Group (SAG)
Issue Tracker
2018-2019 Large Group SAG Meetings
Tracker Updated: 6/19/19
Tracker Overview: The purpose of this document is to track open issues and follow-up from Large Group SAG meetings, including summarizing follow-up items, information requests, and action items from each meeting. This document will also include responses to open items and provide for when issues are "closed." If needed, the SAG Facilitator will follow-up to seek clarification. Issues addressed by SAG Subcommittees and SAG Working Groups will also be tracked by the SAG Facilitator. Visit the SAG website (www.ILSAG.info) to review the agenda, meeting materials and meeting notes for each meeting included in the Issue Tracker.
June 11, 2019 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Financial Resources from the Healthcare Sector | Will Klein, Green & Healthy Homes Initiative (GHHI) | 1. Please reach out to SAG Facilitator (Celia@CeliaJohnsonConsulting.com) with any additional questions on healthcare + EE or to get in touch with the Green & Healthy Homes Initiative. 2. SAG Facilitator to follow-up with utilities to check on whether there are additional questions and/or resources that would be useful on healthcare. | During 2nd quarter of 2019
Energy Efficiency and Health Project Updates | Mark Milby, ComEd | SAG will hear from ComEd in 2020 on results from two healthcare initiatives (SAG Facilitator to schedule): a. Breathe Easy Project – results anticipated Q2 2020. b. Healthy Homes Coordinated Delivery Project – results anticipated Q1 2020. | Q1 2020 and Q2 2020
May 14, 2019 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Addressing Equity, Diversity and Inclusion | Walker-Miller Energy Services; MEEA; Ameren Illinois; ComEd | SAG Facilitator will review written feedback and coordinate with Income Qualified EE Advisory Committee facilitator on suggested topics for future discussion. | During 2nd quarter of 2019
February 25, 2019 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Health and Energy Efficiency | Will Klein, Green and Healthy Homes Initiative | 1) A follow-up teleconference webinar will be scheduled for GHHI to present more information on healthcare funding sources. 2) SAG Facilitator question: Should this topic be further addressed in SAG? If so, what are you interested in discussing? Thoughts and feedback are welcomed. | 1) Schedule within the next 3 months 2) Send feedback by April 1. | Closed - the SAG follow-up call on health + EE funding is scheduled on Tuesday, June 11.
ComEd Quarterly Summary Presentation | Julie Hollensbe, ComEd | • Kristol Simms, Ameren IL Q: How does ComEd’s public housing program differ from what DCEO offered? o Julie Hollensbe will follow-up with Molly Lunn. |  | Closed
ComEd Research and Development Initiatives Presentation | Mark Milby, ComEd | 1) A ComEd webinar within the next month will provide additional information on selected initiatives; SAG Facilitator to distribute information to SAG. 2) ComEd is interested in presenting more information about their unique partnership with the National Renewable Energy Lab at a future SAG meeting. SAG Facilitator to add to the tracking list for consideration.
Ameren Illinois 3rd Party Programs | Kristol Simms, Ameren Illinois | Q from PowerTakeoff: Interested in feedback on response to RFP, is that an option? Ameren IL will check with Cadmus and their procurement teams on what can be provided.
January 14, 2019 Large Group SAG Teleconference Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open / Closed / Postponed
Overview of 2019 SAG Plan | Celia Johnson, SAG Facilitator | 1) Comments on the final draft 2019 SAG Plan are due by COB on Monday, January 28. If SAG participants have proposed edits, please submit them in redline directly to Celia: Celia@CeliaJohnsonConsulting.com. 2) If you are interested in joining the new Market Transformation Savings Working Group, please reach out directly to Celia by COB on Thursday, January 31: Celia@CeliaJohnsonConsulting.com. | 1) 1/28/2019 2) 1/31/2019 | Final 2019 SAG Plan posted on the website and circulated to the SAG Steering Committee on 1/31/2019. Market Transformation Savings Working Group participants will be accepted on a rolling basis.
Oveview of draft ComEd EUL Research Report, Phase 1 | Karen Maoz, Navigant | Comments on the draft report are due by COB on Friday, January 25. Send comments to Karen Maoz (karen.maoz@Navigant.com) and Jennifer Morris, ICC Staff (Jennifer.Morris@illinois.gov). If SAG participants are interested in a follow-up discussion about this EUL research, please let Karen Maoz know when submitting comments on the draft report. | 2019-01-25 | Closed
December 3-4, 2018 Large Group SAG Teleconference Meetings
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Ameren Illinois Evaluator - Overview of Draft EM&V Work Plan for 2019 | Zach Ross, Opinion Dynamics | 1. Business Behavior Modification Pilot: Has this program been evaluated in other jurisdictions? A: This type of program is relatively uncommon but Opinion Dynamics is looking into this. Jonathon Jackson would be happy to share more once they have information available. 2. Does the multi-family IQ initiative provide incentives for heating? Jonathon Jackson will double-check. 3. Do Community Action Agencies touch multifamily? A: No, it is primarily single family. There is a separate implementer that reaches multifamily. Opinion Dynamics will confirm. 4. Voltage Optimization: Are you considering any other approaches besides CVRf? A: VO leads are not on the phone; Opinion Dynamics will follow-up with Chris Neme, NRDC. 5. Economic and Employment Impact Study: The draft job study methodology will be presented to the SAG Non-Energy Impacts Working Group. Anticipating an end of January teleconference meeting. | TBD
ComEd Evaluator - Overview of Draft EM&V Work Plan for 2019 | Jeff Erickson, Navigant | AMI Overview: Follow-up discussion with Rob Neumann, Navigant and Rob Kelter, ELPC offline. R. Kelter is interested in how Bidgely can be used to analyze savings from various program measures. | N/A
Nicor Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Laura Agapay-Read, Navigant | No action items. | N/A
Peoples Gas & North Shore Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Kevin Grabner, Navigant | No action items. | N/A
November 7, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: Market Transformation | Stacey Paradis, MEEA; Jim Fay, ComEd; Randy Opdyke, Nicor Gas; and Christina Pagnusat, Peoples Gas & North Shore Gas | 1. ComEd is finalizing the Market Transformation Summit Report by the end of this year. The final report will be circulated to SAG. 2. There will be a utility collaborative meeting in December (Dec. 14) to further discuss MT. If you are interested in more information, contact Celia Johnson (Celia@CeliaJohnsonConsulting.com) by Friday, December 7 and she will share your contact information with the meeting organizers. | 1. End of 2018 2. Friday, Dec. 7, 2018 | Closed
Peoples Gas & North Shore Gas Quarterly Summary (Q2-Q3) | Christina Pagnusat and Omayra Garcia, Peoples Gas & North Shore Gas | Chris Neme Q: Why are only 1/3 of customers getting weatherization recs? What is the follow through on the 1/3 that do receive recs, do they actually complete the weatherization? Peoples Gas & North Shore Gas will follow-up with this information. | End of 2018
Nicor Gas Quarterly Summary (Q2-Q3) | Chris Vaughn, Nicor Gas | No action items. | N/A | N/A
Ameren Illinois Quarterly Summary (Q2-Q3) | Kristol Simms, Ameren Illinois | HEIQ program (multi-family) – 5,000 residences participated; 2,500 low income and 2,500 moderate income. Q: How many of these are multi-family? ▪ Ameren Illinois will follow-up. ▪ Ameren Illinois will confirm that 50% of the building units need to be income eligible to participate in the IQ program. | End of 2018 | Follow-up from Ameren Illinois: What was the PY2018 planned unit participation for low income? **Income Qualified Initiative – 5,000 total (2,500 low income / 2,500 moderate income) **Multifamily Initiative – 2,500 total What does AIC utilize to confirm income eligibility to participate in the Income Qualified Initiative? ** AIC utilizes https://lihtc.huduser.gov/ list to help determine if it’s a low income type MF property.
ComEd Quarterly Summary (Q2-Q3) | Julie Hollensbe and Neal Latham, ComEd | No action items. | N/A | N/A
SAG Innovative Idea Survey | Celia Johnson, SAG Facilitator | The 2019 SAG Plan is currently in development. If you have any innovative topics that should be addressed in 2019, please fill out the survey by COB on Thursday, Nov. 29: https://www.surveymonkey.com/r/8DPMTZB | Thurs., Nov. 29 | SAG Innovative Ideas will be accepted on an ongoing basis. The survey is posted on the landing page of the SAG website.
September 18, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: "Equity in Energy Efficiency" | Jim Jerozal, Nicor Gas; Kristol Simms, Ameren Illinois; Lauren Casentini, Resource Innovations | 1. Celia will review feedback to develop future action items for SAG; incorporate into the 2019 SAG Plan. 2. Celia will follow-up with Industry Spotlight presenters on next steps for this topic. | End of 2018 | Closed- several equity topics will be included in the 2019 SAG Plan.
Peoples Gas – North Shore Gas Research & Development Program | Christina Pagnusat, Peoples Gas – North Shore Gas; Allen Dusault, Franklin Energy | No action items. | N/A | N/A
ComEd LED Street Lighting Program | Bill Burns, ComEd | No action items. | N/A | N/A
ComEd Voltage Optimization Program | Dan Schick and | No action items. | N/A | N/A
July 31, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
SAG Planning Overview | Celia Johnson, SAG Facilitator | Participation in upcoming discussions: If you want to be included in the Policy Manual Subcommittee, Non-Energy Impacts Working Group, and/or Annual Template Report Working Group, please email the SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
|  | Comments on 2018 SAG Plan (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Comments on SAG Process Guidance document (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Policy Manual Subcommittee: Proposed policies are due by COB on Friday, August 31 – please complete the Proposed Policy Template. Participants are encouraged not to propose substantive changes to policies already agreed upon in the existing Policy Manual, unless there is rationale to make the change. | By COB on Friday, August 31 | Closed - Policy Manual Subcommittee kick-off meeting was held on Wed., Sept. 19.
|  | SAG Website Re-Design: If you have any web developers to suggest, please send to SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
ComEd EE Research & Development (R&D) Programs | Jim Fay, Noel Corral and Jim Lyon, ComEd | SAG Facilitator will schedule a presentation on ComEd’s baseline study in 2019. | N/A | A teleconference meeting will be scheduled in early fall 2019 for Itron to present ComEd's baseline study.
|  | • Q: Chris Neme – For C&I, to what extent are you assessing custom savings? o A: ComEd will discuss internally and follow-up. | N/A
Ameren Illinois Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Kristol Simms, Ameren Illinois | • Q: Chris Neme – What is the breakdown between multi-family and single family? o A: Ameren IL will look into this and follow-up. | N/A
ComEd Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Julie Hollensbe, ComEd | SAG Facilitator to follow-up with MEEA and ComEd on LED street lighting; this may be scheduled at SAG for future discussion. | N/A | Closed - overview of LED Street Lighting (ComEd) held during Sept. large group meeting. SAG Facilitator will follow-up with Ameren IL on whether there is interest in presenting on LED street lighting to SAG at a future meeting.
Nicor Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Chris Vaughn, Nicor Gas | No action items. | N/A
People Gas – North Shore Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Christina Pagnusat and Omayra Garcia, Peoples Gas –North Shore Gas | No action items. | N/A