## Large Group SAG
Illinois Energy Efficiency Stakeholder Advisory Group (SAG)
Issue Tracker
2018 Large Group SAG Meetings
Tracker Updated: 12/11/18
Tracker Overview: The purpose of this document is to track open issues and follow-up from Large Group SAG meetings, including summarizing follow-up items, information requests, and action items from each meeting. This document will also include responses to open items and provide for when issues are "closed." If needed, the SAG Facilitator will follow-up to seek clarification. Issues addressed by SAG Subcommittees and SAG Working Groups will also be tracked by the SAG Facilitator. Visit the SAG website (www.ILSAG.info) to review the agenda, meeting materials and meeting notes for each meeting included in the Issue Tracker.
December 3-4, 2018 Large Group SAG Teleconference Meetings
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Ameren Illinois Evaluator - Overview of Draft EM&V Work Plan for 2019 | Zach Ross, Opinion Dynamics | 1. Business Behavior Modification Pilot: Has this program been evaluated in other jurisdictions? A: This type of program is relatively uncommon but Opinion Dynamics is looking into this. Jonathon Jackson would be happy to share more once they have information available. 2. Does the multi-family IQ initiative provide incentives for heating? Jonathon Jackson will double-check. 3. Do Community Action Agencies touch multifamily? A: No, it is primarily single family. There is a separate implementer that reaches multifamily. Opinion Dynamics will confirm. 4. Voltage Optimization: Are you considering any other approaches besides CVRf? A: VO leads are not on the phone; Opinion Dynamics will follow-up with Chris Neme, NRDC. 5. Economic and Employment Impact Study: The draft job study methodology will be presented to the SAG Non-Energy Impacts Working Group. Anticipating an end of January teleconference meeting. | TBD
ComEd Evaluator - Overview of Draft EM&V Work Plan for 2019 | Jeff Erickson, Navigant | AMI Overview: Follow-up discussion with Rob Neumann, Navigant and Rob Kelter, ELPC offline. R. Kelter is interested in how Bidgely can be used to analyze savings from various program measures.
Nicor Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Laura Agapay-Read, Navigant | No action items. | N/A
Peoples Gas & North Shore Gas Evaluator - Overview of Draft EM&V Work Plan for 2019 | Kevin Grabner, Navigant | No action items. | N/A
November 7, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: Market Transformation | Stacey Paradis, MEEA; Jim Fay, ComEd; Randy Opdyke, Nicor Gas; and Christina Pagnusat, Peoples Gas & North Shore Gas | 1. ComEd is finalizing the Market Transformation Summit Report by the end of this year. The final report will be circulated to SAG. 2. There will be a utility collaborative meeting in December (Dec. 14) to further discuss MT. If you are interested in more information, contact Celia Johnson (Celia@CeliaJohnsonConsulting.com) by Friday, December 7 and she will share your contact information with the meeting organizers. | 1. End of 2018 2. Friday, Dec. 7, 2018
Peoples Gas & North Shore Gas Quarterly Summary (Q2-Q3) | Christina Pagnusat and Omayra Garcia, Peoples Gas & North Shore Gas | Chris Neme Q: Why are only 1/3 of customers getting weatherization recs? What is the follow through on the 1/3 that do receive recs, do they actually complete the weatherization? Peoples Gas & North Shore Gas will follow-up with this information. | End of 2018
Nicor Gas Quarterly Summary (Q2-Q3) | Chris Vaughn, Nicor Gas | No action items. | N/A
Ameren Illinois Quarterly Summary (Q2-Q3) | Kristol Simms, Ameren Illinois | HEIQ program (multi-family) – 5,000 residences participated; 2,500 low income and 2,500 moderate income. Q: How many of these are multi-family? ▪ Ameren Illinois will follow-up. ▪ Ameren Illinois will confirm that 50% of the building units need to be income eligible to participate in the IQ program. | End of 2018
ComEd Quarterly Summary (Q2-Q3) | Julie Hollensbe and Neal Latham, ComEd | No action items. | N/A
SAG Innovative Idea Survey | Celia Johnson, SAG Facilitator | The 2019 SAG Plan is currently in development. If you have any innovative topics that should be addressed in 2019, please fill out the survey by COB on Thursday, Nov. 29: https://www.surveymonkey.com/r/8DPMTZB | Thurs., Nov. 29 | Closed
September 18, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
Industry Spotlight: "Equity in Energy Efficiency" | Jim Jerozal, Nicor Gas; Kristol Simms, Ameren Illinois; Lauren Casentini, Resource Innovations | 1. Celia will review feedback to develop future action items for SAG; incorporate into the 2019 SAG Plan. 2. Celia will follow-up with Industry Spotlight presenters on next steps for this topic. | End of 2018 | Closed- several equity topics will be included in the 2019 SAG Plan.
Peoples Gas – North Shore Gas Research & Development Program | Christina Pagnusat, Peoples Gas – North Shore Gas; Allen Dusault, Franklin Energy | No action items. | N/A | N/A
ComEd LED Street Lighting Program | Bill Burns, ComEd | No action items. | N/A | N/A
ComEd Voltage Optimization Program | Dan Schick and | No action items. | N/A | N/A
July 31, 2018 Large Group SAG Meeting
Agenda Topic | Presenter(s) | Action Items | Due Date (if applicable) | Open/Closed
SAG Planning Overview | Celia Johnson, SAG Facilitator | Participation in upcoming discussions: If you want to be included in the Policy Manual Subcommittee, Non-Energy Impacts Working Group, and/or Annual Template Report Working Group, please email the SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
|  | Comments on 2018 SAG Plan (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Comments on SAG Process Guidance document (draft): Send comments and proposed edits directly to the SAG Facilitator. | By COB on Tuesday, August 14 | Closed
|  | Policy Manual Subcommittee: Proposed policies are due by COB on Friday, August 31 – please complete the Proposed Policy Template. Participants are encouraged not to propose substantive changes to policies already agreed upon in the existing Policy Manual, unless there is rationale to make the change. | By COB on Friday, August 31 | Closed - Policy Manual Subcommittee kick-off meeting was held on Wed., Sept. 19.
|  | SAG Website Re-Design: If you have any web developers to suggest, please send to SAG Facilitator. | By COB on Wed., Aug. 15 | Closed
ComEd EE Research & Development (R&D) Programs | Jim Fay, Noel Corral and Jim Lyon, ComEd | SAG Facilitator will schedule a presentation on ComEd’s baseline study in 2019. | N/A
|  | • Q: Chris Neme – For C&I, to what extent are you assessing custom savings? o A: ComEd will discuss internally and follow-up. | N/A
Ameren Illinois Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Kristol Simms, Ameren Illinois | • Q: Chris Neme – What is the breakdown between multi-family and single family? o A: Ameren IL will look into this and follow-up. | N/A
ComEd Quarterly Report-Out (Q1 2018); Overview of PY9 and Transition Period Results | Julie Hollensbe, ComEd | SAG Facilitator to follow-up with MEEA and ComEd on LED street lighting; this may be scheduled at SAG for future discussion. | N/A | Closed - overview of LED Street Lighting (ComEd) held during Sept. large group meeting. SAG Facilitator will follow-up with Ameren IL on whether there is interest in presenting on LED street lighting to SAG at a future meeting.
Nicor Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Chris Vaughn, Nicor Gas | No action items. | N/A
People Gas – North Shore Gas Quarterly Report-Out (Q1 2018); Overview of PY6 and Transition Period Results | Christina Pagnusat and Omayra Garcia, Peoples Gas –North Shore Gas | No action items. | N/A