## Policy Manual V2 Tracking
Policy Tracking Document
SAG Policy Manual Subcommittee Version 2.0
Updated 10/1/18
This tracking document includes the following information: 1) Policy Manual issues that have been raised to the SAG Facilitator since Version 1.0 was approved by the Commission in December 2015. 2) Policy issues that were substantive in nature, raised during the administrative Version 1.1 update process (the Version 1.1 process focused on non-substantive edits). 3) Policy issues raised by ICC Staff in the Version 1.0 docket. (Note that ICC Staff discussed internally and reconsidered several issues; updated information is included below). 4) Proposed policies submitted by various parties. 5) Notes and prioritization discussed during the Sept. 19, 2018 kick-off meeting. Version 2.0 Website: *Planning documents, agendas and initial Proposed Policy documents are available for download on the SAG website: http://www.ilsag.info/policy_manual_version_2.html *Additional edits to policy language will be circulated directly to Subcommittee participants and will not be posted on the SAG website. Policies in Bold/Italics have a corresponding Policy Template that includes additional information (posted on the SAG website).
Administrative Edits
Policy Issue | Policy Manual Section | Background | Notes/ Questions | Priority | 9/19 Meeting Notes
Introductory language / participation in Policy Manual Version 2.0 | "Acknowledgements" section | This language should be updated to reflect who participates in the Version 2.0 process. |  | Medium | Facilitator will propose edits | January 9 call
Remove references to 2017 | Section 2.4: Updates to this Policy Manual | Remove references to 2017 |  | Medium | Facilitator will propose edits | January 9 call
Fix references to IL-TRM Policy Document | TBD | References to the IL-TRM Policy Document need to be fixed to refer to Version 2.0. |  | Medium | Facilitator will propose edits | January 9 call
Review various SAG definitions | Section 3.3, Advisory Role | Review the various SAG groups (Large Group SAG, EE SAG Technical Advisory Committee, EE SAG Subcommittees) to ensure the definitions match what is in the SAG facilitator contract. Add the definition of "SAG Working Groups." |  | Medium | Facilitator will propose edits | January 9 call
Updated Policies from Version 1.1
Policy Issue | Policy Manual Section | Background | Notes/ Questions | Priority | 9/19 Meeting Notes
Change timing of draft EM&V Work Plans and review process | Section 10.1, EM&V Work Plans | Change Final EM&V Work Plan deadline from Feb. 20 to Feb. 28. Evaluators would like more time to review prior to finalizing. Change draft timing for EM&V planning, so that draft EM&V plans are available earlier (by mid-December, instead of early January) Provide SAG participants 20 business days for review, instead of 15 business days. Open questions: What happens if evaluators don't meet the final deadline of April 30? What if they don't have all program data in time, or there is an error/correction that is needed? | Source of recommendation is Vince Gutierrez, ComEd (2/13/18). Rationale is that existing deadline is practically unworkable and doesn't provide much opportunity to review revised drafts of EM&V plans before they are finalized. ICC Staff and Navigant have also shared that changes to EM&V work plan timing would be useful. | High | Jeff: Remove the open question as it could be controversial, while the first three are fairly straightforward. April 30th is statutory. Facilitator will propose edits | October meeting
Updates to Quarterly Reporting requirements | Section 6.5, Program Administrator Quarterly Reports | Quarterly Report Changes Requested: 1) Include the annual portfolio budgets, for each of the program years 2) Add a template table for historial expenditures Background for #1: Include the portfolio spending caps + budget and a comparison of the program year to date spending to the program year budget. ICC Staff receives similar requests often, and this information is difficult to track down. This information was inadvertently excluded from the Quarterly Report Template. Background for #2: This is included in the Quarterly Report Template instructions as a request from ICC Staff, but the information has not been provided to date. This is already required for the Annual Report. | ICC Staff request Nicor Gas comment: Any requested changes to the template should be discussed in the Quarterly Report Template small group, if necessary. Changes to Policy Manual language are not needed. | High | ICC and IL AG think this is important for transparency. Concerns were raised by other parties. Follow-up discussion in Quarterly Report Template Working Group; preference to reach agreement on the Template instead of changing Policy Manual language. | Discuss in quarterly report template working group
Updates to Annual Reporting requirements | Section 6.6, Program Administrator Annual Summary of Activities (Annual Report) | To create a template for upcoming annual reporting for Illinois utilities, stakeholders will have to make sure that the template includes the information required by section 6 of the Policy Manual. It is prudent, therefore to consider whether the requirements that are listed in the Policy Manual are sufficiently detailed to provide the underlying data necessary to assess and understand the program performance. For reasons outlined in the Proposed Resolution and Background Research section, the addition of a small number of additional data points (which are values that are already being calculated but not reported) to the annual report requirements would – between the annual and quarterly reports – bring Illinois’ reporting up to a level that would enhance the ability of researchers, analysts, and policymakers to fully understand the program impacts in Illinois and to be able to compare Illinois utilities’ performance intra-state and against regional peers. | Proposed by MEEA. See Proposed Policy on SAG website. | High | Chris Vaughn: Suggestion to use the Quarterly Report Template for the Annual Report and add the remaining required items from the Policy Manual Annual Report list. Follow-up discussion will be held in Annual Report Working Group. Also schedule this topic at the Oct. Policy Manual meeting. | October meeting
Net-to-Gross Policy | Section 7.2, Net-to-Gross Policy | The current net-to-gross policy creates unnecessary uncertainty associated with changes in net-to-gross (NTG) values. NTG values fluctuate over time, driven primarily by external market factors and inability of evaluators to precisely measure actual NTG values. Utilities have little control of NTG results however utilities bear all the risks associated with changing NTG values. Other states have implemented a range of policies that address these unreasonable risks, while continuing to allow ongoing measurement of NTG values. These options are outlined in the “Background Research” section of this Policy Template, and include: • Measuring savings performance using gross savings. • Deeming NTG ratios for entire portfolios at 1.0. • Deeming NTG ratios for entire portfolios at values below 1.0. • Providing a multi-year lock on prospective NTG values within plan cycles. While not implemented in other states, an additional option available in Illinois is to include changes in NTG in Adjustable Savings Goals calculations. This approach provides all of the risk protection associated with the four options used in other states, without some of their negative consequences; it is the approach recommended by Nicor Gas. Note that Nicor Gas is not recommending that evaluators stop performing NTG research in Illinois. Under the Nicor Gas proposal, NTG research would continue to occur at frequencies deemed appropriate by evaluators, with input from utilities and stakeholders. While utility savings goals will adjust to mitigate NTG risk, utilities will continue to report net savings based on updated NTG values. Utilities, with input from evaluators and stakeholders, could also use NTG research to adjust program design—if warranted or possible—that improve NTG results and program performance. | Proposed by Nicor Gas. See Proposed Policy on SAG website, including a NTG Memo with additional information. | High | Nicor Gas already drafted language for review. | November meeting
Modify the definition of "Incentives" | Section 8.4, TRC Costs | The definition of "incentives" needs to be modified to include health and safety (specificially Incentives paid to Customers) See the definition of "Financial Incentives Paid to Customers" and "Incentives Paid to Third Parties" in Section 8.4 of the Policy Manual. | Issue raised during Policy Manual Version 1.1. If the definition of "incentives" is modified, the definition of "incremental costs" may also need to be modified to include health and safety. Several parties have shared that this change may not be needed. | Low | Participants agreed to put as "low priority" so this issue doesn't get lost in case a definition change is needed.
New Policies
Policy Issue | Policy Manual Section | Background | Notes/ Questions | Priority | 9/19 Meeting Notes
Income Qualified EE Programs
Statewide Policy on Low Income Programs | TBD | The northern utilities and certain stakeholders came to stipulated agreements on a variety of policy issues in their respective EE Plan dockets for the time period of 2018-2021. These stipulated agreements did not include Ameren Illinois though many of the policy issues affect AIC and its Plan implementation. AIC would like to set up a structure going forward on how to address these inconsistencies in a fair and productive manner. | Proposed by Ameren Illinois. See Proposed Policy on SAG website. | High | Ameren IL will review the Policy Manual and propose edits; will also propose a new section specific to low income programs. Jim: Ensure there is also alignment with metrics. | January meeting
Low income savings attribution for IHWAP program | TBD | There was an initial SAG discussion of low income savings attribution for the IHWAP program. Following the SAG meeting, interested parties have been discussing consensus language to address this issue. Utilities (Ameren IL, ComEd, Nicor Gas, Peoples Gas & North Shore Gas) and non-financially interested stakeholders (IL AG, ICC Staff, NRDC, and CUB) are close to reaching agreement. | Issue raised by several participants Final agreement language is in development. | High | Concern was raised about the language specifying Ameren IL since policies should be statewide; participants agreed that this policy should be included in the Manual. Agreement language is close to being finalized. Jennifer Moore (Ameren IL) will follow-up. | January meeting
Add a definition of "Income Qualified EE Advisory Committee" | Section 1: Glossary | Add a definition of the Income Qualified EE Advisory Committee, and a reference to the statutory requirement. | Would it be helpful to also define the Income Qualified Working Group, which addresses technical and/or policy issues that are more appropriate for SAG discussion? | Medium | This may be needed if there are references to the Policy Manual added related to low income - Ameren IL will propose (see row 26). | January meeting (if needed)
Additional Reporting (for Income Qualified, Public Sector and Diversity) | Section 6: Program Administration and Reporting | Add language to the Policy Manual regarding income qualified program reporting: • Statutory requirements – “develop and implement reporting procedures that address and assist in determining the amount of energy savings that can be applied to the low-income procurement and expenditure requirements set forth in this subsection (c).” • Review - sector-specific reporting requirements in the revised Policy Manual." | Holdover issue from Version 1.1. What type of reporting needs to be added? Nicor Gas comment: This is premature; metrics should be discussed/agreed upon in the IQ Committees. IQ program updates are already included in the Quarterly Report Template. IL AG: This reporting is not needed in the Policy Manual at this time. | Low | Participants agreed we should be thoughtful about how we develop metrics; it may not be needed at this time; this may be a topic for the IQ Advisory Committees.
Policies Related to FEJA
Add policies related to FEJA | TBD - new section on FEJA? | Add a number of additional provisions necessary to address other key aspects of these statutory changes that were not part of past versions of the Manual. Examples of policies that may need to be addressed: 1) Societal discount rate 2) Measure life fixed at time of implementation 3) Tracking persistent savings (electric EE programs) 4a) How to perform CPAS calculations for measures with measure lives that are not whole numbers (including measures with baseline shifts). For example, if a measure had a 5.5 year measure life, should the program count the full first year savings for 5 years and in the last year count half of the first year savings? 4b) Overall question: How should CPAS compliance be calculated? How to calculate CPAS is in an Excel file in the Quarterly Report Template. 5) Definition of Applicable Annual Incremental Goal (this is in the statute) 6) Cap on gas savings that can be counted in MWh equivalents, towards the Applicable Annual Incremental Goal (and the priorization of low income gas savings) 7) Calculation of the annual spending caps -Spending caps are statutory, but the methodology is not (how to define the 'average residential retail rate'? Currently the utilities are using the same definition.) 8) Whether the performance incentive should be included in the TRC as a cost. -The National Standard Practice Manual includes this as a cost. There may need to be edits to the definition of "Non-Incentive Costs" and "Portfolio Costs." | #s 1-3 were raised during Version 1.1 discussions #4a raised by Andy Vaughn, Ameren IL #4b, #5, #6 and #7 raised by Chris Neme, representing NRDC #8 raised by ICC Staff Open question: Are there any additional issues related to FEJA that need to be included in Version 2.0? The SAG Facilitator is preparing background information / excerpted statutory language for this list of 8 issues. | #s 1, 2, 3, 4, 5, and 7 are high priority Remove #6 #8 low priority | Societal discount rate is in the IL-TRM; 10 year t-bill. This should be memorialized. Gas section says "discounted cost" i.e. FEJA is silent; proposal is to document that gas should be same as electric. #3 and 4 should be combined. Navigant drafted a memo on this - Randy Gunn will follow-up. Definition of Applicable Annual Incremental Goal: expand how the calculation is converted (which is not in FEJA) . Keep CHP in mind as an exception. Chris Neme (rep. NRDC) will draft policy language for #s 1, 2, 3, 4, 5 and 7 | November meeting
Weighted Average Measure Life calculation methodology | Section 4: Program and Portfolio Planning | Document the WAML methodology agreed to as part of the SAG WAML discussions in November 2017. | See final SAG WAML Report for policy language - Feb. 14, 2018. Available on SAG website: http://www.ilsag.info/sag-reports.html | High | Jennifer: Do gas savings need to be acounted for or not?, This is a nuance that we might want to clarify. Jennifer Morris (ICC Staff) will draft language | October meeting
Adjustable Goals for Weighted Average Measure Lives | TBD | The Settlement Agreements signed by Illinois utilities and stakeholders in 2018-21 Plan Approval dockets defined minimum weighted average measure life (WAML) values. These provisions ensured that utilities continue to emphasize lifecycle savings as they exercised Policy Manual provisions that allow flexibility in shifting budgets among programs. Many of the measure lives used to set WAML values in the settlement agreements have since been updated based on secondary research by Navigant. These changes affect WAML values even when utilities do not shift budgets from approved Plan budgets. It is inconsistent with the intents of the settlement agreements for utilities to manage changes to WAML values that do not result from budget shifts. Note that these changes in measures lives can both increase or decrease WAML. | Proposed by Nicor Gas. See Proposed Policy on SAG website. | High | Another option proposed at the meeting is to work on a separate stipulation for this issue since this needs to be addressed in 2018 (for Nicor, Peoples & North Shore) Mechanial edits may be needed to the Adjustable Savings Goal Template
Policies Raised in Stipulated Agreements Between Non-Financially Interested Stakeholders and ComEd, Nicor Gas, Peoples Gas & North Shore Gas
IL-TRM Administrator authority | Section 7.1, Technical Reference Manual | To agree on a policy regarding IL-TRM Administrator authority, to the extent consensus cannot be reached on a measure or measure values in the TRM. | ICC Staff: This may need to be added to the IL-TRM Policy Document. | High | Karen Lusson (IL AG) will draft language | October meeting
Vendor participation in IL-TRM | Section 7.1, Technical Reference Manual | Develop a policy for vendor participation in IL-TRM meetings. Policy language agreed to in March 2018: A conflict of interest is present when a Product Representative, in the judgment of the IL-TRM Administrator, has a financial stake in a discussion topic and participation by the Product Representative could have adverse consequences, such as hindering complete and frank discussions. To prevent conflicts of interest, financially-interested Product Representatives will not participate in the IL-TRM Version 7.0 measure selection, IL-TRM Technical Advisory Committee (TAC) meetings or the consensus process, unless invited to participate in the IL-TRM TAC of the SAG by the IL-TRM Administrator. The IL-TRM Administrator will honor reasonable requests from utilities to invite Product Representatives to present factual information or to answer questions on a specific measure under discussion for inclusion in the annual TRM update. “Product Representatives” means a financially-interested party or parties that works for or on behalf of a company that sells a product that is or may be included as a measure in the IL-TRM. | This policy was already discussed/agreed upon by interested parties in March 2018. | High | Jennifer (ICC Staff): The version number needs to be removed from this policy. Karen Lusson (IL AG) will review and draft language edits. | October meeting
Independence (IL-TRM Administrator; Evaluators; SAG Facilitator) | TBD | Document the policy for IL-TRM Administrator, evaluator and SAG Facilitator independence. | ICC Staff: IL-TRM Administrator independence may need to be added to the IL-TRM Policy Document. ICC Staff comment: Currently evaluator independence is addressed in each utility's individual EE Plan dockets. It would be more efficient to include agreed-upon language in the Policy Manual. | High | Three independence policies were combined into one Policy Manual topic. Jennifer Morris (ICC Staff) will draft language. | October meeting
Consistent contract requirements | TBD | Develop consistent contract requirements within the Policy Manual Subcommittee that ensure Evaluation, Measurement & Verification (“EM&V”) evaluator independence, SAG Facilitator independence, and IL-TRM Administrator independence. | This is a Nicor Gas stipulation | High | Jennifer Morris (ICC Staff) will draft language. | October meeting
Public availability of evaluator contracts | Section 7: Evaluation Policies | Reach agreement on whether the contract(s) and scope of work for independent evaluators may be made public in whole or in part. | This is a ComEd stipulation | Low | Jennifer Morris: For some utilities the contracts are filed publicly but others redact all of the info, this needs a discussion before an actual policy can be developed.
Other Policy Issues
Jobs Reporting | TBD | Utilities should estimate and report on jobs created through their efficiency programs. The reports should be annual, at the portfolio level, and account for direct, indirect and induced jobs created. The estimates should be provided by the utilities evaluators based on a common statewide method agreed to by the utilities’ evaluators with input from the SAG. | Proposed by NRDC. See Proposed Policy on SAG website. | High | Chris Neme (representing NRDC) will draft general policy Ameren IL and ComEd evaluators are working on research for NEBs in 2018 that includes jobs We need an accepted methodology; it may be appropriate to hire an outside firm to do this work in the future. | October meeting
Diverse EE Workforce (Workforce Development) | TBD | Statewide policy on energy efficiency’s role in developing, supporting and growing a diverse energy efficiency workforce while still meeting savings goals and other Commission-approved plan objectives. | Proposed by Ameren Illinois. See Proposed Policy on SAG website. | High | Kristol Simms: This should be included to affirmatively state this is a policy for IL: we should increase jobs for diverse communities. Both aspirational and metrics based. Ameren IL will draft language | January meeting
Stipulation Inconsistencies | TBD | The northern utilities and certain stakeholders came to stipulated agreements on a variety of policy issues in their respective EE Plan dockets for the time period of 2018-2021. These stipulated agreements did not include Ameren Illinois though many of the policy issues affect AIC and its Plan implementation. AIC would like to set up a structure going forward on how to address these inconsistencies in a fair and productive manner. | Proposed by Ameren Illinois. See Proposed Policy on SAG website. | High | Kristol Simms: There should be a process if a policy does not apply to all utilities due to a stipulation; and how stipulations are dealt with if there is not unanimous agreement Ameren IL will draft language | January meeting
IL-TRM Policy Issues | Section 3: IL EE SAG | The IL-TRM Administrator requested SAG discussion of several policy issues, which was held by teleconference in June 2018. Proposed policies are still in discussion and may need to be included in the Policy Manual: 1. Secondary Electricity Savings from Reduced Water Use: A “kWh per million-gallon” factor should be used to calculate secondary electricity savings from reduced water use. Specific details on the factor to be used and which measures it will apply to will be addressed by the TAC in the IL-TRM Version 7.0 process. Note - this does not need to be included in the Policy Manual, it is included in the IL-TRM on an individual measure basis. 2. Custom Measures: For custom measures, the existing baseline could be used in savings calculations at the discretion of program administrators (for example, if the existing condition is not compliant with code and there is data to back that up, the existing condition can be used). 3. Prescriptive Measures: For prescriptive measures, code level will be assumed to be the baseline. Any adjustment should be made in the NTG ratio, not in TRM savings calculations. 4. NTG Working Group Follow-Up: The NTG Working Group will review how to make adjustments to NTG ratios for the below code baseline scenarios, for both prescriptive and custom measures. 5. Seeking SAG Approval: When a situation arises in the IL-TRM TAC where an efficient condition doesn’t meet code, the IL-TRM Administrator will seek SAG approval on a case by case basis before approving the measure. 6. Memorializing Policy Agreements: Policies should be included in either Policy Manual Version 2.0 or an updated version of the IL-TRM Policy Document. The SAG Facilitator will add this policy topic to tracking list. | TBD; a follow-up SAG call is anticipated in September | High | On 9/26/18 SAG call the suggestion was made to discuss this in the Policy Manual Subcommittee, to be added to the IL-TRM Policy Document. Facilitator will circulate edits for review. | November meeting
Federal standard changes and the IL-TRM | TBD | Do federal standard changes constitute an "errata" for the IL-TRM? For example, changes to lighting standards. | Raised by ICC Staff ICC Staff comment: This may need to be added to the IL-TRM Policy Document (to modify the definition of 'errata') | Low | Participants do not think a policy is needed at this time; this is the only measure wherethe federal standard will cause a baseline shift.
Ensure EM&V expenditures are prudent, minimize costs associated with EM&V, and allow for a more diverse set of evaluation professionals to perform EM&V work. | TBD | 1. SAG (and IQ committees, if relates to income qualified portfolios) should review not only each annual evaluation plan, but also the budget the evaluators propose for the evaluation. SAG and IQ committee members should be permitted to ask questions about budget line items to ensure evaluators are being prudent. 2. The SAG should be able to recommend whether individual studies should be performed by the designed evaluation contractor, or should be bid out to give smaller and diverse businesses the opportunity to bid. 3. SAG should carefully evaluate the level of proposed annual expenditures on EM&V to ensure that whatever levels are necessary and appropriate to determine savings and portfolio cost-effectiveness. The assumption should not be that the full budget annual EM&V budget will be spent. EM&V funds that are not spent should be returned to the portfolios and spent on program activity. | Anonymous policy propsal | Low | Evaluators have no objection to discussing budgets. Facilitator followed up with the party that proposed it - this policy has been withdrawn.
Policy Manual Version 1.0 Docket
Prohibited Expenses (Inducements) | Section 5.4 Inducements | ICC Staff proposes to change the name of Section 5.4 Inducements to Section 5.4 Prohibited Expenses and to modify the language of the section to make it clear that the section is not related to the tracking and reporting of “inducements” as a cost category, rather the purpose of the section is to specify certain prohibited expenses that shall not be recoverable from ratepayers. In addition, ICC Staff proposes expanding the list of prohibited expenses to include complimentary or discounted tickets to entertainment events, marketing of the utility name without direct connection to energy efficiency programs, incentive compensation unrelated to energy efficiency, and incentive compensation tied to financial metrics. This policy requires inclusion in Policy Manual Version 2.0 in order to provide greater clarity and certainty for utilities as to certain specific expenses that are not recoverable from ratepayers. In addition, this policy is intended to reduce litigation before the Commission because the utilities will know in advance certain categories of expenses that they should not fund with ratepayer money. | Proposed by ICC Staff. See Proposed Policy on SAG website. | High | Concerns were raised by various parties. IL AG supports this policy. This is the topic of an open ICC docket, so Facilitator will wait to schedule until the docket is closed. Jennifer Morris (ICC Staff) already drafted policy language. | January (assuming docket is closed)
Adjustable Savings Goals, fixing measure participation levels (ICC Staff request) | Section 6.2, Adjustable Savings Goals | Clarify that the measure participation levels are fixed in the adjustable savings goal calculation. For purposes of the Section 8-104 Programs Adjustable Savings Goals policy approved in the Illinois Energy Efficiency Policy Manual Version 1.1, the energy efficiency measure participation levels identified in the approved Plan to derive the energy savings goals shall be fixed for the entirety of the Plan, in the adjustable savings goal calculation, where adjustments are applied. | Issued raised in Version 1.0 docket. | High | Jennifer Morris (ICC Staff) will draft language. | January 9 call
Updated definition of "Incremental Costs" (ICC Staff request) | Section 8.4, TRC Costs | Staff raises several concerns regarding Section 8.4, TRC Costs, and provides significant edits to the Section for Commission review and approval. ICC Staff recently reviewed this issue, and would like to discuss one change - ICC Staff recommends that additional detail be added to the Policy Manual to further define incremental costs. | Issued raised in Version 1.0 docket. | High | Jennifer Morris (ICC Staff) will draft language. | November meeting
Breakthrough Equipment and Devices - Program Administrator "determines" language (ICC Staff request) | Section 1: Glossary | Staff requests that the Commission revise the Policy Manual by removing the phrase “the Program Administrator determines” from the definition of “Breakthrough Equipment and Devices” to clarify that Program Administrators do not have the unilateral right to make final determinations as to which technologies, measures, projects, programs, and/or services are covered by the definition. ICC Staff is open to adding clarifying language at the end of this definition - such as "if there is a dispute the Commission has the authority to decide." | Issued raised in Version 1.0 docket. | Medium | Jennifer Morris (ICC Staff) and Karen Lusson (IL AG) will draft language. | January 9 call
Requiring SAG Facilitator compliance with the Policy Manual | Section 3.4, Facilitation | Staff states that it is concerned that "the SAG provisions contained in the Policy Manual may not actually take place, due to the fact that SAG is not an entity regulated by the Commission.” Staff Initial Comments at 18. Staff seeks changes to the Policy Manual imposing requirements on the utilities to include requirements in their contracts with the SAG Facilitator to require compliance with the Policy Manual directives. | Issued raised in Version 1.0 docket. ICC Staff comment: The current SAG Facilitator contract effectively already incorporates this requirement, so this should not be a contested issue. | Low
Filing final deemed NTG values in dockets (ICC Staff request) | Section 7.2, Net-to-Gross Policy | Finally, Staff further requests that the Commission direct the utilities to file the final deemed NTG ratios within 14 days of receipt of the final deemed ratios from the evaluators to "ensure clarity and minimize potential for future litigation." Id. at 34. | Issued raised in Version 1.0 docket. | Low