## Tracker (hidden)
IL-TRM V13.0 - DRAFT Measure Update Priority List
VEIC - March 22nd, 2024 |  |  | Items grayed out have been deprioritized for v.12.0 update.
Sorted by Type (Existing then New measures) and then Measure Code/Section
| Request Summary | Request Type | Existing Measure Name | Measure Section (for new measures only) | Requester Name | Requester Company | Work Paper Deadline | Work Paper Completed | Status | Priority | Assigned To | Created | Change Type | Revision Completed | Existing Measure Code | Modified | Modified By | Item Type | Path | Notes | Column1
Exist | EUL assumptions for IQ populations | Change to existing measure |  |  | IQ Working Group |  |  | FALSE | Open | (2) Medium |  | 2024-03-21 05:17 |  | FALSE |  | 2024-03-21 05:17 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
Exist | Update Dehumidifier ENERGY STAR market conditions and consider adding whole-home | Change to existing measure |  |  | Seth Craigo-Snell | SCS ANALYTICS in support of Ameren Illinois |  | FALSE | Open | (2) Medium |  | 2024-03-20 23:11 |  | FALSE | 5.1.3 RES ENERGY STAR Dehumidifier | 2024-03-20 23:11 | Seth Craigo-Snell | Item | sites/illinoistrm/Lists/RequestTracker |  | Duplicate
Exist | Update Air Purifier for ENERGY STAR market conditions and DOE Conservation Standard | Change to existing measure |  |  | Seth Craigo-Snell | SCS ANALYTICS in support of Ameren Illinois |  | FALSE | Open | (1) High |  | 2024-03-20 22:42 |  | FALSE | 5.1.1 RES ENERGY STAR Air Purifier/Cleaner | 2024-03-20 23:06 | Seth Craigo-Snell | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Multifmaily Common Use Spaces | Question/Clarification |  |  | Sara Castleberry | RI |  | FALSE | Open | (2) Medium |  | 2024-03-20 17:49 |  | FALSE |  | 2024-03-20 17:49 | Sara Castleberry | Item | sites/illinoistrm/Lists/RequestTracker
New | Thermal Energy Storage System | New measure request |  | 4.4 C&I HVAC End Use | Alex Smillie | Trane |  | FALSE | Open | (2) Medium |  | 2024-03-20 16:26 |  | FALSE |  | 2024-03-20 17:06 | Alex Smillie | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Heat Pump Market Adder | Change to existing measure |  |  | Josh Sharon / Richard Tonielli | ComEd |  | FALSE | Open | (2) Medium |  | 2024-03-20 16:42 |  | FALSE |  | 2024-03-20 16:42 | Josh Sharon | Item | sites/illinoistrm/Lists/RequestTracker | Policy/Volume 4
Exist | Commercial Chillers | Change to existing measure |  |  | Josh Sharon | ComEd |  | FALSE | Open | (2) Medium |  | 2024-03-20 14:24 |  | FALSE |  | 2024-03-20 14:24 | Josh Sharon | Item | sites/illinoistrm/Lists/RequestTracker | Policy/Volume 4
Exist | Residential Heat Pump | Change to existing measure |  | 5.3 Residential HVAC End Use | Josh Sharon | ComEd |  | FALSE | Open | (2) Medium |  | 2024-03-20 14:15 |  | FALSE |  | 2024-03-20 14:15 | Josh Sharon | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
Exist | Commercial Heat Pumps | Change to existing measure |  |  | Josh Sharon | ComEd |  | FALSE | Open | (2) Medium |  | 2024-03-20 14:13 |  | FALSE | 4.4 C&I HVAC End Use | 2024-03-20 14:13 | Josh Sharon | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump | Duplicate
New | Commercial Water Heater Timer | New measure request |  | 4.3 C&I Hot Water | Wade Morehead | Morehead Energy on behalf of Ameren IL |  | FALSE | Open | (3) Low |  | 2024-03-20 14:09 |  | FALSE |  | 2024-03-20 14:09 | Wade Morehead | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Clarify efficiency calculation for commercial boilers and furnaces | Question/Clarification |  |  | Wade Morehead | Morehead Energy on behalf of Ameren IL |  | FALSE | Open | (2) Medium |  | 2024-03-20 14:00 |  | FALSE | 4.4.10 C&I High Efficiency Boiler | 2024-03-20 14:00 | Wade Morehead | Item | sites/illinoistrm/Lists/RequestTracker | Input/output issue
Exist | Update Heat Pump measure for simultaneous operation | Change to existing measure |  |  | Wade Morehead | Morehead Energy on behalf of Ameren IL |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:57 |  | FALSE | 5.3.1 RES Air Source Heat Pump | 2024-03-20 13:57 | Wade Morehead | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
Exist | 5.6.8 High Performance Windows Update | Change to existing measure |  |  | Randy Opdyke/Brady Nemeth | Nicor Gas/Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:46 |  | FALSE | 5.6.8 Triple Pane and Thin Triple Windows | 2024-03-20 13:46 | Randy Opdyke | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Residential TRM Incremental Cost Data Assumption Review and update - Residential HVAC (Gas and Electric) End Uses Space heating, Water Heating and cooking | Change to existing measure |  |  | Randy Opdyke | Nicor Gas |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:42 |  | FALSE | 5.3 RES HVAC End Use | 2024-03-20 13:42 | Randy Opdyke | Item | sites/illinoistrm/Lists/RequestTracker
Exist | ENERGY STAR Clothes Dryer | Change to existing measure |  |  | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:36 |  | FALSE | 5.1 RES Appliances End Use | 2024-03-20 13:36 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker | ESTAR Spec change in development
Exist | ENERGY STAR Dehumidifiers | Change to existing measure |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:31 |  | FALSE |  | 2024-03-20 13:31 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker | ESTAR Spec change in development | Duplicate
Exist | ENERGY STAR Pool Pumps | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:25 |  | FALSE |  | 2024-03-20 13:25 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker | Existing measure 5.7.1
New | All-in-one Washer/Electric Dryer | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:23 |  | FALSE |  | 2024-03-20 13:25 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker |  | Combine
New | All-in-One Washer/Heat Pump Dryer | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:24 |  | FALSE |  | 2024-03-20 13:24 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker |  | Combine
New | Laundry Center | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:22 |  | FALSE |  | 2024-03-20 13:22 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker |  | Combine
New | Jobsite fans | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:18 |  | FALSE |  | 2024-03-20 13:18 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker
New | Cordless pruners | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:18 |  | FALSE |  | 2024-03-20 13:18 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker
New | Pruning chainsaws | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:17 |  | FALSE |  | 2024-03-20 13:17 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker
New | Lithium-ion circular saws | New measure request |  | 5.1 Residential Appliances End Use | Bobbi Fey | ICF |  | FALSE | Open | (2) Medium |  | 2024-03-20 13:17 |  | FALSE |  | 2024-03-20 13:17 | Bobbi Fey | Item | sites/illinoistrm/Lists/RequestTracker
New | Computer Room Air Conditioner (CRAC) | New measure request |  | 4.4 C&I HVAC End Use | Sri Paruchuri | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:53 |  | FALSE |  | 2024-03-20 12:57 | Sanjyot Varade | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Data Center Efficient UPS/(Uninterruptible Power Supply) | New measure request |  | 4.7 C&I Miscellaneous End Use | Sri Paruchuri | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:53 |  | FALSE |  | 2024-03-20 12:57 | Sanjyot Varade | Item | sites/illinoistrm/Lists/RequestTracker | Existing measure 4.8.18?
Exist | Electric Chillers (IL TRM v12, 4.4.6) | Change to existing measure |  |  | Sri Paruchuri | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:56 |  | FALSE | 4.4.6 C&I Electric Chiller | 2024-03-20 12:56 | Sanjyot Varade | Item | sites/illinoistrm/Lists/RequestTracker
New | Elevator Modernization | New measure request |  | 4.7 C&I Miscellaneous End Use | Sri Paruchuri | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:52 |  | FALSE |  | 2024-03-20 12:52 | Sanjyot Varade | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Possibly merge 5.1.7 and 5.1.13 for Room AC | Question/Clarification |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:43 |  | FALSE | 5.1.7 ENERGY STAR Room Air Conditioner | 2024-03-20 12:43 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
New | Add Measure for Auto Diverting Tub Spout System | New measure request |  | 5.4 Residential Hot Water End Use | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:31 |  | FALSE |  | 2024-03-20 12:31 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
Exist | DHW Boiler Tune-up - Additional HW Gal/Year Option | Change to existing measure |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 11:33 |  | FALSE | 4.3.10 DHW Boiler Tune-up | 2024-03-20 12:17 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
Exist | High Speed Clothes Washers - Additional Options | Change to existing measure |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 11:45 |  | FALSE | 4.8.5 High Speed Clothes Washer | 2024-03-20 12:17 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
New | Add Measure for Residential Duct Insulation | New measure request |  | 5.3 Residential HVAC End Use | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 11:55 |  | FALSE |  | 2024-03-20 12:16 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
New | Add Measure for Steam Leak Fix-it-Now | New measure request |  | 4.7 C&I Miscellaneous End Use | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 12:08 |  | FALSE |  | 2024-03-20 12:08 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Room AC Covers - Algorithm Modification for Number of Floors | Change to existing measure |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-20 11:29 |  | FALSE | 4.4.38 Covers and Gap Sealers for Room Air Conditioners | 2024-03-20 11:29 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
New | Door Gaskets for Walk-in and Reach-in Coolers and Freezers | New measure request |  | 4.6 C&I Refrigeration End Use | Sanjyot Varade | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-20 09:19 |  | FALSE |  | 2024-03-20 09:19 | Sanjyot Varade | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Correction to Commercial Steam Cooker calculations | Change to existing measure |  |  | Tyler Sellner | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:33 |  | FALSE | 4.2.3 C&I Commercial Steam Cooker | 2024-03-19 16:33 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker | Errata
Exist | Update HVAC Tune-up Measure | Change to existing measure |  |  | Zach Ross | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:31 |  | FALSE | 5.3.10 RES HVAC Tune Up (Central Air Conditioning | 2024-03-19 16:31 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
Exist | Identify availability of data to update Food Service assumptions | Change to existing measure |  |  | Jessica Raker | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:29 |  | FALSE |  | 2024-03-19 16:29 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Define DI installation guidelines | Change to existing measure |  |  | Jessica Raker | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:27 |  | FALSE |  | 2024-03-19 16:27 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Add Calculation examples to more measures | Change to existing measure |  |  | Jessica Raker | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:26 |  | FALSE |  | 2024-03-19 16:26 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Correct Commercial Steam Cooker Demand /CF | Correction of TRM mistake |  |  | Tyler Sellner | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:25 |  | FALSE | 4.2.3 C&I Commercial Steam Cooker | 2024-03-19 16:25 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Clarify treatment of zone-specific Residential Heat Pumps | Change to existing measure |  |  | Jessica Raker | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:23 |  | FALSE | 5.3.1 RES Air Source Heat Pump | 2024-03-19 16:23 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
Exist | Update to ISR For Self-install Smart Thermostats with no verification | Change to existing measure |  |  | Sam Lamos | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:21 |  | FALSE | 5.3.16 Advanced Thermostats | 2024-03-19 16:21 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Update Showerhead GPM Low Table | Change to existing measure |  |  | Alex Caratti | Opinion Dynamics |  | FALSE | Open | (2) Medium |  | 2024-03-19 16:18 |  | FALSE | 5.4.5 RES Low Flow Showerheads | 2024-03-19 16:18 | Jessica Raker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | CAC for Mobile Homes | Change to existing measure |  |  | David Kilgore | Leidos on behalf of Ameren Illinois |  | FALSE | Open | (2) Medium |  | 2024-03-19 12:28 |  | FALSE | 5.3.3 RES Central Air Conditioning > 14.5 SEER | 2024-03-19 12:28 | David Kilgore | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
New | Residential Electric Water Heater | New measure request |  |  | Courtney Golino & Ridhi Kalra | Guidehouse |  | FALSE | Open | (2) Medium |  | 2024-03-19 07:21 |  | FALSE |  | 2024-03-19 07:21 | Courtney Golino | Item | sites/illinoistrm/Lists/RequestTracker
New | Portable Heat Pumps | New measure request |  | 5.1 Residential Appliances End Use | Andy Vaughn | Leidos on behalf of Ameren Illinois |  | FALSE | Open | (2) Medium |  | 2024-03-18 23:20 |  | FALSE |  | 2024-03-18 23:20 | Andrew Vaughn | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
Exist | Radon Mitigation - Energy Star fans | Change to existing measure |  |  | David Kilgore | Leidos on behalf of Ameren Illinois |  | FALSE | Open | (2) Medium |  | 2024-03-18 17:08 |  | FALSE | 5.3.9 RES High Efficiency Bathroom Exhaust Fan | 2024-03-18 17:09 | David Kilgore | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
Exist | HVAC Tune-Up Measure Adjust | Change to existing measure |  |  | David Kilgore | Leidos on behalf of Ameren Illinois |  | FALSE | Open | (2) Medium |  | 2024-03-15 15:04 |  | FALSE | 5.3 RES HVAC End Use | 2024-03-15 15:04 | Andrew Vaughn | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
New | (4.8.New) Commercial Secondary Windows | New measure request |  | 4.7 C&I Miscellaneous End Use | Randy Opdyke/Ramanathan Dharmarajan | Nicor Gas/GTI Energy | 2024-05-15 | FALSE | Open | (2) Medium |  | 2024-03-15 09:18 |  | FALSE |  | 2024-03-15 09:26 | Randy Opdyke | Item | sites/illinoistrm/Lists/RequestTracker
New | Efficient Rooftop Unit | New measure request |  | 4.4 C&I HVAC End Use | Randy Opdyke | Nicor Gas/Resource Innovations | 2024-05-15 | FALSE | Open | (2) Medium |  | 2024-03-15 09:23 |  | FALSE |  | 2024-03-15 09:23 | Randy Opdyke | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Res Furnace Tune-up Typo | Question/Clarification |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-14 17:36 |  | FALSE | 5.3.13 Residential Furnace Tune-Up | 2024-03-14 17:36 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Ductless Heat Pump Demand Savings | Question/Clarification |  |  | Zach Obert | Franklin Energy |  | FALSE | Open | (2) Medium |  | 2024-03-14 17:33 |  | FALSE | 4.4.59 Ductless Heat Pumps | 2024-03-14 17:33 | Zach Obert | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
New | Electric Vehicles/EV Efficiency | New measure request |  |  | Nick Warnecke | Ameren |  | FALSE | Open | (2) Medium |  | 2024-03-13 10:36 |  | FALSE |  | 2024-03-13 10:36 | Nick Warnecke | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Correction to savings algorithm for fuel switching on large commercial water heaters | Correction of TRM mistake |  |  | Rob Parker | Michaels Energy |  | FALSE | Open | (2) Medium |  | 2024-03-07 10:39 |  | FALSE | 4.3.1 C&I Storage Water Heater | 2024-03-11 18:07 | Rob Parker | Item | sites/illinoistrm/Lists/RequestTracker | Errata
Exist | Baseline UPS efficiency tables are not valid at larger sizes | Correction of TRM mistake |  |  | Rob Parker | Michaels Energy |  | FALSE | Open | (2) Medium |  | 2024-03-11 18:07 |  | FALSE | 4.8.18 ENERGY STAR Uninterruptible Power Supply | 2024-03-11 18:07 | Rob Parker | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Update Res HP Measure Factors | Change to existing measure |  |  | Andrey Gribovich | DNV |  | FALSE | Open | (2) Medium |  | 2024-03-07 11:12 |  | FALSE | 5.3.1 RES Air Source Heat Pump | 2024-03-11 15:25 | Andrey Gribovich | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
Exist | Use Standard Algebraic Expressions | Question/Clarification |  |  | Sara Castleberry | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-07 13:40 |  | FALSE |  | 2024-03-07 13:40 | Sara Castleberry | Item | sites/illinoistrm/Lists/RequestTracker | Formatting - may be worth waiting to see if we change format
Exist | Label Equations and Tables | Question/Clarification |  |  | Sara Castleberry | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2024-03-07 12:03 |  | FALSE |  | 2024-03-07 12:03 | Sara Castleberry | Item | sites/illinoistrm/Lists/RequestTracker | Formatting - may be worth waiting to see if we change format
Exist | Apply Res HP Methodology to Commercial Measure | Change to existing measure |  |  | Andrey Gribovich | DNV |  | FALSE | Open | (2) Medium |  | 2024-03-07 11:10 |  | FALSE | 4.4.9 C&I Heat Pump Systems | 2024-03-07 11:12 | Andrey Gribovich | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump | Duplicate
New | New Measure- Zero Energy Refrigerated Case Doors | New measure request |  | 4.6 C&I Refrigeration End Use | Gert Schmitt | Leidos |  | FALSE | Open | (2) Medium |  | 2024-03-06 13:27 |  | FALSE |  | 2024-03-06 14:04 | Travis Hinck | Item | sites/illinoistrm/Lists/RequestTracker | May be able to add to existing measure with different baseline
Exist | Integrated Variable Frequency Drives | Change to existing measure |  |  | Travis Hinck | GDS Associates |  | FALSE | Open | (2) Medium |  | 2024-03-06 14:04 |  | FALSE | 4.4.26 C&I Variable Speed Drivers for HVAC Supply and Return Fans | 2024-03-06 14:04 | Travis Hinck | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Review climate data and assumptions | Change to existing measure |  |  | Sam Dent | VEIC |  | FALSE | Open | (2) Medium |  | 2022-11-15 08:36 |  | FALSE |  | 2024-02-20 06:02 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker | Commercial modeling
Exist | Clarification to Retention Rate and a Wave with Negative Savings | Change to existing measure |  |  | Carly Olig | Guidehouse |  | FALSE | Open | (2) Medium |  | 2024-01-23 11:55 |  | FALSE | 6.1 Behavior | 2024-01-23 11:55 | Courtney Golino | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Update gas & electric space heat and DHW assumptions using implementation contractor data. | Change to existing measure |  |  | Thomas Manjarres | Peoples Gas and North Shore Gas |  | FALSE | Open | (1) High |  | 2023-10-31 10:37 |  | FALSE |  | 2023-10-31 10:37 | Thomas Manjarres | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Update unknown assumptions for space heat & water heating | Change to existing measure |  |  | Thomas Manjarres | Peoples Gas and North Shore Gas |  | FALSE | Open | (1) High |  | 2023-10-20 18:07 |  | FALSE |  | 2023-10-31 10:29 | Thomas Manjarres | Item | sites/illinoistrm/Lists/RequestTracker
Exist | 4.6.8 - Refrigeration Economizers | Question/Clarification |  |  | Dimitry Burdjalov | Applied Energy Group |  | FALSE | Open | (2) Medium |  | 2023-10-04 01:26 |  | FALSE | 4.6.8 C&I Refrigeration Economizers | 2023-10-04 01:26 | Dimitry Burdjalov | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Electric Pasta Cookers | Change to existing measure | 4.2.17 C&I Pasta Cooker |  | Houston Dowen | Frontier Energy | 2023-05-14 | FALSE | Open | (1) High |  | 2023-03-13 23:41 |  | FALSE | 4.2.17 C&I Pasta Cooker | 2023-05-18 15:32 | Houston Dowen | Item | sites/illinoistrm/Lists/RequestTracker
Exist | Update gas heating measures to apply to hybrid gas + electric heat pump configurations | Change to existing measure | 5.3 RES HVAC End Use |  | Thomas Manjarres | Peoples Gas and North Shore Gas |  | FALSE | Open | (2) Medium |  | 2023-05-17 17:33 |  | FALSE | 5.3 RES HVAC End Use | 2023-05-17 17:33 | Administrator | Item | sites/illinoistrm/Lists/RequestTracker | Heat Pump
New | NEW Measure: Range Oven | New measure request |  | 4.2 C&I Food Service Equipment End Use | Houston Dowen | Frontier Energy |  | TRUE | Open | (1) High |  | 2023-03-14 18:40 |  | FALSE |  | 2023-05-15 01:01 | Houston Dowen | Item | sites/illinoistrm/Lists/RequestTracker
Exist | IQ Systematic Review | Change to existing measure |  |  | Kalee Whitehouse | VEIC |  | FALSE | Open | (2) Medium |  | 2023-03-22 09:13 |  | FALSE |  | 2023-03-22 09:13 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
New | ENERGY STAR Doors | New measure request | 5.6 RES Shell End Use |  | Jason Fegley | Leidos |  | FALSE | Open | (2) Medium |  | 2023-03-15 12:41 |  | FALSE | 5.6 RES Shell End Use | 2023-03-15 12:41 | David Kilgore | Item | sites/illinoistrm/Lists/RequestTracker
New | High Lumen Screw Based Garage Lights | New measure request | 5.5 RES Lighting End Use |  | Jason Fegley | Leidos |  | FALSE | Open | (2) Medium |  | 2023-03-14 22:15 |  | FALSE | 5.5 RES Lighting End Use | 2023-03-14 22:15 | David Kilgore | Item | sites/illinoistrm/Lists/RequestTracker
New | NEW Measure: Induction Soup Well | New measure request |  | 4.2 C&I Food Service Equipment End Use | Houston Dowen | Frontier Energy |  | TRUE | Open | (2) Medium |  | 2023-03-14 18:41 |  | FALSE |  | 2023-03-14 18:41 | Houston Dowen | Item | sites/illinoistrm/Lists/RequestTracker
New | Fireplace measure | New measure request |  | 5.3 Residential HVAC End Use | Haley Keegan | Resource Innovations |  | FALSE | Open | (2) Medium |  | 2023-03-14 11:58 |  | FALSE |  | 2023-03-14 11:58 | Haley Keegan | Item | sites/illinoistrm/Lists/RequestTracker
New | Hot Food Holding Bins | New measure request |  | 4.2 C&I Food Service Equipment End Use | Houston Dowen | Frontier Energy | 2023-05-14 | FALSE | Open | (1) High |  | 2023-03-13 23:43 |  | FALSE |  | 2023-03-13 23:43 | Houston Dowen | Item | sites/illinoistrm/Lists/RequestTracker
New | Electric Rotisseries | New measure request |  | 4.2 C&I Food Service Equipment End Use | Houston Dowen | Frontier Energy | 2023-05-14 | FALSE | Open | (1) High |  | 2023-03-13 23:43 |  | FALSE |  | 2023-03-13 23:43 | Houston Dowen | Item | sites/illinoistrm/Lists/RequestTracker
Exist | 5.7.4 Heat Pump Pool Heater Update | Change to existing measure | 5.7 RES Miscellaneous End Use |  | Rebecca McNish | ComEd |  | FALSE | Open | (2) Medium |  | 2023-03-10 11:39 |  | FALSE | 5.7 RES Miscellaneous End Use | 2023-03-10 11:40 | Administrator | Item | sites/illinoistrm/Lists/RequestTracker
Exist | IQ Behavior program - Enhanced Energy Education | Change to existing measure |  |  | Annette Beitel | IQ Working Group |  | FALSE | Open | (2) Medium |  | 2022-03-23 06:27 |  | FALSE |  | 2022-03-23 06:27 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker | IQ Working Group
New | Commercial Air Curtain | New measure request |  | 4.7 C&I Miscellaneous End Use | Andy Vaughn | Leidos |  | FALSE | Open | (3) Low |  | 2022-03-02 07:08 |  | FALSE |  | 2022-03-02 07:08 | Andrew Vaughn | Item | sites/illinoistrm/Lists/RequestTracker
Exist | PROVISIONAL On Demand Package Sealer | New measure request |  | 4.2 C&I Food Service Equipment End Use | Michael Drennan | CLEAResult |  | TRUE | Open | (1) High |  | 2021-02-24 16:39 |  | FALSE |  | 2021-11-04 07:03 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker
Exist | PROVISIONAL Energy Efficient Gear Oils | New measure request |  | 4.7 C&I Miscellaneous End Use | Adam McMurtrey | ExxonMobil |  | FALSE | Open | (2) Medium |  | 2020-02-26 00:06 |  | FALSE |  | 2021-01-29 08:05 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker
Exist | PROVISIONAL Energy efficient hydraulic oils | New measure request |  |  | Adam McMurtrey | ExxonMobil |  | TRUE | Open | (2) Medium |  | 2020-02-25 08:49 |  | FALSE |  | 2021-01-29 08:05 | Sam Dent | Item | sites/illinoistrm/Lists/RequestTracker

## v13 Tracker Items
IL-TRM V13.0 - FINAL Measure Update Priority List
VEIC - April 1st, 2024
Sorted by Type (Existing then New measures) and then Measure Code/Section
Type | Request Summary | Measure Code (existing measure) Measure Section (new measures) | Requester Name | Requester Company | Market | Work paper Required | Workpaper Responsible Company | Proposed Working Group | Notes | Possible Errata | Workpaper loaded | VEIC Assignee | Status | Present to TAC? | Date Presented | Summary of Changes | Loaded to Sharepoint | In Memo
Exist | Discount and Inflation Rate updates | 3.11 Discount Rates, Inflation Rates, and O&M Costs | Sam Dent | VEIC | N/A | N
Exist | Identify availability of data to update Food Service assumptions | 4.2 Food Service Equipment End Use | Jessica Raker | Opinion Dynamics | C&I | Y | Opinion Dynamics
Exist | PROVISIONAL On Demand Package Sealer | 4.2.1 On-Demand Package Sealers | Michael Drennan | CLEAResult | C&I | Y | CLEAResult
Exist | Correction to Commercial Steam Cooker calculations | 4.2.3 C&I Commercial Steam Cooker | Tyler Sellner | Opinion Dynamics | C&I | N |  |  |  | Y
Exist | Correct Commercial Steam Cooker Demand /CF | 4.2.3 C&I Commercial Steam Cooker | Tyler Sellner | Opinion Dynamics | C&I | N
Exist | Correction to savings algorithm for fuel switching on large commercial water heaters | 4.3.1 Water Heater | Rob Parker | Michaels Energy | C&I | N |  |  |  | Y
Exist | Residential Electric Water Heater | 4.3.1 Water Heater | Courtney Golino & Ridhi Kalra | Guidehouse | C&I | Y | Guidehouse
Exist | DHW Boiler Tune-up - Additional HW Gal/Year Option | 4.3.10 DHW Boiler Tune-up | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy
Exist | Electric Chillers (IL TRM v12, 4.4.6) | 4.4.6 C&I Electric Chiller | Sri Paruchuri | Resource Innovations | C&I | Y | Resource Innovations
Exist | Commercial Chillers | 4.4.6 Electric Chiller | Josh Sharon | ComEd | C&I |  |  |  | Policy/Volume 4 Issue?
Exist | Commercial Heat Pumps | 4.4.9 C&I Heat Pump Systems | Josh Sharon | ComEd | C&I | Y | ComEd | Heat Pump
Exist | Apply Res HP Methodology to Commercial Measure | 4.4.9 C&I Heat Pump Systems | Andrey Gribovich | DNV | C&I | Y | DNV | Heat Pump
Exist | Clarify efficiency calculation for commercial boilers and furnaces | 4.4.10 C&I High Efficiency Boiler | Wade Morehead | Morehead Energy on behalf of Ameren IL | C&I | N
Exist | Integrated Variable Frequency Drives | 4.4.26 C&I Variable Speed Drivers for HVAC Supply and Return Fans | Travis Hinck | GDS Associates | C&I | Y | GDS Associates
Exist | ERV Update for 2021 IECC Code | 4.4.27 Energy Recovery Ventilator | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy
Exist | Combined Heat and Power | 4.4.32 Combined Heat and Power | Sam Dent | VEIC | C&I |  |  | Combined Heat and Power | Following TAC call - this is likely to be removed and Working Group not be active again this year.
Exist | Room AC Covers - Algorithm Modification for Number of Floors | 4.4.38 Covers and Gap Sealers for Room Air Conditioners | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy
Exist | Advanced Rooftop Controls with High Rotor Pole Switch Reluctance Motors | 4.4.51 Advanced Rooftop Controls with High Rotor Pole Switch Reluctance Motors | Ryan Kroll | Driftless Energy/Guidehouse | C&I | Y | Driftless Energy/Guidehouse
Exist | Ductless Heat Pump Demand Savings | 4.4.59 Ductless Heat Pumps | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy | Heat Pump
Exist | 4.6.8 - Refrigeration Economizers | 4.6.8 C&I Refrigeration Economizers | Dimitry Burdjalov | Applied Energy Group | C&I | Y | Applied Energy Group
Exist | High Speed Clothes Washers - Additional Options | 4.8.5 High Speed Clothes Washer | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy
Exist | Data Center Efficient UPS/(Uninterruptible Power Supply) | 4.8.18 ENERGY STAR Uninterruptible Power Supply | Sri Paruchuri | Resource Innovations | C&I | Y | Resource Innovations
Exist | Baseline UPS efficiency tables are not valid at larger sizes | 4.8.18 ENERGY STAR Uninterruptible Power Supply | Rob Parker | Michaels Energy | C&I | Y | Michaels Energy
Exist | PROVISIONAL Energy efficient hydraulic oils | 4.8.20 Energy Efficient Hydraulic Oils | Adam McMurtrey | ExxonMobil | C&I | Y | ExxonMobil
Exist | PROVISIONAL Energy Efficient Gear Oils | 4.8.21 Energy Efficient Gear Lubricants | Adam McMurtrey | ExxonMobil | C&I | Y | ExxonMobil
Exist | Update Air Purifier for ENERGY STAR market conditions and DOE Conservation Standard | 5.1.1 RES ENERGY STAR Air Purifier/Cleaner | Seth Craigo-Snell | SCS ANALYTICS in support of Ameren Illinois | RES | Y | SCS ANALYTICS in support of Ameren Illinois
Exist | Update Dehumidifier ENERGY STAR market conditions and consider adding whole-home | 5.1.3 RES ENERGY STAR Dehumidifier | Seth Craigo-Snell | SCS ANALYTICS in support of Ameren Illinois | RES | Y | SCS ANALYTICS in support of Ameren Illinois |  | Duplicate with below
Exist | Possibly merge 5.1.7 and 5.1.13 for Room AC | 5.1.7 ENERGY STAR Room Air Conditioner | Zach Obert | Franklin Energy | RES | Y | Franklin Energy
Exist | ENERGY STAR Clothes Dryer | 5.1.10 ENERGY STAR Clothes Dryer | Bobbi Fey | ICF | RES | Y | ICF
Exist | Residential TRM Incremental Cost Data Assumption Review and update - Residential HVAC (Gas and Electric) End Uses Space heating, Water Heating and cooking | 5.3 RES HVAC End Use | Randy Opdyke | Nicor Gas | RES | Y | Nicor Gas
Exist | Update gas heating measures to apply to hybrid gas + electric heat pump configurations | 5.3 RES HVAC End Use | Thomas Manjarres | Peoples Gas and North Shore Gas | RES | Y | Peoples Gas and North Shore Gas | Heat Pump
Exist | Radon Mitigation - Energy Star fans | 5.3 HVAC End Use | David Kilgore | Leidos on behalf of Ameren Illinois | RES | Y | Leidos on behalf of Ameren Illinois | IQ Working Group
Exist | Update gas & electric space heat and DHW assumptions using implementation contractor data. | 5.3 HVAC End Use | Thomas Manjarres | Peoples Gas and North Shore Gas | RES | Y | Peoples Gas and North Shore Gas
Exist | Update unknown assumptions for space heat & water heating | 5.3 HVAC End Use | Thomas Manjarres | Peoples Gas and North Shore Gas | RES | Y | Peoples Gas and North Shore Gas
Exist | Residential Heat Pump | 5.3.1 RES Air Source Heat Pump | Josh Sharon | ComEd | RES | Y | ComEd | Heat Pump
Exist | Update Heat Pump measure for simultaneous operation | 5.3.1 RES Air Source Heat Pump | Wade Morehead | Morehead Energy on behalf of Ameren IL | RES | Y | Morehead Energy on behalf of Ameren IL | Heat Pump
Exist | Clarify treatment of zone-specific Residential Heat Pumps | 5.3.1 RES Air Source Heat Pump | Jessica Raker | Opinion Dynamics | RES | Y | Opinion Dynamics | Heat Pump
Exist | Update Res HP Measure Factors | 5.3.1 RES Air Source Heat Pump | Andrey Gribovich | DNV | RES | Y | DNV | Heat Pump
Exist | CAC for Mobile Homes | 5.3.3 RES Central Air Conditioning > 14.5 SEER | David Kilgore | Leidos on behalf of Ameren Illinois | RES | Y | Leidos on behalf of Ameren Illinois | IQ Working Group
Exist | Update HVAC Tune-up Measure | 5.3.10 RES HVAC Tune Up (Central Air Conditioning | Zach Ross | Opinion Dynamics | RES | Y | Opinion Dynamics | IQ Working Group
Exist | HVAC Tune-Up Measure Adjust | 5.3.10 HVAC Tune Up | David Kilgore | Leidos on behalf of Ameren Illinois | RES | Y | Leidos on behalf of Ameren Illinois | IQ Working Group
Exist | Res Furnace Tune-up Typo | 5.3.13 Residential Furnace Tune-Up | Zach Obert | Franklin Energy | RES | N
Exist | Update to ISR For Self-install Smart Thermostats with no verification | 5.3.16 Advanced Thermostats | Sam Lamos | Opinion Dynamics | RES | Y | Opinion Dynamics
Exist | Possible issue in HPWH measure and calculation of sensible/latent heat impacts | 5.4.3 RES Heat Pump Water Heaters | Sam Dent | VEIC | RES | Y | SCS ANALYTICS in support of Ameren Illinois
Exist | Update Showerhead GPM Low Table | 5.4.5 RES Low Flow Showerheads | Alex Caratti | Opinion Dynamics | RES | Y | Opinion Dynamics
Exist | 5.6.8 High Performance Windows Update | 5.6.8 Triple Pane and Thin Triple Windows | Randy Opdyke/Brady Nemeth | Nicor Gas/Resource Innovations | RES | Y | Nicor Gas/Resource Innovations
Exist | 5.7.4 Heat Pump Pool Heater Update | 5.7 RES Miscellaneous End Use | Rebecca McNish | ComEd | RES | Y | ComEd
Exist | Clarification to Retention Rate and a Wave with Negative Savings | 6.1 Behavior | Carly Olig | Guidehouse | RES | Y | Guidehouse
Exist | IQ Behavior program - Enhanced Energy Education | 6.1 Behavior | Annette Beitel | IQ Working Group | RES | Y | IQ Working Group | IQ Working Group
Exist | Code and Standard Updates | Multiple | Sam Dent | VEIC | C&I, RES | Y | VEIC |  | Residential CW, Room AC and C&I Room AC
Exist | EUL assumptions for IQ populations | Multiple | IQ Working Group |  | RES | Y |  | IQ Working Group
Exist | Multifmaily Common Use Spaces | Multiple | Sara Castleberry | RI | C&I | Y | RI
Exist | Define DI installation guidelines | Multiple | Jessica Raker | Opinion Dynamics | RES | Y | Opinion Dynamics
Exist | Add Calculation examples to more measures | Multiple | Jessica Raker | Opinion Dynamics | C&I, RES | Y | Opinion Dynamics
Exist | Use Standard Algebraic Expressions | Multiple | Sara Castleberry | Resource Innovations | C&I, RES | Y | Resource Innovations |  | Formatting issue - will consider through TRM Format update process. Note ticket describes formula error to be fixed.
Exist | Label Equations and Tables | Multiple | Sara Castleberry | Resource Innovations | C&I, RES | Y | Resource Innovations |  | Formatting issue - will consider through TRM Format update process.
Exist | Review climate data and assumptions | Multiple | Sam Dent | VEIC | C&I | Y | VEIC |  | Commercial modeling
Exist | IQ Systematic Review | Multiple | Kalee Whitehouse | VEIC | RES | Y | VEIC | IQ Working Group
Exist | Heat Pump Market Adder | Volume 4? | Josh Sharon / Richard Tonielli | ComEd | RES | Y | ComEd |  | Policy/Volume 4 Issue?
New | Commercial Water Heater Timer | 4.3 Hot Water End Use | Wade Morehead | Morehead Energy on behalf of Ameren IL | C&I | Y | Morehead Energy on behalf of Ameren IL
New | Thermal Energy Storage System | 4.4 C&I HVAC End Use | Alex Smillie | Trane | C&I | Y | Trane
New | Computer Room Air Conditioner (CRAC) | 4.4 HVAC End Use | Sri Paruchuri | Resource Innovations | C&I | Y | Resource Innovations
New | Add Measure for Steam Leak Fix-it-Now | 4.4 HVAC End Use | Zach Obert | Franklin Energy | C&I | Y | Franklin Energy
New | Efficient Rooftop Unit | 4.4 HVAC End Use | Randy Opdyke | Nicor Gas/Resource Innovations | C&I | Y | Nicor Gas/Resource Innovations
New | Door Gaskets for Walk-in and Reach-in Coolers and Freezers | 4.6 Refrigeration End Use | Sanjyot Varade | Resource Innovations | C&I | Y | Resource Innovations
New | New Measure- Zero Energy Refrigerated Case Doors | 4.6 Refrigeration End Use | Gert Schmitt | Leidos | C&I | Y | Leidos |  | May be able to add to existing measure with different baseline
New | Elevator Modernization | 4.8 Miscellaneous End Use | Sri Paruchuri | Resource Innovations | C&I | Y | Resource Innovations
New | (4.8.New) Commercial Secondary Windows | 4.8 Miscellaneous End Use | Randy Opdyke/Ramanathan Dharmarajan | Nicor Gas/GTI Energy | C&I | Y | Nicor Gas/GTI Energy
New | Commercial Air Curtain | 4.8 Miscellaneous End Use | Andy Vaughn | Leidos | C&I | Y | Leidos
New | All-in-one Washer/Electric Dryer and All-in-One Washer/Heat Pump Dryer | 5.1 Residential Appliances End Use | Bobbi Fey | ICF | RES | Y | ICF |  | Two tickets combined
New | Laundry Center | 5.1 Residential Appliances End Use | Bobbi Fey | ICF | RES | Y | ICF
New | Add Measure for Residential Duct Insulation | 5.3 HVAC End Use | Zach Obert | Franklin Energy | RES | Y | Franklin Energy
New | Portable Heat Pumps | 5.3 HVAC End Use | Andy Vaughn | Leidos on behalf of Ameren Illinois | RES | Y | Leidos on behalf of Ameren Illinois | IQ Working Group
New | Add Measure for Auto Diverting Tub Spout System | 5.4 Hot Water End Use | Zach Obert | Franklin Energy | RES | Y | Franklin Energy
New | High Lumen Screw Based Garage Lights | 5.5 RES Lighting End Use | Jason Fegley | Leidos | RES | Y | Leidos
New | Cordless pruners | 5.7 RES Miscellaneous End Use | Bobbi Fey | ICF | RES | Y | ICF
New | Pruning chainsaws | 5.7 RES Miscellaneous End Use | Bobbi Fey | ICF | RES | Y | ICF
New | Electric Vehicles/EV Efficiency | 5.7 Miscellaneous End Use | Nick Warnecke | Ameren | RES | Y | Ameren

## 2024 Reliability Review
Utility Programs (Mark "X" measures not offered, and "Low" measures with low expected volume)
Measure # | Measure Name | Proposed Priority Level | Reason | Sunset Date | ComEd | Ameren | Nicor | Peoples & North Shore Gas
4.1.11 | Commercial LED Grow Lights | Medium | Recent review | 2024-01-01 |  |  | x | x
4.1.13 | Irrigation Pump VFD | Medium | 3 years since last review | 2025-01-01 |  | Low | x | x
4.1.14 | High Efficiency Grain Dryer | Low | Low participation | 2025-01-01 | x | Low | Low | x
4.1.15 | Grain Dryer Tune-Up | Low | Low participation | 2025-01-01 | x | x | Low | x
4.1.16 | Greenhouse Boiler Tune-Up | Medium | 3 years since last review | 2025-01-01 | x | Low | Low
4.1.17 | Greenhouse Thermal Curtains | Low | Low participation | 2025-01-01 | x | Low | Low | Low
4.1.18 | Infrared Film for Greenhouse | Low | Low participation | 2025-01-01 | x | Low | Low | Low
4.1.19 | ENERGY STAR Dairy Water Heater | Low | Low participation | 2025-01-01 | x | Low | Low | Low
4.2.21 | On-Demand Package Sealers - Provisional | No reliability | Already tracker item - Provisional measure | 2025-01-01 |  | Low | x | x
4.3.3 | Low Flow Showerheads | Medium | 2 years since last review | 2024-01-01 |  | Low
4.3.4 | Commercial Pool Covers | Low | Low participation | 2025-01-01 | x | Low | Low | Low
4.3.7 | Multifamily Central Domestic Hot Water Plants | Medium | 2 years since last review | 2025-01-01 | x | Low
4.4.1 | Air Conditioner Tune-up | High | 4 years since last review | 2025-01-01 |  | x | x | x
4.4.2 | Space Heating Boiler Tune-up | High | 4 years since last review | 2025-01-01 | x
4.4.7 | ENERGY STAR and CEE Super Efficient Room Air Conditioner | Low | Low participation | 2025-01-01 | x | Low | x | x
4.4.12 | Infrared Heaters (all sizes), Low Intensity | Medium | 2 years since last review | 2025-01-01 | x | Low | Low
4.4.14 | Pipe Insulation | Medium | 2 years since last review | 2024-01-01 | ? | Low
4.4.16 | Steam Trap Replacement or Repair | Low | Recent review | 2025-01-01 | x
4.4.17 | Variable Speed Drives for HVAC Pumps and Cooling Tower Fans | Low | Recent review | 2025-01-01 |  |  | x | x
4.4.20 | High Turndown Burner for Space Heating Boilers | Medium | 2 years since last review | 2024-01-01 | x | Low | Low
4.4.28 | Stack Economizer for Boilers Serving HVAC Loads | Low | Low participation | 2025-01-01 | x | x | Low | Low
4.4.32 | Combined Heat and Power | No reliability | Already tracker item | 2025-01-01 | x |  | Low | Low
4.4.33 | Industrial Air Curtain | Medium | 2 years since last review | 2024-01-01 | x | Low | Low
4.4.34 | Destratification Fan | Medium | 2 years since last review | 2025-01-01 | x | Low | Low
4.4.44 | Commercial Ground Source and Ground Water Source Heat Pump | High | Review against other HP measures | 2025-01-01 |  | Low | x | x
4.4.46 | Server Room Temperature Set back | No reliability | No utility program | 2024-01-01 | x | x | x | x
4.4.51 | Advanced Rooftop Controls with High Rotor Pole Switch | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.4.53 | HVAC Supply, Return and Exhaust Fans - Fan Energy Index | Medium | 2 years since last review | 2025-01-01 | x | Low | x
4.4.55 | Commercial Gas Heat Pump | Low | Low participation | 2025-01-01 | x | x | Low | Low
4.4.58 | Steam Trap Monitoring System | Medium | 2 years since last review | 2025-01-01 | x |  | Low
4.4.59 | Ductless Heat Pump | No reliability | Already tracker item | 2025-01-01 |  |  | x | x
4.4.61 | Chiller Condenser Water Temperature Reset | Low | Low participation | 2025-01-01 | x | Low | x | x
4.4.62 | Cooling Tower Water Side Economizer | Low | Low participation | 2025-01-01 | x | Low | x | x
4.5.3 | High Performance and Reduced Wattage T8 Fixtures and Lamps | No reliability | No utility program - retire? | 2025-01-01 | x | x | x | x
4.5.7 | Lighting Power Density | No reliability | Code related measure | 2024-01-01 |  |  | x | x
4.5.9 | Multi-Level Lighting Switch | Medium | 2 years since last review | 2025-01-01 |  | x | x | x
4.5.11 | Solar Light Tubes | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.5.12 | T5 Fixtures and Lamps | No reliability | No utility program - retire? | 2025-01-01 | x | x | x | x
4.5.13 | Occupancy Controlled Bi-Level Lighting Fixtures | Medium | 2 years since last review | 2025-01-01 |  | Low | x | x
4.5.16 | LED Streetlighting | Medium | 2 years since last review | 2025-01-01 | x |  | x | x
4.5.17 | Exterior Photocell Repair | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.6.2 | Beverage and Snack Machine Controls | Medium | 3 years since last review | 2025-01-01 |  | x | x | x
4.6.4 | Electronically Commutated Motors (ECM) for Walk-in and Reach-in Coolers / Freezers | Medium | 3 years since last review | 2025-01-01 |  |  | x | x
4.6.5 | ENERGY STAR Refrigerated Beverage Vending Machine | Low | Low participation | 2025-01-01 | x | Low | x | x
4.6.6 | Evaporator Fan Control for Electrically Commutated Motors | Medium | 3 years since last review | 2025-01-01 |  |  | x | x
4.6.12 | Variable Speed Drive for Condenser Fans | High | 5+ years since last review | 2025-01-01 |  |  | x | x
4.6.13 | Add Doors to Open Refrigerated Display Cases | Medium | 3 years since last review | 2025-01-01 |  |  | x | x
4.7.3 | Compressed Air No-Loss Condensate Drains | High | 5+ years since last review | 2025-01-01 |  |  | x | x
4.7.12 | AODD Pump Controls | Low | Low participation | 2025-01-01 | x | Low | x | x
4.8.3 | Computer Power Management Software | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.8.6 | ENERGY STAR Computers | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.8.8 | High Efficiency Transformer | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.8.9 | High Frequency Battery Chargers | High | 4 years since last review | 2025-01-01 |  |  | x | x
4.8.13 | Variable Speed Drives for Process Fans | Medium | 2 years since last review | 2025-01-01 |  |  | x | x
4.8.14 | Low Flow Toilets and Urinals | No reliability | No utility program | 2023-01-01 | x | x | x | x
4.8.15 | Smart Irrigation Controls | No reliability | No utility program | 2025-01-01 | x | x | x | x
4.8.20 | Energy Efficient Hydraulic Oils - Provisional | No reliability | Already tracker item - Provisional measure | 2023-01-01 | x | Low | x | x
4.8.21 | Energy Efficient Gear Lubricants - Provisional | No reliability | Already tracker item - Provisional measure | 2023-01-01 | x | Low | x | x
4.8.22 | Smart Sockets | Medium | 3 years since last review | 2025-01-01 |  | Low | x | x
4.8.23 | Lithium Ion Forklift Batteries | Medium | 2 years since last review | 2025-01-01 |  |  | x | x
4.8.24 | Building Operator Certification | Medium | 2 years since last review | 2024-01-01 |  |  | Low
4.8.25 | Warm-Mix Asphalt Chemical Additives | Low | Low participation | 2025-01-01 | x | Low | Low | x
5.1.1 | ENERGY STAR Air Purifier/Cleaner | Medium | 2 years since last review | 2025-01-01 |  |  | x | x
5.1.2 | ENERGY STAR Clothes Washers | Medium | 2 years since last review | 2025-01-01 |  |  | x | x
5.1.3 | ENERGY STAR Dehumidifier | No reliability | Already tracker item | 2025-01-01 |  |  | x | x
5.1.4 | ENERGY STAR Dishwasher | Medium | 2 years since last review | 2025-01-01 | x |  | Low | x
5.1.7 | ENERGY STAR Room Air Conditioner | Medium | 2 years since last review | 2025-01-01 |  |  | x | x
5.1.8 | Refrigerator and Freezer Recycling | No reliability | No utility program | No active programs. | x | x | x | x
5.1.9 | Room Air Conditioner Recycling | Medium | 2 years since last review | 2025-01-01 |  | Low | x | x
5.1.15 | Residential Bolt-On Smart Dryer Sensor | Medium | 2 years since last review | 2025-01-01 | x | x | x
5.2.1 | Advanced Power Strip – Tier 1 | Medium | 3 years since last review | 2025-01-01 |  |  | x | x
5.2.3 | ENERGY STAR Televisions | Low | Low participation | 2025-01-01 | x | Low | x | x
5.3.1 | Air Source Heat Pump | No reliability | Already tracker item | 2025-01-01 |  |  | x | x
5.3.2 | Boiler Pipe Insulation | Medium | 3 years since last review | 2025-01-01 | x | x | Low
5.3.7 | Gas High Efficiency Furnace | Medium | 2 years since last review | 2025-01-01 | x
5.3.10 | HVAC Tune Up (Central Air Conditioning or Air Source Heat Pump) | No reliability | Already tracker item | 2025-01-01 |  | x | Low | x
5.3.11 | Programmable Thermostats | Medium | 3 years since last review | 2025-01-01 |  | x | Low
5.3.13 | Residential Furnace Tune-Up | Medium | 2 years since last review | 2025-01-01 | x | x | Low
5.3.19 | Thermostatic Radiator Valves - Provisional | No reliability | Already tracker item - Provisional measure | 2023-01-01 | x | x | x | x
5.3.20 | Residential Energy Recovery Ventilator | Low | Low participation | 2025-01-01 | x | Low | Low | x
5.3.21 | Air Handler Filter Cleaning/Replacement | Low | Low participation | 2025-01-01 | x | x | Low | x
5.4.1 | Domestic Hot Water Pipe Insulation | Medium | 2 years since last review | 2025-01-01
5.4.2 | Gas Water Heater | High | Potential Federal Standard update | 2025-01-01 | x |  | Low
5.4.3 | Heat Pump Water Heaters | High | Potential Federal Standard update | 2025-01-01 |  |  | x
5.4.4 | Low Flow Faucet Aerators | Medium | 2 years since last review | 2025-01-01
5.4.5 | Low Flow Showerheads | Medium | 2 years since last review | 2025-01-01
5.4.8 | Thermostatic Restrictor Shower Valve | Medium | 2 years since last review | 2023-01-01 | x |  | Low | Low
5.4.12 | Recirculating Pump Controls | Medium | 2 years since last review | 2025-01-01 | x | x | Low
5.5.10 | Holiday String Lighting | Low | Low participation | 2025-01-01 | x | Low | x | x
5.5.11 | LED Nightlights | High | 5+ years since last review | 2025-01-01 |  |  | x | x
5.6.2 | Basement Sidewall Insulation | Medium | 2 years since last review | 2025-01-01 |  |  | Low
5.6.3 | Floor Insulation Above Crawlspace | Medium | 2 years since last review | 2025-01-01 |  |  | Low
5.6.4 | Wall Insulation | Medium | 2 years since last review | 2025-01-01 |  |  | Low
5.6.5 | Ceiling/Attic Insulation | Medium | 2 years since last review | 2025-01-01
5.6.6 | Rim/Band Joist Insulation | Medium | 2 years since last review | 2025-01-01 |  |  | Low
5.7.1 | High Efficiency Pool Pumps | Medium | 3 years since last review | 2025-01-01 | x |  | Low | x
5.7.2 | Low Flow Toilets | Low | Low participation | 2023-01-01 | x | Low | x | x
5.7.3 | Level 2 Electric Vehicle Charger | Low | Low participation | 2025-01-01 | x | Low | x | x
5.7.5 | Tree Planting | Medium | 2 years since last review | 2025-01-01 | x |  | x | x